## Sheet1
REGION | PROVINCES | CITY/MUNICIPALITY | 2018 SALINTUBIG
|  |  | NO. OF PROJECTS | ALLOCATION | STATUS AS OF DECEMBER 2018 | STATUS AS OF FEBRUARY 2019
REGION X | BUKIDNON | CABANGLASAN | 1 | 2 | On-going Construction | On-going Construction
REGION X | BUKIDNON | DANGCAGAN | 1 | 10 | DED and POW finalization | DED and POW finalization
REGION X | BUKIDNON | TALAKAG | 1 | 10 | Procurement process | Procurement process
REGION X | CAMIGUIN | SAGAY | 1 | 2 | Delivery of Materials | Delivery of Materials
REGION X | LANAO DEL NORTE | BACOLOD |  | 3 | DED and POW preparation | DED and POW preparation
REGION X | LANAO DEL NORTE | KAUSWAGAN | 2 | 5 | DED and POW preparation | DED and POW preparation
REGION X | LANAO DEL NORTE | LALA | 1 | 12 | Procurement process | Procurement process
REGION X | LANAO DEL NORTE | MAGSAYSAY | 1 | 10 | DED and POW finalization | DED and POW finalization
REGION X | LANAO DEL NORTE | SULTAN NAGA DIMAPORO | 3 | 8 | 2-Procurement Process | 2-On-going Construction
[5 empty] | 1-On-going Construction | 1-Procurement Process
REGION X | LANAO DEL NORTE | TUBOD | 3 | 8 | Procurement process | Procurement process
REGION X | MISAMIS OCCIDENTAL | ALORAN | 3 | 8 | 2-Procurement process | 2-Procurement process
[5 empty] | 1-DED and POW finalization | 1-DED and POW finalization
REGION X | MISAMIS OCCIDENTAL | BONIFACIO | 1 | 2 | On-going Construction | COMPLETED
REGION X | MISAMIS OCCIDENTAL | TUDELA | 2 | 6 | DED and POW finalization | DED and POW finalization
|  |  | 20 | 86
REGION | PROVINCE | CITY / MUNICIPALITY | 2018 ASSISTANCE TO MUNICIPALITIES (AM-WATER)
|  |  | NO. OF PROJECT | ALLOCATION | STATUS AS OF DECEMBER 2018 | STATUS AS FEBRUARY 2019
REGION X | BUKIDNON | BAUNGON | 1 | 5.7892 | Procurement process | Procurement process
REGION X | BUKIDNON | KALILANGAN | 1 | 6.0638 | Procurement process | Procurement process
REGION X | BUKIDNON | KITAOTAO | 1 | 7.7629 | CANCELLED | CANCELLED
REGION X | BUKIDNON | LANTAPAN | 1 | 6.6979 | Procurement process | Procurement process
REGION X | BUKIDNON | MANOLO FORTICH | 4 | 7.47 | Procurement process | Procurement process
REGION X | BUKIDNON | SAN FERNANDO | 1 | 6.4721 | On-going Construction | On-going Construction
REGION X | CAMIGUIN | SAGAY | 2 | 3.92 | On-going Construction | On-going Construction
REGION X | LANAO DEL NORTE | KAUSWAGAN | 2 | 0.43955 | Procurement process | Procurement process
REGION X | LANAO DEL NORTE | NUNUNGAN | 1 | 3.9999 | Procurement process | Procurement process
REGION X | LANAO DEL NORTE | PANTAR | 2 | 4 | On-going Construction | On-going Construction
REGION X | LANAO DEL NORTE | SULTAN NAGA DIMAPORO | 1 | 7.8232 | On-going Construction | On-going Construction
REGION X | MISAMIS OCCIDENTAL | JIMENEZ | 1 | 12.9877 | Procurement process | On-going Construction
REGION X | MISAMIS ORIENTAL | BINUANGAN | 1 | 15.2194 | Procurement process | Procurement process
REGION X | MISAMIS ORIENTAL | JASAAN | 1 | 9.2197 | Procurement process | Procurement process
REGION X | MISAMIS ORIENTAL | KINOGUITAN | 1 | 9.4721 | Procurement process | Procurement process
REGION X | MISAMIS ORIENTAL | LUGAIT | 1 | 7.9794 | DED and POW Preparation | DED and POW Preparation
REGION X | MISAMIS ORIENTAL | MANTICAO | 1 | 7.4126 | Procurement process | On-going Construction
REGION X | MISAMIS ORIENTAL | TAGOLOAN | 1 | 5.8092 | DED and POW Preparation | DED and POW Preparation
|  |  | 24 | 128.5387
REGION | PROVINCE | CITY / MUNICIPALITY | 2018 ASSISTANCE TO MUNICIPALITIES (AM-LAR)
|  |  | NO. OF PROJECT | ALLOCATION | STATUS AS OF DECEMBER 2018 | STATUS AS FEBRUARY 2019
REGION X | BUKIDNON | CABANGLASAN | 1 | 6.66 | On-going Construction | COMPLETED
REGION X | BUKIDNON | DAMULOG | 2 | 5.5 | On-going Construction | On-going Construction
REGION X | BUKIDNON | DANGCAGAN | 2 | 7.2 | On-going Construction | On-going Construction
REGION X | BUKIDNON | DON CARLOS | 1 | 7.9 | Procurement process | Procurement process
REGION X | BUKIDNON | IMPASUG-ONG | 1 | 6.2 | On-going Construction | COMPLETED
REGION X | BUKIDNON | KADINGILAN | 1 | 5.7 | On-going Construction | On-going Construction
REGION X | BUKIDNON | KIBAWE | 1 | 5.9 | On-going Construction | On-going Construction
REGION X | BUKIDNON | LIBONA | 1 | 8.8 | On-going Construction | On-going Construction
REGION X | BUKIDNON | MALITBOG | 1 | 5.4 | Procurement process | On-going Construction
REGION X | BUKIDNON | MARAMAG | 1 | 5.6 | Procurement process | Procurement process
REGION X | BUKIDNON | PANGANTUCAN | 2 | 6.4 | Procurement process | Procurement process
REGION X | BUKIDNON | QUEZON | 1 | 9.1 | On-going Construction | COMPLETED
REGION X | BUKIDNON | SUMILAO | 1 | 7.4 | On-going Construction | On-going Construction
REGION X | BUKIDNON | TALAKAG | 1 | 7.1 | Procurement process | Procurement process
REGION X | CAMIGUIN | CATARMAN | 1 | 5.1 | On-going Construction | On-going Construction
REGION X | CAMIGUIN | GUINSILIBAN | 1 | 7.7 | DED and POW for Review | DED and POW Finalization
REGION X | CAMIGUIN | MAHINOG | 5 | 5 | 3-On-going Construction | 1-On-going Construction
[5 empty] | 1-Procurement Process | 1-Procurement Process
REGION X | CAMIGUIN | MAMBAJAO (Capital) | 1 | 5.4 | Procurement process | On-going Construction
REGION X | CAMIGUIN | SAGAY | 1 | 4 | On-going Construction | On-going Construction
REGION X | LANAO DEL NORTE | BACOLOD | 1 | 5.4 | On-going Construction | On-going Construction
REGION X | LANAO DEL NORTE | BALOI | 2 | 6.5 | On-going Construction | On-going Construction
REGION X | LANAO DEL NORTE | BAROY | 1 | 6.6 | On-going Construction | On-going Construction
REGION X | LANAO DEL NORTE | KAPATAGAN | 1 | 14.1 | On-going Construction | On-going Construction
REGION X | LANAO DEL NORTE | KAUSWAGAN | 3 | 3 | On-going Construction | On-going Construction
REGION X | LANAO DEL NORTE | KOLAMBUGAN | 1 | 12.1 | Procurement process | On-going Construction
REGION X | LANAO DEL NORTE | LALA | 1 | 9.3 | On-going Construction | On-going Construction
REGION X | LANAO DEL NORTE | LINAMON | 3 | 12.1 | 2-On-going Construction | 1-COMPLETED
[5 empty] | 1-Procurement Process | 2-On-going Construction
REGION X | LANAO DEL NORTE | MAGSAYSAY | 1 | 5.1 | On-going Construction | On-going Construction
REGION X | LANAO DEL NORTE | MAIGO | 1 | 5.3 | Procurement process | Procurement process
REGION X | LANAO DEL NORTE | MATUNGAO | 1 | 5 | Procurement process | On-going Construction
REGION X | LANAO DEL NORTE | MUNAI | 1 | 5.6 | On-going Construction | On-going Construction
REGION X | LANAO DEL NORTE | PANTAO RAGAT | 1 | 5.4 | On-going Construction | On-going Construction
REGION X | LANAO DEL NORTE | PANTAR | 1 | 4.4 | COMPLETED | COMPLETED
REGION X | LANAO DEL NORTE | POONA PIAGAPO | 1 | 5.4 | Procurement process | Procurement process
REGION X | LANAO DEL NORTE | SALVADOR | 1 | 6.9 | On-going Construction | On-going Construction
REGION X | LANAO DEL NORTE | SAPAD | 1 | 6.6 | COMPLETED | COMPLETED
REGION X | LANAO DEL NORTE | TAGOLOAN | 1 | 6.8 | DED and POW Preparation | DED and POW Preparation
REGION X | LANAO DEL NORTE | TANGCAL | 1 | 5 | On-going Construction | On-going Construction
REGION X | LANAO DEL NORTE | TUBOD | 1 | 12.9 | On-going Construction | On-going Construction
REGION X | MISAMIS OCCIDENTAL | ALORAN | 1 | 12.2 | Procurement process | Procurement process
REGION X | MISAMIS OCCIDENTAL | BALIANGAO | 1 | 5.1 | Procurement process | On-going Construction
REGION X | MISAMIS OCCIDENTAL | BONIFACIO | 1 | 7 | COMPLETED | COMPLETED
REGION X | MISAMIS OCCIDENTAL | CALAMBA | 1 | 6.2 | On-going Construction | On-going Construction
REGION X | MISAMIS OCCIDENTAL | CLARIN | 1 | 6.8 | On-going Construction | COMPLETED
REGION X | MISAMIS OCCIDENTAL | CONCEPCION | 1 | 7.7 | DED and POW Preparation | DED and POW Preparation
REGION X | MISAMIS OCCIDENTAL | DON VICTORIANO CHIONGBIAN (DON MARIANO MARCOS) | 1 | 4.9 | Procurement process | On-going Construction
REGION X | MISAMIS OCCIDENTAL | LOPEZ JAENA | 1 | 5.4 | Procurement process | On-going Construction
REGION X | MISAMIS OCCIDENTAL | PANAON | 2 | 8.7 | On-going Construction | On-going Construction
REGION X | MISAMIS OCCIDENTAL | PLARIDEL | 2 | 12.5 | 1-On-going Construction | COMPLETED
1-Procurement Process
REGION X | MISAMIS OCCIDENTAL | SAPANG DALAGA | 1 | 11.9 | On-going Construction | On-going Construction
REGION X | MISAMIS OCCIDENTAL | SINACABAN | 1 | 8 | On-going Construction | On-going Construction
REGION X | MISAMIS OCCIDENTAL | TUDELA | 1 | 6.9 | On-going Construction | On-going Construction
REGION X | MISAMIS ORIENTAL | ALUBIJID | 1 | 7.4 | Procurement process | Procurement process
REGION X | MISAMIS ORIENTAL | BALINGASAG | 1 | 9 | On-going Construction | On-going Construction
REGION X | MISAMIS ORIENTAL | CLAVERIA | 1 | 8.1 | Procurement process | Procurement process
REGION X | MISAMIS ORIENTAL | GITAGUM | 1 | 7 | On-going Construction | COMPLETED
REGION X | MISAMIS ORIENTAL | KINOGUITAN | 1 | 4 | Procurement process | Procurement process
REGION X | MISAMIS ORIENTAL | LAGONGLONG | 2 | 7.1 | On-going Construction | On-going Construction
REGION X | MISAMIS ORIENTAL | LIBERTAD | 1 | 8.1 | Procurement process | On-going Construction
REGION X | MISAMIS ORIENTAL | MAGSAYSAY (LINUGOS) | 1 | 7.7 | On-going Construction | On-going Construction
REGION X | MISAMIS ORIENTAL | MEDINA | 2 | 7.5 | On-going Construction | On-going Construction
REGION X | MISAMIS ORIENTAL | NAAWAN | 1 | 13.7 | On-going Construction | On-going Construction
REGION X | MISAMIS ORIENTAL | OPOL | 1 | 9.3 | Procurement process | On-going Construction
REGION X | MISAMIS ORIENTAL | SALAY | 1 | 7.4 | On-going Construction | On-going Construction
REGION X | MISAMIS ORIENTAL | SUGBONGCOGON | 1 | 7.8 | Procurement process | On-going Construction
REGION X | MISAMIS ORIENTAL | TAGOLOAN | 1 | 4 | DED and POW Preparation | DED and POW Preparation
REGION X | MISAMIS ORIENTAL | TALISAYAN | 2 | 8.6 | Procurement process | Procurement process
REGION X | MISAMIS ORIENTAL | VILLANUEVA | 1 | 8.5 | Procurement process | On-going Construction
|  |  | 85 | 494.06
REGION | PROVINCE | CITY / MUNICIPALITY | 2018 ASSISTANCE TO MUNICIPALITIES (AM-OTHERS)
|  |  | NO. OF PROJECT | ALLOCATION | STATUS AS OF DECEMBER 2018 | STATUS AS FEBRUARY 2019
REGION X | BUKIDNON | MANOLO FORTICH | 1 | 1.5 | DED and POW finalization | DED and POW finalization
REGION X | BUKIDNON | MARAMAG | 1 | 10 | Procurement process | Procurement process
REGION X | CAMIGUIN | MAMBAJAO (Capital) | 1 | 1.4 | Procurement process | Procurement process
REGION X | LANAO DEL NORTE | KAUSWAGAN | 1 | 2 | On-going Construction | On-going Construction
REGION X | LANAO DEL NORTE | LINAMON | 2 | 1.5 | 1-Procurement process | 1-Procurement process
[5 empty] | 1-On-going Construction | 1-On-going Construction
REGION X | LANAO DEL NORTE | NUNUNGAN | 1 | 3 | Procurement process | Procurement process
REGION X | LANAO DEL NORTE | SULTAN NAGA DIMAPORO | 1 | 0.6 | Prep. of Doc.Requirements | Preparation of Documentary Requirements
REGION X | MISAMIS ORIENTAL | BALINGOAN | 2 | 7.6 | 1-Procurement process | 1-Procurement process
[5 empty] | 1-Prep. of Doc. Requirements | 1-Prep. of Doc.Requirements
REGION X | MISAMIS ORIENTAL | INITAO | 1 | 7.5129 | DED and POW finalization | DED and POW finalization
REGION X | MISAMIS ORIENTAL | LAGUINDINGAN | 1 | 7.2169 | On-going Construction | On-going Construction
|  |  | 12 | 42.3298