## By Province
WEEKLY ACCOMPLISHMENT REPORT under PDMU
LOCALLY-FUNDED PROJECTS
as of June 26, 2020
PROVINCE | Year | Total No. of Projects | PAMANA |  |  |  |  | SALINTUBIG |  |  |  |  | BUB | [19 empty] | LGSF | [29 empty] | ADM | [14 empty] | AM | [14 empty] | CMGP |  |  |  |  | Remarks |  |  | BUKIDNON | CAMIGUIN | LANAO DEL NORTE | MISAMIS OCCIDENTAL | MISAMIS ORIENTAL | SUB-TOTAL
[13 empty] | Water |  |  |  |  | Local Access Road |  |  |  |  | Others |  |  |  |  | Evacuation Center |  |  |  |  | Water |  |  |  |  | Local Access Road |  |  |  |  | Others |  |  |  |  | Flood Control |  |  |  |  | Bridges |  |  |  |  | DRR Equipment |  |  |  |  | Water |  |  |  |  | Local Access Road |  |  |  |  | Evacuation Center |  |  |  |  | Water |  |  |  |  | Local Access Road |  |  |  |  | DRR & OTHER INFRA.
|  |  | Completed | On-going | Procurement | Finalization | Preparation/ Review | Completed | On-going | Procurement | Finalization | Preparation/ Review | Completed | On-going | Procurement | Finalization | Preparation/ Review | Completed | On-going | Procurement | Finalization | Preparation/ Review | Completed | On-going | Procurement | Finalization | Preparation/ Review | Completed | On-going | Procurement | Finalization | Preparation/ Review | Completed | On-going | Procurement | Finalization | Preparation/ Review | Completed | On-going | Procurement | Finalization | Preparation/ Review | Completed | On-going | Procurement | Finalization | Preparation/ Review | Completed | On-going | Procurement | Finalization | Preparation/ Review | Completed | On-going | Procurement | Finalization | Preparation/ Review | Completed | On-going | Procurement | Finalization | Preparation/ Review | Completed | On-going | Procurement | Finalization | Preparation/ Review | Completed | On-going | Procurement | Finalization | Preparation/ Review | Completed | On-going | Procurement | Finalization | Preparation/ Review | Completed | On-going | Procurement | Finalization | Preparation/ Review | Completed | On-going | Procurement | Finalization | Preparation/ Review | Completed | On-going | Procurement | Finalization | Preparation/ Review | Completed | On-going | Procurement | Finalization | Preparation/ Review
, | 2012 | 2 | [5 empty] | 2 | 0 | 0 | 0 | 0 | [86 empty] | COMPLETED |  | 331 | 102 | 323 | 277 | 280 | 1313
| 2013 | 47 | 11 | 0 | 0 | 0 | 0 | [5 empty] | 36 | 0 | 0 | 0 | 0
| 2014 | 52 | [5 empty] | 3 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | [71 empty] | ON-GOING |  | 26 | 5 | 23 | 17 | 16 | 87
| 2015 | 38 | 3 | 0 | 0 | 0 | 0 | [5 empty] | 18 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0
| 2016 | 94 | [5 empty] | 5 | 0 | 0 | 0 | 0 | 19 | 1 | 0 | 0 | 0 | [10 empty] | 1 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | [45 empty] | 14 | 0 | 0 | 0 | 0 |  | PROCUREMENT |  | 25 | 5 | 39 | 18 | 43 | 130
| 2017 | 65 | [5 empty] | 4 | 0 | 0 | 0 | 0 | [50 empty] | 15 | 1 | 0 | 0 | 0 | 34 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | [15 empty] | 6 | 0 | 0 | 0 | 0
| 2018 | 34 | [5 empty] | 1 | 2 | 0 | 0 | 0 | [65 empty] | 6 | 2 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 |  | FINALIZATION |  | 10 | 11 | 15 | 7 | 5 | 48
| 2019 | 31 | [5 empty] | 0 | 1 | 1 | 0 | 0 | [65 empty] | 0 | 4 | 1 | 0 | 0 | 5 | 10 | 1 | 0 | 0 | 1 | 1 | 1 | 2 | 0 | 0 | 3 | 0 | 0 | 0
| 2020 | 30 | [5 empty] | 0 | 0 | 2 | 1 | 0 | [65 empty] | 0 | 0 | 2 | 4 | 1 | 0 | 0 | 16 | 3 | 0 | 0 | 0 | 1 | 0 | 0 | [6 empty] | PREPARATION/ REVIEW |  | 1 | 1 | 2 | 5 | 3 | 12
Sub-Total: |  | 393 | 14 | 0 | 0 | 0 | 0 | 15 | 3 | 3 | 1 | 0 | 103 | 2 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | [15 empty] | 15 | 1 | 0 | 0 | 0 | 34 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 6 | 6 | 3 | 4 | 1 | 22 | 10 | 17 | 3 | 0 | 3 | 1 | 2 | 2 | 0 | 24 | 3 | 0 | 0 | 0
Camiguin | 2013 | 1 | [10 empty] | 1 | 0 | 0 | 0 | 0 | [81 empty] | SUB-TOTAL |  | 393 | 124 | 402 | 324 | 347
| 2014 | 9 | [10 empty] | 4 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0
| 2015 | 13 | [10 empty] | 8 | 0 | 0 | 0 | 0 | [5 empty] | 5 | 0 | 0 | 0 | 0 | [71 empty] | GRAND TOTAL | [6 empty] | 1590
| 2016 | 41 | [5 empty] | 7 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | [10 empty] | 2 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 5 | 0 | 0 | 0 | 0
| 2017 | 18 | [60 empty] | 9 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | [20 empty] | 4 | 0 | 0 | 0 | 0
| 2018 | 17 | [5 empty] | 1 | 0 | 0 | 0 | 0 | [65 empty] | 2 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0
| 2019 | 14 | [5 empty] | 1 | 0 | 0 | 0 | 0 | [65 empty] | 0 | 0 | 2 | 1 | 0 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 4 | 0 | 0 | 0
| 2020 | 11 | [5 empty] | 0 | 0 | 0 | 2 | 0 | [65 empty] | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 3 | 0
Sub-Total: |  | 124 | [5 empty] | 9 | 0 | 0 | 2 | 0 | 14 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | [10 empty] | 9 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | [5 empty] | 2 | 0 | 2 | 3 | 0 | 11 | 1 | 1 | 3 | 1 | 1 | 0 | 2 | 3 | 0 | 13 | 4 | 0 | 0 | 0
Lanao Del Norte | 2012 | 16 | 15 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
| 2013 | 19 | 3 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0
| 2014 | 44 | 3 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0
| 2015 | 59 | 1 | 0 | 0 | 0 | 0 | 31 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
| 2016 | 67 | [5 empty] | 6 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | [10 empty] | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | [45 empty] | 3 | 0 | 0 | 0 | 0
| 2017 | 64 | [5 empty] | 5 | 0 | 0 | 0 | 0 | [50 empty] | 15 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | [15 empty] | 2 | 0 | 0 | 0 | 0
| 2018 | 50 | [5 empty] | 10 | 1 | 0 | 0 | 0 | [65 empty] | 6 | 0 | 0 | 0 | 0 | 22 | 2 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0
| 2019 | 37 | [5 empty] | 0 | 1 | 1 | 2 | 0 | [65 empty] | 2 | 1 | 2 | 0 | 0 | 5 | 12 | 3 | 0 | 0 | 0 | 5 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0
| 2020 | 46 | [5 empty] | 0 | 0 | 7 | 0 | 1 | [65 empty] | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 15 | 6 | 0 | 0 | 0 | 9 | 5 | 1
Sub-Total: |  | 402 | 22 | 0 | 0 | 0 | 0 | 66 | 2 | 8 | 2 | 1 | 49 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | [15 empty] | 15 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 8 | 1 | 2 | 2 | 0 | 27 | 14 | 18 | 6 | 0 | 5 | 5 | 11 | 5 | 1 | 9 | 1 | 0 | 0 | 0
Misamis Occidental | 2012 | 3 | [5 empty] | 3 | 0 | 0 | 0 | 0
| 2013 | 12 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0
| 2014 | 42 | [5 empty] | 2 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0
| 2015 | 62 | [5 empty] | 28 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0
| 2016 | 65 | [5 empty] | 11 | 0 | 0 | 0 | 0 | 7 | 2 | 0 | 0 | 0 | [10 empty] | 9 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 28 | 1 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | [45 empty] | 1 | 0 | 0 | 0 | 0
| 2017 | 72 | [5 empty] | 2 | 0 | 0 | 0 | 0 | [50 empty] | 24 | 0 | 0 | 0 | 0 | 39 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | [15 empty] | 4 | 1 | 0 | 0 | 0
| 2018 | 23 | [5 empty] | 6 | 0 | 0 | 0 | 0 | [65 empty] | 1 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | [5 empty] | 1 | 1 | 0 | 0 | 0
| 2019 | 24 | [5 empty] | 0 | 4 | 3 | 0 | 0 | [65 empty] | 0 | 1 | 0 | 0 | 0 | 3 | 5 | 4 | 0 | 0 | [5 empty] | 0 | 2 | 2 | 0 | 0
| 2020 | 21 | [5 empty] | 0 | 0 | 1 | 0 | 1 | [65 empty] | 0 | 0 | 3 | 0 | 1 | 0 | 0 | 5 | 5 | 2 | 0 | 0 | 0 | 2 | 1
Sub-Total: |  | 324 | [5 empty] | 53 | 4 | 4 | 0 | 1 | 60 | 2 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 28 | 1 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | 24 | 0 | 0 | 0 | 0 | 39 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 0 | 1 | 17 | 5 | 9 | 5 | 2 | 0 | 0 | 0 | 2 | 1 | 6 | 4 | 2 | 0 | 0
Misamis Oriental | 2012 | 2 | [5 empty] | 2 | 0 | 0 | 0 | 0
| 2013 | 8 | [5 empty] | 8 | 0 | 0 | 0 | 0
| 2014 | 35 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
| 2015 | 45 | [10 empty] | 20 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 23 | 0 | 0 | 0 | 0
| 2016 | 95 | 1 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | [10 empty] | 5 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 51 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0
| 2017 | 65 | [5 empty] | 2 | 0 | 0 | 0 | 0 | [50 empty] | 20 | 1 | 0 | 0 | 0 | 37 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | [15 empty] | 3 | 0 | 0 | 0 | 0
| 2018 | 31 | [75 empty] | 4 | 1 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0
| 2019 | 34 | [5 empty] | 0 | 0 | 2 | 0 | 0 | [65 empty] | 0 | 1 | 4 | 0 | 0 | 4 | 7 | 11 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0
| 2020 | 32 | [5 empty] | 0 | 0 | 2 | 1 | 0 | [65 empty] | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 17 | 0 | 2 | 0 | 0 | 2 | 2 | 1
Sub-Total: |  | 347 | 1 | 0 | 0 | 0 | 0 | 24 | 0 | 4 | 1 | 0 | 56 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 51 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 1 | 0 | 0 | 0 | 37 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 4 | 2 | 8 | 1 | 0 | 22 | 7 | 28 | 1 | 2 | 3 | 1 | 3 | 2 | 1 | 6 | 4 | 0 | 0 | 0
GRAND TOTAL: |  | 1590 | 37 | 0 | 0 | 0 | 0 | 167 | 9 | 19 | 6 | 2 | 282 | 4 | 0 | 0 | 0 | 54 | 0 | 0 | 0 | 0 | 85 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 149 | 1 | 0 | 0 | 0 | 37 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83 | 2 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 15 | 1 | 0 | 0 | 0 | 21 | 10 | 18 | 10 | 2 | 99 | 37 | 73 | 18 | 5 | 12 | 7 | 18 | 14 | 3 | 58 | 16 | 2 | 0 | 0 |  |  | .
| Prepared by: | [26 empty] | Verified by: | [34 empty] | Submitted to:
| RICHELLE P. BADE | [27 empty] | ENGR. MARISIA C. NAYBE, CESE | [35 empty] | ARNEL M. AGABE, CESO III
| PDMU STAFF | [27 empty] | PDMU CHIEF | [35 empty] | REGIONAL DIRECTOR
Note on CK7: ====== ID#AAAAJK6JbFw PDMU-Brylle (2020-02-14 01:33:47) BUILDING DRAINAGE SYSTEM GROUND IMPROVEMENT

## By Project
WEEKLY ACCOMPLISHMENT REPORT under PDMU
LOCALLY-FUNDED PROJECTS
as of June 26, 2020
Year | Total No. of Projects | PAMANA |  |  |  |  | SALINTUBIG |  |  |  |  | BUB |  |  |  |  | LGSF |  |  |  |  | ADM |  |  |  |  | AM |  |  |  |  | CMGP |  |  |  |  | Remarks
|  | Completed | On-going | Procurement | Finalization | Preparation/ Review | Completed | On-going | Procurement | Finalization | Preparation/ Review | Completed | On-going | Procurement | Finalization | Preparation/ Review | Completed | On-going | Procurement | Finalization | Preparation/ Review | Completed | On-going | Procurement | Finalization | Preparation/ Review | Completed | On-going | Procurement | Finalization | Preparation/ Review | Completed | On-going | Procurement | Finalization | Preparation/ Review
2012 | 23 | 15 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0
2013 | 87 | 14 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 57 | 0 | 0 | 0 | 0
2014 | 182 | 3 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 167 | 0 | 0 | 0 | 0
2015 | 217 | 4 | 0 | 0 | 0 | 0 | 59 | 0 | 0 | 0 | 0 | 153 | 1 | 0 | 0 | 0
2016 | 362 | 1 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 63 | 3 | 0 | 0 | 0 | 231 | 1 | 0 | 0 | 0 | [10 empty] | 23 | 0 | 0 | 0 | 0
2017 | 284 | [5 empty] | 13 | 0 | 0 | 0 | 0 | [10 empty] | 248 | 3 | 0 | 0 | 0 | [5 empty] | 20 | 0 | 0 | 0 | 0
2018 | 155 | [5 empty] | 18 | 3 | 0 | 0 | 0 | [15 empty] | 110 | 6 | 0 | 0 | 0 | 16 | 2 | 0 | 0 | 0
2019 | 140 | [5 empty] | 1 | 6 | 7 | 2 | 0 | [15 empty] | 22 | 48 | 35 | 4 | 0 | 0 | 13 | 2 | 0 | 0
2020 | 140 | [5 empty] | 0 | 0 | 12 | 4 | 2 | [15 empty] | 0 | 0 | 74 | 38 | 10
SUB-TOTAL: |  | 37 | 0 | 0 | 0 | 0 | 167 | 9 | 19 | 6 | 2 | 440 | 4 | 0 | 0 | 0 | 231 | 1 | 0 | 0 | 0 | 248 | 3 | 0 | 0 | 0 | 132 | 54 | 109 | 42 | 10 | 59 | 15 | 2 | 0 | 0
GRAND TOTAL: | 1590
Prepared by: | [12 empty] | Verified by: | [12 empty] | Submitted to:
| RICHELLE P. BADE | [13 empty] | ENGR. MARISIA C. NAYBE, CESE | [12 empty] | ARNEL M. AGABE, CESO III
| PDMU STAFF | [13 empty] | PDMU CHIEF | [12 empty] | REGIONAL DIRECTOR

## By Year
WEEKLY ACCOMPLISHMENT REPORT under PDMU
LOCALLY-FUNDED PROJECTS
as of June 26, 2020
Year | Total No. of Projects | Completed | On-going | Procurement | Finalization |  | Preparation/ Review | Remarks
2012 | 23 | 23 | 0 | 0 | 0 |  | 0
2013 | 87 | 87 | 0 | 0 | 0 |  | 0
2014 | 182 | 182 | 0 | 0 | 0 |  | 0
2015 | 217 | 216 | 1 | 0 | 0 |  | 0
2016 | 362 | 358 | 4 | 0 | 0 |  | 0
2017 | 284 | 281 | 3 | 0 | 0 |  | 0
2018 | 155 | 144 | 11 | 0 | 0 |  | 0
2019 | 140 | 23 | 67 | 44 | 6 |  | 0
2020 | 140 | 0 | 0 | 86 | 42 |  | 12 | Preparation/Review(12) Please see attached file.
SUB-TOTAL: |  | 1314 | 86 | 130 | 48 |  | 12
GRAND TOTAL: | 1590
|  |  |  | 2015 (On-going) |  |  |  | 2018 (On-going)
|  |  |  | BUB-WATER | 1 | DON CARLOS | BUKIDNON | AM-OTHERS
[5 empty] | 1 |  |  |  | 1 | MUNAI | LANAO DEL NORTE
Prepared by: | [8 empty] | 1 | POONA PIAGAPO | LANAO DEL NORTE
|  |  |  | 2016 (On-going) |  |  |  |  | 1 | BALINGOAN | MISAMIS ORIENTAL
|  |  |  | BUB-WATER | 1 | KITAOTAO | BUKIDNON |  | 3
RICHELLE P. BADE |  |  |  |  | 1 | ALORAN | MISAMIS OCCIDENTAL | AM-WATER
[5 empty] | 1 | PANAON | MISAMIS OCCIDENTAL |  | 1 | KALILANGAN | BUKIDNON
PDMU STAFF |  |  |  | LGSF-LAR | 1 | CONCEPCION | MISAMIS OCCIDENTAL |  | 1 | LANTAPAN | BUKIDNON
|  |  |  | TOTAL | 4 |  |  |  | 1 | LUGAIT | MISAMIS ORIENTAL
3
|  |  |  | 2017 (On-going) |  |  |  | SALINTUBIG
|  |  |  | ADM-EVACUATION | 1 | TALISAYAN | MISAMIS ORIENTAL |  | 1 | DANGCAGAN | BUKIDNON
Verified by: |  |  |  | ADM-WATER | 1 | TALAKAG | BUKIDNON |  | 1 | TALAKAG | BUKIDNON
[5 empty] | 1 | TAGOLOAN | MISAMIS ORIENTAL |  | 1 | LALA | LANAO DEL NORTE
ENGR. MARISIA C. NAYBE, CESE |  |  |  | TOTAL | 3 |  |  |  | 3
CMGP
PDMU CHIEF |  |  |  | 2019(FINALIZATION) |  |  |  |  | 1 | MISAMIS ORIENTAL |  | 0
|  |  |  | SALINTUBIG |  |  |  |  | 1 | MISAMIS OCCIDENTAL
[5 empty] | 2 | BACOLOD, Lanao del Norte |  |  | 2
Submitted to: |  |  |  | AM-OTHER |  |  |  | TOTAL
[5 empty] | 1 | BALINGOAN, MISAMIS ORIENTAL |  |  | 11
[5 empty] | 2 | BAUNGON, BUKIDNON
ARNEL M. AGABE, CESO III |  |  |  | AM-WATER
[5 empty] | 1 | MAMBAJAO, CAMIGUIN
REGIONAL DIRECTOR |  |  |  | TOTAL | 6
[5 empty] | as of June 19, 2020 |  | as of June 26, 2020 | Remarks
[5 empty] | FY 2015 Projects |  | FY 2015 Projects
[5 empty] | * Ongoing -1 |  | * Ongoing -1
[5 empty] | FY 2016 Projects |  | FY 2016 Projects
[5 empty] | * Ongoing -5 |  | * Ongoing -4 | - 1 project added to completed
[5 empty] | FY 2017 Projects |  | FY 2017 Projects
[5 empty] | * Ongoing -6 |  | * Ongoing -3 | - 3 projects added to completed
[5 empty] | FY 2018 Projects |  | FY 2018 Projects
[5 empty] | * Ongoing -17 |  | * Ongoing -11 | - 6 projects added to completed
[5 empty] | FY 2019 Projects |  | FY 2019 Projects
[5 empty] | * Ongoing -70 |  | * Ongoing -67 | -3 projects added to completed
[5 empty] | *Procurement - 45 |  | *Procurement - 45
[5 empty] | * Finalization - 6 |  | * Finalization - 6
[5 empty] | * Preparation/Review - 0 |  | * Preparation/Review - 0
[5 empty] | FY 2020 Projects |  | FY 2020 Projects
[5 empty] | * Ongoing -0 |  | * Ongoing -0
[5 empty] | *Procurement - 79 |  | *Procurement - 86 | - 4 projects added for Procurement
[5 empty] | * Finalization - 48 |  | * Finalization - 42 | - 6 projects added to procurement
[5 empty] | * Preparation/Review - 13 |  | * Preparation/Review - 12 | -1 project added to procurement

## LFPs-issues&concerns
REGION X
LOCALLY FUNDED PROJECTS
PROJECT STATUS (ON-GOING PROJECTS 2015-2018)
as of June 26, 2020
PMO | FY | PROVINCES | CITY / MUNICIPALITY | BARANGAY | NAME OF PROJECT | PROJECT TYPE | ALLOCATION | STATUS | REMARKS | Date Updated | UPDATE FROM
BUB-WATER | 2015 | BUKIDNON | DON CARLOS | Kasingot, Pualas, Cabadiangan, Kalubihon, Old & New Nonongan, Calao |  |  | 3.78 | 90.25% Physical Accomplishment | FOR CANCELLATION PER ENGR.ALAMBAN | 2020-06-05
DELAYED DUE TO ROAD WIDENING FOR REVISION ONCE FINALIZED. TAKEN OVER BY LGU WITH REQUEST FOR RECONSIDERATION AND AFFIDAVIT OF UNDERTAKING UNTIL MARCH 2020 (UPDATE AS OF 10/31/2019)
BUB-WATER | 2016 | BUKIDNON | KITAOTAO | Poblacion |  |  | 8 | 90.15% Physical Accomplishment | IDENTIFIED EXISTING SOURCE FOR APPROVAL BY SB | 2020-01-30 | MONTHLY MEETING
BUB-WATER | 2016 | MISAMIS OCCIDENTAL | ALORAN | Tuburan, Tawi tawai, maular,conat |  |  | 9 | 90.04% Physical Accomplishment | LGU COUNTERPART ISSUE | 2020-01-23
Issue on LGU counterpart
BUB-WATER | 2016 | MISAMIS OCCIDENTAL | PANAON | Municipal-wide |  |  | 6.5 | 80% Physical Accomplishment | AS OF 12/18/2019 SWA | 2020-01-02
IMPLEMENTED BY SAME CONTRACTOR
LGSF-OTHERS | 2016 | CAMIGUIN | GUINSILIBAN | North & South Poblacion | 130 linear meter structural concreteRiver Control (Brgys. North & South Poblacion) | Flood Control | 2000000 | COMPLETED | 0 | 2020-06-26
RROW ISSUE
LGSF-OTHERS | 2016 | MISAMIS OCCIDENTAL | CONCEPCION |  | Construction of Local Road (Brgy. Virayan) | Roads/ Bridges - LGSF | 15000000 | 40.17% PHYSICAL ACCOMPLISHMENT | DIFFICULTY ON DELIVERY OF CONSTRUCTION MATERIALS DUE TO TERRAIN CONDITION | 2020-06-26 | K.E
ADM-OTHERS | 2017 | MISAMIS ORIENTAL | TALISAYAN | POBLACION, SAN JOSE, STA. INES | Evacuation Facility |  | 3274000 | On-going cancellation | Poblacion - 89.48% SWA AS OF MAY 2020 | 2020-02-27
[9 empty] | San Jose - 91.79% (SWA) AS OF MAY 2020 | 2020-02-27
[9 empty] | Sta. Ines - 75.65% (SWA) AS OF MAY 2020 | 2020-02-27
ADM-WATER | 2017 | BUKIDNON | TALAKAG | BRGYS 1,2,3,4,5, CACAON, DAGUMBAAN, STO NINO, SAN ISIDRO, SAN ANTONIO, LINGION | Provision of Potable Water Supply |  | 13025000 | 93.32% Physical Accomplishment | Ongoing cancellation | 2020-01-30
[9 empty] | PHASE II: LACKING WORKS ON 2 ROAD-CROSSING SECTIONS OF PIPES; DELAYED DUE TO UNABLE TO SECURE PERMITS FROM DPWH; ON GOING EVALUATION AND TERMINATION OF CONTRACT |  |  | TERMINATED
ADM-WATER | 2017 | CAMIGUIN | GUINSILIBAN | BRGY. BUTAY & NORTH POBLACION | Provision of Potable Water Supply |  | 14001000 | Completed | 0 | 2020-06-26
ADM-WATER | 2017 | MISAMIS ORIENTAL | TAGOLOAN | BRGY. CASINGLOT | Provision of Potable Water Supply |  | 8190000 | 90% Physical Accomplishment | on going implementation | 2019-12-06 | 0
AFFECTED BY ROAD WIDENING
ADM-WATER | 2017 | MISAMIS ORIENTAL | VILLANUEVA | SOURCE- NAPAPONG SPRING, BENEFICIARIES- BRGY. KATIPUNAN, DAYAWAN, TAMBOBONG, BALACANAS & BRGY. SAN MARTIN | Provision of Potable Water Supply |  | 13898000 | COMPLETED | PER ENGR. PUIG | 2020-06-23
AM-OTHERS | 2018 | CAMIGUIN | GUINSILIBAN | NATIONAL HIGHWAY, SOUTH POBLACION TO KIWAKAT | LOCAL ACCESS ROAD |  |  | COMPLETED | 0 | 2020-06-26 | engr.alpas
AM-OTHERS | 2018 | LANAO DEL NORTE | MUNAI | PANGGAO-TAMPARAN | LOCAL ACCESS ROAD |  |  | 23.91% Physical Accomplishment | AS OF 04/15/2020 SWA ongoing implementation | 2020-05-05 | 0
AM-OTHERS | 2018 | LANAO DEL NORTE | POONA PIAGAPO | BRGY. NUNANG TO BRGY. POBLACION | LOCAL ACCESS ROAD |  |  | 37.76% Physical Accomplishment | AS OF 1/15/2020 SWA ongoing cancellation | 2020-06-26 | 0
AM-OTHERS | 2018 | MISAMIS ORIENTAL | KINOGUITAN | BRGY. CALUBO TO BRGY. KITOTOK ROAD | LOCAL ACCESS ROAD |  |  | COMPLETED | PER ENGR. PUIG | 2020-06-23 | npj
AM-OTHERS | 2018 | MISAMIS ORIENTAL | VILLANUEVA | SITIO BANBAN TO SITIO MADRID, BRGY. LOOC | LOCAL ACCESS ROAD |  |  | COMPLETED | PER ENGR. PUIG BUT HAS DEFFECTS | 2020-06-23 | npj
AM-OTHERS | 2018 | MISAMIS ORIENTAL | BALINGOAN | MUNICIPAL WIDE | PROVISION OF SANITARY TOILET AND HYGIENE FACILITIES |  |  | 90.00% Physical Accompishment | ongoing implementation | 2020-06-23 | engr. puig
AM-OTHERS | 2018 | MISAMIS ORIENTAL | INITAO | APAS, INITAO | LOCAL BRIDGES |  |  | COMPLETED | UPDATE PER ENGR.PUIG | 2020-06-23 | 0
AM-WATER | 2018 | BUKIDNON | KALILANGAN | BARANGAY LAMPANUSAN | PROVISION OF POTABLE WATER SUPPLY |  |  | 80.33% Physical Accomplishment | AS OF 05/20/2020 SWA ongoing cancellation | 2020-06-03 | 0
AM-WATER | 2018 | BUKIDNON | PROVISION OF POTABLE WATER SUPPLY | BARANGAY KAATUAN, LANTAPAN | PROVISION OF POTABLE WATER SUPPLY |  |  | 98.29% Physical Accomplishment | AS OF 5/20/2020 (under suspension due to COVID-19) | 2020-06-25 | 0 | TERMINATED
AM-WATER | 2018 | MISAMIS ORIENTAL | BINUANGAN | BARANGAY DAMPIAS, MOSANGOT, POBLACION AND MABINI | PROVISION OF POTABLE WATER SUPPLY |  |  | COMPLETED | 0 | 2020-06-23 | NPJ
AM-WATER | 2018 | MISAMIS ORIENTAL | KINOGUITAN | MUNICIPAL WIDE, BARANGAY KAGUMAHAN | PROVISION OF POTABLE WATER SUPPLY |  |  | COMPLETED | 0 | 2020-06-23 | NPJ
AM-WATER | 2018 | MISAMIS ORIENTAL | LUGAIT | POBLACION | PROVISION OF POTABLE WATER SUPPLY |  |  | 78.00% Physical Accomplishment | AS OF 2/15/2020 SWA ongoing implementation | 2020-03-03 | 0
SALINTUBIG | 2018 | BUKIDNON | TALAKAG |  |  |  |  | 81.40% Physical Accomplishment ongoing cancellation | #REF! | #REF! | #REF! | TERMINATED
SALINTUBIG | 2018 | LANAO DEL NORTE | LALA |  |  |  |  | 85% Physical Accomplishment | #REF! | #REF! | #REF!
Note on J7: ====== ID#AAAAJK6JbFg (2020-03-03 03:47:16) Jovan Karl Bustamante <jovankarlbustamante@gmail.com> Hi engr, ask lang ko if wala bay update pila na status ani? as of now? paapil nalang pud ko sa uban na program sa bukidnon.Thank you Engr. -Richelle Bade
Note on J10: ====== ID#AAAAJK6JbFs (2020-03-03 03:47:16) kleanoure emperio <kleanouree@gmail.com> Hi engr, ask lang ko if wala bay update pila na status ani? as of now? paapil nalang pud ko sa uban na program sa mis. oc. Thank you nuy. -Richelle Bade
Note on J17: ====== ID#AAAAJK6JbF4 (2020-03-03 03:47:16) Erwin James Docallos <erjamesdocallos@gmail.com> Hi ya, ask lang ko if wala bay update pila na status ani? as of now? paapil nalang pud ko sa uban na program sa mis. or. Thank you ya. -Richelle Bade
Note on J29: ====== ID#AAAAJK6JbFo (2020-03-03 03:47:16) Abulcair Lindao <adlindao_2011@yahoo.com> Hi engr, ask lang ko if wala bay update pila na status ani? as of now? paapil nalang pud ko sa uban na program sa lanao.Thnk you engr. -Richelle Bade

## 2013 BUB-WATER
REGION X
2013 BUB - WATER
as of June 26, 2020
|  |  |  | FINANCIAL |  |  |  |  | CANCELLED PROJECTS | UNDER PREP | APPROVED FS/POW or DED PREP. | PROCUREMENT | ON-GOING | COMPLETED | STATUS | REMARKS | DATE UPDATED
PROVINCES | LGUs | NO. OF LGUs | TOTAL NO. OF PROJECTS | ALLOCATION | CANCELLED ALLOCATION | TOTAL RELEASES | TOTAL LIQUIDATION | AMOUNT OBLIGATED
BUKIDNON | BAUNGON | 1 | 2 | 0.8 |  | 800000 | 800000 | 0.8 | [5 empty] | 2
| San Miguel | [13 empty] | Completed
| Mahayahay | [13 empty] | Completed
BUKIDNON | CABANGLASAN | 1 | 4 | 3.13 |  | 3130000 | 3130000 | 3.13
| Cabulohan | [12 empty] | 1 | Completed
| Imbatug | [12 empty] | 1 | Completed
| Jasaan | [12 empty] | 1 | Completed | SWA | 11/16/2017
| Iba | [12 empty] | 1 | Completed | SWA | 2017-07-28
BUKIDNON | CITY OF VALENCIA | 1 | 1 | 4.2395 |  | 4240000 | 4240000 | 4.2395 | [5 empty] | 1 | Completed
BUKIDNON | DON CARLOS | 1 | 1 | 9.1 |  | 9100000 | 9100000 | 9.1 | [5 empty] | 1 | Completed
BUKIDNON | IMPASUG-ONG | 1 | 1 | 2.8 |  | 2800000 | 2800000 | 2.8 | [5 empty] | 1 | Completed
BUKIDNON | KALILANGAN | 1 | 5 | 1.25 |  | 1250000 | 1250000 | 1.25 | [5 empty] | 5
| Pamotolon | [13 empty] | Completed
| Barorawon | [13 empty] | Completed
| Lampanusan | [13 empty] | Completed
| Canituan | [13 empty] | Completed
| Kibaning | [13 empty] | Completed
BUKIDNON | KIBAWE | 1 | 1 | 0.87 |  | 870000 | 870000 | 0.87 | [5 empty] | 1 | Completed
BUKIDNON | KITAOTAO | 1 | 4 | 2 |  | 2000000 | 1720738.02 | 2 | [5 empty] | 4
| Cabalantian | [13 empty] | Completed
| Sagundanon | [13 empty] | Completed
| White Kulaman | [13 empty] | Completed
| Balangigay | [13 empty] | Completed | SWA | 2017-11-15
BUKIDNON | LANTAPAN | 1 | 1 | 1.5 |  | 1500000 | 1347891.35 | 1.5 | [5 empty] | 1 | Completed
BUKIDNON | MALAYBALAY CITY | 1 | 1 | 2 |  | 2000000 | 2000000 | 2 | [5 empty] | 1 | Completed
BUKIDNON | MALITBOG | 1 | 1 | 1.7 |  | 1700000 | 1700000 | 1.7 | [5 empty] | 1 | Completed
BUKIDNON | MANOLO FORTICH | 1 | 1 | 5 |  | 5000000 | 5000000 | 5 | [5 empty] | 1 | Completed
BUKIDNON | MARAMAG | 1 | 4 | 6.2 |  | 6200000 | 6200000 | 6.2 | [5 empty] | 4
| San Miguel (Poblacion & Purok 6) | [13 empty] | Completed
| Sitio Anibong, Dologon | [13 empty] | Completed
| Bagong Silang | [13 empty] | Completed
| Sitio Magsaysay, Kuya | [13 empty] | Completed
BUKIDNON | PANGANTUCAN | 1 | 6 | 4.09 |  | 4090000 | 4090000 | 4.09
| Kimanait | [12 empty] | 1 | Completed
| Gandingan | [12 empty] | 1 | Completed
| Pigtauranan | [12 empty] | 1 | Completed
| Mendis | [12 empty] | 1 | Completed
| Barandias | [12 empty] | 1 | Completed
| Bangahan | [12 empty] | 1 | Completed
BUKIDNON | QUEZON (Magsaysay) | 1 | 1 | 4.094 |  | 4094000 | 4094000 | 4.094 | [5 empty] | 1 | Completed
BUKIDNON | SAN FERNANDO | 1 | 2 | 4.5 |  | 4500000 | 4500000 | 4.5 | [5 empty] | 2
| Matupe | [13 empty] | Completed
| Cayaga | [13 empty] | Completed
BUKIDNON |  | 16 | 36 | 53.2735 | 0 | 53274000 | 52842629.37 | 53.2735 | 0 | 0 | 0 | 0 | 0 | 36
CAMIGUIN | MAHINOG | 1 | 1 | 0.3 |  | 300000 | 300000 | 0.3 | [5 empty] | 1 | Completed
CAMIGUIN |  | 1 | 1 | 0.3 | 0 | 300000 | 300000 | 0.3 |  | 0 | 0 | 0 | 0 | 1
LANAO DEL NORTE | BALOI | 1 | 1 | 5 |  | 5000000 | 5000000 | 5 | [5 empty] | 1 | Completed
LANAO DEL NORTE | BAROY | 1 | 1 | 0.5 |  | 500000 | 500000 | 0.5 | [5 empty] | 1 | Completed
LANAO DEL NORTE | KAPATAGAN | 1 | 1 | 1.6 |  | 1600000 | 1600000 | 1.6 | [5 empty] | 1 | Completed
LANAO DEL NORTE | MAGSAYSAY | 1 | 1 | 0.25 |  | 250000 | 250000 | 0.25 | [5 empty] | 1 | Completed
LANAO DEL NORTE | MUNAI | 1 | 2 | 7.6 |  | 7600000 | 7600000 | 7.6 | [5 empty] | 2
| Sendiga | [13 empty] | Completed
| Ramain, Tupurog | [13 empty] | Completed
LANAO DEL NORTE | SALVADOR | 1 | 1 | 0.97 |  | 970000 | 970000 | 0.97 | [5 empty] | 1 | Completed
LANAO DEL NORTE | TANGCAL | 1 | 1 | 8 |  | 8000000 | 8000000 | 8 | [5 empty] | 1 | Completed
LANAO DEL NORTE | TUBOD (CAPITAL) | 1 | 1 | 0.12 |  | 120000 | 120000 | 0.12 | [5 empty] | 1 | Completed
LANAO DEL NORTE |  | 8 | 9 | 24.04 | 0 | 24040000 | 24040000 | 24.04 | 0 | 0 | 0 | 0 | 0 | 9
MISAMIS OCCIDENTAL | ALORAN | 1 | 1 | 1 |  | 1000000 | 1000000 | 1 | [5 empty] | 1 | Completed
MISAMIS OCCIDENTAL | BALIANGAO | 1 | 1 | 2.36 |  | 2332804.04 | 2332804.04 | 2.36 | [5 empty] | 1 | Completed | (DILG Implemented: 1st and 2nd Billing + Mobilization)
MISAMIS OCCIDENTAL | BONIFACIO | 1 | 5 | 1.4 |  | 1400000 | 1400000 | 1.4 | [5 empty] | 5
| Bag-ong Anonang | [13 empty] | Completed
| Pisa-an | [13 empty] | Completed
| Buenavista | [13 empty] | Completed
| Lilo-an | [13 empty] | Completed
| Poblacion, Digson | [13 empty] | Completed
MISAMIS OCCIDENTAL | DON VICTORIANO CHIONGBIAN | 1 | 1 | 2.1 |  |  |  | 2.1
| Lalud |  |  |  | 1.05 | - | - |  | 1 | [5 empty] | CANCELLED | THE PROJECT WAS DECLARED FAILURE OF DRILLING | 2018-09-27 | KE
| Bag-ong Clarin |  |  |  |  | 1050000 | 1074660.4 | [6 empty] | 1 | Completed
MISAMIS OCCIDENTAL | LOPEZ JAENA | 1 | 1 | 1 |  | 1000000 | 1000000 | 1 | [5 empty] | 1 | Completed
MISAMIS OCCIDENTAL | PLARIDEL | 1 | 1 | 5.88 |  | 5880000 | 5880000 | 5.88 | [5 empty] | 1 | Completed
MISAMIS OCCIDENTAL | TUDELA | 1 | 1 | 2 |  | 2000000 | 2000000 | 2 | [5 empty] | 1 | Completed
MISAMIS OCCIDENTAL |  | 7 | 11 | 15.74 | 1.05 | 14662804.04 | 14687464.44 | 15.74 | 1 | 0 | 0 | 0 | 0 | 11
X SUB-TOTAL |  | 32 | 57 | 93.3535 | 1.05 | 92276804.04 | 91870093.81 | 93.3535 | 1 | 0 | 0 | 0 | 0 | 57

## 2014 BUB-Others
REGION X - BUB
2014 BUB OTHERS
as of June 26, 2020
PROJECT CODE | PMO | FY | REGION | PROVINCE | CITY / MUNICIPALITY | BARANGAY | NAME OF PROJECT | PROJECT TYPE | ORIGINAL ALLOCATION | FINANCIAL | [6 empty] | CANCELLED | UNDER PREP. | APPROVED FS/POW or DED PREP. | PROCUREMENT PROCESS | ON-GOING | COMPLETED | STATUS | REMARKS | DATE UPDATED
ALLOCATION
[10 empty] | AMOUNT | RE-ALIGNED | CANCELLED | REVISED | TOTAL RELEASES | TOTAL LIQUIDATION | AMOUNT OBLIGATED
OT-14-10-13-12-000-01 | BUB-OT | 2014 | REGION_X | BUKIDNON | CITY OF MALAYBALAY |  | Establishment of Early Warning System | DRRM EQUIPMENT | 480000 |  | 480000 |  | 480000 | 480000 | 480000 | 480000 | [5 empty] | 1 | COMPLETED
SUB-TOTAL |  |  |  |  | 1 |  | 1 |  | 480000 | 0 | 480000 | 0 | 480000 | 480000 | 480000 | 480000 | 0 | 0 | 0 | 0 | 0 | 1
OT-14-10-35-04-000-01 | BUB-OT | 2014 | REGION_X | LANAO DEL NORTE | CITY OF ILIGAN |  | Disaster Risk Reduction and Early Warning System Installation | DRRM EQUIPMENT | 980000 |  | 980000 |  | 980000 | 630000 | - | 980000 | [5 empty] | 1 | COMPLETED |  | 2018-11-01 | MCN
| BUB-OT | 2014 | REGION_X | LANAO DEL NORTE | KAUSWAGAN |  | Disaster Risk Reduction Capacity building | CAPDEV | 498750 |  |  |  | 498750 | 498750 | 498750 | 498750 | [5 empty] | 1 | COMPLETED
OT-14-10-35-07-000-02 | BUB-OT | 2014 | REGION_X | LANAO DEL NORTE | KAUSWAGAN |  | Disaster Management & Mitigation | CAPDEV | 292713 | 292713 |  | 76630 | 216083 | 216083 | 216083 | 216083 | [5 empty] | 1 | COMPLETED
OT-14-10-35-10-000-01 | BUB-OT | 2014 | REGION_X | LANAO DEL NORTE | LINAMON |  | Procurement of Rescue Equipment and Life Saving Apparatus | RESCUE EQUIPMENT | 350000 |  | 350000 |  | 350000 | 350000 | 350000 | 350000 | [5 empty] | 1 | COMPLETED
OT-14-10-35-06-000-01 | BUB-OT | 2014 | REGION_X | LANAO DEL NORTE | SULTAN NAGA DIMAPORO |  | Purchase of Rescue and Life Saving Equipment | RESCUE EQUIPMENT | 425000 |  | 425000 |  | 425000 | 425000 | 425000 | 425000 | [5 empty] | 1 | COMPLETED
SUB-TOTAL |  |  |  |  | 4 |  | 5 |  | 2546463 | 292713 | 1755000 | 76630 | 2469833 | 2119833 | 1489833 | 2469833 | 0 | 0 | 0 | 0 | 0 | 5
OT-14-10-42-05-000-01 | BUB-OT | 2014 | REGION_X | MISAMIS OCCIDENTAL | CLARIN |  | Purchase of Equipment (Early warning Device, hand-held radios, rubber boats, ropes, harness) | DRRM EQUIPMENT | 2375000 |  | 2375000 |  | 2375000 | 2137500 | 2137500 | 2375000 | [5 empty] | 1 | COMPLETED |  | 2018-03-20 | KE
| BUB-OT | 2014 | REGION_X | MISAMIS OCCIDENTAL | CLARIN |  | Capability Enhancement Training for Emergency Response Teams | CAPDEV | 997500 |  |  |  | 997500 | 862800 | 862800 | 997500 | [5 empty] | 1 | COMPLETED |  | 2017-11-01 | MCN
| BUB-OT | 2014 | REGION_X | MISAMIS OCCIDENTAL | CITY OF OROQUIETA |  | Capability Building Program | CAPDEV | 1000000 |  |  |  | 1000000 | 1000000 | 1000000 | 1000000 | [5 empty] | 1 | COMPLETED
SUB-TOTAL |  |  |  |  | 2 |  | 3 |  | 4372500 | 0 | 2375000 | 0 | 4372500 | 4000300 | 4000300 | 4372500 | 0 | 0 | 0 | 0 | 0 | 3
OT-14-10-43-18-000-01 | BUB-OT | 2014 | REGION_X | MISAMIS ORIENTAL | MANTICAO |  | Procurement of Early Warning Device | DRRM EQUIPMENT | 390000 |  | 390000 |  | 390000 | 390000 | 174316 | 390000 | [5 empty] | 1 | COMPLETED
| BUB-OT | 2014 | REGION_X | MISAMIS ORIENTAL | BALINGOAN |  | Disaster Preparedness | CAPDEV | 1000000 | [5 empty] | - |  | 1 | [5 empty] | CANCELLED: | not obligated due to non-submission of documents
SUB-TOTAL |  |  |  |  | 2 |  | 2 |  | 1390000 | 0 | 390000 | 0 | 390000 | 390000 | 174316 | 390000 | 1 | 0 | 0 | 0 | 0 | 1
GRAND TOTAL (OTHERS): |  |  |  |  | 9 |  | 11 |  | 8788963 | 292713 | 5000000 | 76630 | 7712333 | 6990133 | 6144449 | 7712333 | 1 | 0 | 0 | 0 | 0 | 10
| BUB-OT | 2014 | REGION_X | BUKIDNON | Dangcagan |  | Conc. of Dagohoy-San Isidro rd. | LOCAL ROADS | 450000 |  |  |  |  | 1797588.89 | 1797588.89 | 450000 | [5 empty] | 1 | COMPLETED
| BUB-OT | 2014 | REGION_X | BUKIDNON | Dangcagan |  | Conc. Of Sitio San Miguel | LOCAL ROADS | 450000 | [6 empty] | 450000 | [5 empty] | 1 | COMPLETED
| BUB-OT | 2014 | REGION_X | BUKIDNON | Dangcagan |  | Conc. Of Bugwak rd | LOCAL ROADS | 900000 | [6 empty] | 900000 | [5 empty] | 1 | COMPLETED
| BUB-OT | 2014 | REGION_X | BUKIDNON | Kadingilan |  | Conc. Of Kibalagon rd-Junc. Matampay and Cabadiangan Rd | LOCAL ROADS | 997000 |  |  |  |  | 7796924.96 | 7796924.96 | 997000 | [5 empty] | 1 | COMPLETED
| BUB-OT | 2014 | REGION_X | BUKIDNON | Kadingilan |  | Conc. Of Purok 7, Bagongbayan Rd | LOCAL ROADS | 997000 | [6 empty] | 997000 | [5 empty] | 1 | COMPLETED
| BUB-OT | 2014 | REGION_X | BUKIDNON | Kadingilan |  | Conc. Of Junction Mabuhay E/S rd-Balaoro Rd | LOCAL ROADS | 1096700 | [6 empty] | 1096700 | [5 empty] | 1 | COMPLETED
| BUB-OT | 2014 | REGION_X | BUKIDNON | Kadingilan |  | Conc. Of Purok 7-Karingag Spillway-Purok Center Bagongbayan | LOCAL ROADS | 1520425 | [6 empty] | 1520425 | [5 empty] | 1 | COMPLETED
| BUB-OT | 2014 | REGION_X | BUKIDNON | Kadingilan |  | Conc. Of Junction proper Bagongbanyan Rd. | LOCAL ROADS | 1545350 | [6 empty] | 1545350 | [5 empty] | 1 | COMPLETED
| BUB-OT | 2014 | REGION_X | BUKIDNON | Kadingilan |  | Conc. Of Busay-Spillway Pinamangguan Rd. | LOCAL ROADS | 1645050 | [6 empty] | 1645050 | [5 empty] | 1 | COMPLETED
| BUB-OT | 2014 | REGION_X | BUKIDNON | Kitaotao |  | Repair of 2km. Road | LOCAL ROADS | 500000 |  |  |  |  | 500000 | 500000 | 500000 | [5 empty] | 1 | COMPLETED
| BUB-OT | 2014 | REGION_X | BUKIDNON | San Fernando |  | Candelaria FMR | LOCAL ROADS | 150030 |  |  |  |  | 2229260.02 | 2085188.22 | 150030 | [5 empty] | 1 | COMPLETED
| BUB-OT | 2014 | REGION_X | BUKIDNON | San Fernando |  | Mabuhay-Balaas FMR | LOCAL ROADS | 200070 | [6 empty] | 200070 | [5 empty] | 1 | COMPLETED
| BUB-OT | 2014 | REGION_X | BUKIDNON | San Fernando |  | Rehabilitation of Footbridge @ Candelaria (P-2)/Iglugsad | LOCAL ROADS | 463250 | [6 empty] | 463250 | [5 empty] | 1 | COMPLETED
| BUB-OT | 2014 | REGION_X | BUKIDNON | San Fernando |  | Rehabilitation of Footbridge @ Halapitan (P-2)/kawayan | LOCAL ROADS | 463250 | [6 empty] | 463250 | [5 empty] | 1 | COMPLETED
| BUB-OT | 2014 | REGION_X | BUKIDNON | San Fernando |  | Re-const. of Malayanan Footbridge | LOCAL ROADS | 463250 | [6 empty] | 463250 | [5 empty] | 1 | COMPLETED
| BUB-OT | 2014 | REGION_X | BUKIDNON | San Fernando |  | Re-const. of Footbridge @ Tugop | LOCAL ROADS | 232050 | [6 empty] | 232050 | [5 empty] | 1 | COMPLETED
| BUB-OT | 2014 | REGION_X | BUKIDNON | San Fernando |  | Re-const. of Footbridge @ Candelaria (P-1) | LOCAL ROADS | 232050 | [6 empty] | 232050 | [5 empty] | 1 | COMPLETED
| BUB-OT | 2014 | REGION_X | BUKIDNON | San Fernando |  | Re-const. of Footbridge @ Halapitan | LOCAL ROADS | 232050 | [6 empty] | 232050 | [5 empty] | 1 | COMPLETED
SUB-TOTAL |  |  |  |  | 4 |  | 18 |  | 12537525 | 0 | 0 | 0 | 0 | 12323773.87 | 12179702.07 | 12537525 | 0 | 0 | 0 | 0 | 0 | 18
| BUB-OT | 2014 | REGION_X | CAMIGUIN | Mahinog |  | Conc. Of Brgy. Tupsan Pequeño (FMR) | LOCAL ROADS | 270000 |  |  |  |  | 3279703.14 | 3279703.14 | 270000 | [5 empty] | 1 | COMPLETED
| BUB-OT | 2014 | REGION_X | CAMIGUIN | Mahinog |  | Conc. Of Brgy. San Isidro | LOCAL ROADS | 900000 | [6 empty] | 900000 | [5 empty] | 1 | COMPLETED
| BUB-OT | 2014 | REGION_X | CAMIGUIN | Mahinog |  | Conc. Of Inahan sa Kanunay Panabang to Sitio Taoctaoc FMR | LOCAL ROADS | 900000 | [6 empty] | 900000 | [5 empty] | 1 | COMPLETED
| BUB-OT | 2014 | REGION_X | CAMIGUIN | Mahinog |  | Conc. Of Rd in Quebe, San Miguel | LOCAL ROADS | 1350000 | [6 empty] | 1350000 | [5 empty] | 1 | COMPLETED
| BUB-OT | 2014 | REGION_X | CAMIGUIN | Mambajao |  | Concreting of Anito-Tambaan FMR | LOCAL ROADS | 1740000 |  |  |  |  | 1730139.11 | 1730139.11 | 1740000 | [5 empty] | 1 | COMPLETED
SUB-TOTAL |  |  |  |  | 2 |  | 5 |  | 5160000 | 0 | 0 | 0 | 0 | 5009842.25 | 5009842.25 | 5160000 | 0 | 0 | 0 | 0 | 0 | 5
| BUB-OT | 2014 | REGION_X | LANAO DEL NORTE | Baloi |  | Rehab. Of Angayen Road | LOCAL ROADS | 500000 |  |  |  |  | 4000000 | 4000000 | 500000 | [5 empty] | 1 | COMPLETED
| BUB-OT | 2014 | REGION_X | LANAO DEL NORTE | Baloi |  | Rehab. Of Mama-anun Road | LOCAL ROADS | 500000 | [6 empty] | 500000 | [5 empty] | 1 | COMPLETED
| BUB-OT | 2014 | REGION_X | LANAO DEL NORTE | Baloi |  | Rehab. of Lumbac Road | LOCAL ROADS | 500000 | [6 empty] | 500000 | [5 empty] | 1 | COMPLETED
| BUB-OT | 2014 | REGION_X | LANAO DEL NORTE | Baloi |  | Rehab. Of Maria Cristina Road | LOCAL ROADS | 500000 | [6 empty] | 500000 | [5 empty] | 1 | COMPLETED
| BUB-OT | 2014 | REGION_X | LANAO DEL NORTE | Baloi |  | Rehab. Of Sandar Bubong Paco Road | LOCAL ROADS | 500000 | [6 empty] | 500000 | [5 empty] | 1 | COMPLETED
| BUB-OT | 2014 | REGION_X | LANAO DEL NORTE | Baloi |  | Rehab. Of Bangko Road | LOCAL ROADS | 500000 | [6 empty] | 500000 | [5 empty] | 1 | COMPLETED
| BUB-OT | 2014 | REGION_X | LANAO DEL NORTE | Baloi |  | Rehab. Of Pacalundo Road | LOCAL ROADS | 500000 | [6 empty] | 500000 | [5 empty] | 1 | COMPLETED
| BUB-OT | 2014 | REGION_X | LANAO DEL NORTE | Baloi |  | Rehab of east Poblacion Road | LOCAL ROADS | 500000 | [6 empty] | 500000 | [5 empty] | 1 | COMPLETED
| BUB-OT | 2014 | REGION_X | LANAO DEL NORTE | Linamon |  | Improvement of Purakan-Bosque Farm to Market Road | LOCAL ROADS | 1338725 |  |  |  |  | 1333962.94 | 1333962.94 | 1338725 | [5 empty] | 1 | COMPLETED
| BUB-OT | 2014 | REGION_X | LANAO DEL NORTE | Pantar |  | Conc. Pavement Road | LOCAL ROADS | [8 empty] | 1 | [5 empty] | CANCELLED
| BUB-OT | 2014 | REGION_X | LANAO DEL NORTE | Pantar |  | Conc. Pavement Road | LOCAL ROADS | [8 empty] | 1 | [5 empty] | CANCELLED
| BUB-OT | 2014 | REGION_X | LANAO DEL NORTE | Pantar |  | Road Project with Conc. Pavement road | LOCAL ROADS | [8 empty] | 1 | [5 empty] | CANCELLED
| BUB-OT | 2014 | REGION_X | LANAO DEL NORTE | Pantar |  | 2 km. Road Project w/ conc. Pavement Road | LOCAL ROADS | [8 empty] | 1 | [5 empty] | CANCELLED
SUB-TOTAL |  |  |  |  | 3 |  | 13 |  | 5338725 | 0 | 0 | 0 | 0 | 5333962.94 | 5333962.94 | 5338725 | 4 | 0 | 0 | 0 | 0 | 9
| BUB-OT | 2014 | REGION_X | MISAMIS OCCIDENTAL | Aloran |  | Conc. Of Manamong (Sitio Silangit) Road | LOCAL ROADS | 945000 |  |  |  |  | 4095000 | 4095000 | 945000 | [5 empty] | 1 | COMPLETED
| BUB-OT | 2014 | REGION_X | MISAMIS OCCIDENTAL | Aloran |  | Conc. Of Tubod -Mitaazan Road | LOCAL ROADS | 1575000 | [6 empty] | 1575000 | [5 empty] | 1 | COMPLETED
| BUB-OT | 2014 | REGION_X | MISAMIS OCCIDENTAL | Aloran |  | Conc. Of Pelong Road | LOCAL ROADS | 1575000 | [6 empty] | 1575000 | [5 empty] | 1 | COMPLETED
| BUB-OT | 2014 | REGION_X | MISAMIS OCCIDENTAL | Jimenez |  | Conc. Of Jimenez Access Rd to Agora Public Mrkt. | LOCAL ROADS | 1000000 |  |  |  |  | 1000000 | 1000000 | 1000000 | [5 empty] | 1 | COMPLETED
| BUB-OT | 2014 | REGION_X | MISAMIS OCCIDENTAL | Plaridel |  | Concreting of Puntod-Catarman Road Concreting | LOCAL ROADS | 935000 |  |  |  |  | 935000 | 935000 | 935000 | [5 empty] | 1 | COMPLETED
| BUB-OT | 2014 | REGION_X | MISAMIS OCCIDENTAL | Tudela |  | Conc. Of Sebac Road | LOCAL ROADS | 460390 |  |  |  |  | 960390 | 960390 | 460390 | [5 empty] | 1 | COMPLETED
| BUB-OT | 2014 | REGION_X | MISAMIS OCCIDENTAL | Tudela |  | Conc. Of Col. Settlement road | LOCAL ROADS | 500000 | [6 empty] | 500000 | [5 empty] | 1 | COMPLETED
| BUB-OT | 2014 | REGION_X | MISAMIS OCCIDENTAL | Ozamis City |  | Concreting of Cavinte Barangay Road (FMR) | LOCAL ROADS | 1930000 |  |  |  |  | 1861085 | 1861085 | 1930000 | [5 empty] | 1 | COMPLETED
| BUB-OT | 2014 | REGION_X | MISAMIS OCCIDENTAL | Tangub City |  | Conc. Of FMR (Brgy. Pangabuan) | LOCAL ROADS | 500000 |  |  |  |  | 1000000 | 1000000 | 500000 | [5 empty] | 1 | COMPLETED
| BUB-OT | 2014 | REGION_X | MISAMIS OCCIDENTAL | Tangub City |  | Conc. Of FMR (Brgy. Balatacan) | LOCAL ROADS | 500000 | [6 empty] | 500000 | [5 empty] | 1 | COMPLETED
SUB-TOTAL |  |  |  |  | 6 |  | 10 |  | 9920390 | 0 | 0 | 0 | 0 | 9851475 | 9851475 | 9920390 | 0 | 0 | 0 | 0 | 0 | 10
| BUB-OT | 2014 | REGION_X | MISAMIS ORIENTAL | Medina |  | Concreting Pavement of Road (San Jose) | LOCAL ROADS | 655125 |  |  |  |  | 7280100 | 7280100 | 655125 | [5 empty] | 1 | COMPLETED
| BUB-OT | 2014 | REGION_X | MISAMIS ORIENTAL | Medina |  | Concreting Pavement of Road (San Roque) | LOCAL ROADS | 1000000 | [6 empty] | 1000000 | [5 empty] | 1 | COMPLETED
| BUB-OT | 2014 | REGION_X | MISAMIS ORIENTAL | Medina |  | Concreting Pavement of Road (Portulin) | LOCAL ROADS | 1000000 | [6 empty] | 1000000 | [5 empty] | 1 | COMPLETED
| BUB-OT | 2014 | REGION_X | MISAMIS ORIENTAL | Medina |  | Concreting Pavement of Road (Gasa) | LOCAL ROADS | 1000000 | [6 empty] | 1000000 | [5 empty] | 1 | COMPLETED
| BUB-OT | 2014 | REGION_X | MISAMIS ORIENTAL | Medina |  | Concreting Pavement of Road (San Vicente) | LOCAL ROADS | 1485000 | [6 empty] | 1485000 | [5 empty] | 1 | COMPLETED
| BUB-OT | 2014 | REGION_X | MISAMIS ORIENTAL | Medina |  | Concreting Pavement of Road (San Isidro) | LOCAL ROADS | 1980000 | [6 empty] | 1980000 | [5 empty] | 1 | COMPLETED
| BUB-OT | 2014 | REGION_X | MISAMIS ORIENTAL | Medina |  | Concreting Pavement of Road (Sitio Sidlakan, Bangbang) | LOCAL ROADS | 1980000 | [6 empty] | 1980000 | [5 empty] | 1 | COMPLETED
SUB-TOTAL |  |  |  |  | 1 |  | 7 |  | 9100125 | 0 | 0 | 0 | 0 | 7280100 | 7280100 | 9100125 | 0 | 0 | 0 | 0 | 0 | 7
GRAND TOTAL (LAR): |  |  |  |  | 16 |  | 53 |  | 42056765 | 0 | 0 | 0 | 0 | 39799154.06 | 39655082.26 | 42056765 | 4 | 0 | 0 | 0 | 0 | 49
GRAND TOTAL (OTHERS+LAR): | [8 empty] | 50845728 | 292713 | 5000000 | 76630 | 7712333 | 46789287.06 | 45799531.26 | 49769098 | 5 | 0 | 0 | 0 | 0 | 59

## 2014 BUB-WATER
REGION X
2014 BUB - WATER
as of June 26, 2020
|  |  |  | FINANCIAL |  |  |  |  | CANCELLED PROJECTS | UNDER PREP | APPROVED FS/POW or DED PREP. | PROCUREMENT | ON-GOING | COMPLETED | STATUS | REMARKS | Date Updated
PROVINCES | LGUs | NO. OF LGUs | TOTAL NO. OF PROJECTS | ALLOCATION | CANCELLED ALLOCATION | TOTAL RELEASES | TOTAL LIQUIDATION | AMOUNT OBLIGATED
BUKIDNON | BAUNGON | 1 | 1 | 3 |  | 2732719.9 | 2732719.9 | 3 | [5 empty] | 1 | Completed
BUKIDNON | CABANGLASAN | 1 | 6 | 2.9325 |  | 2932500 | 2932500 | 2.9325 | [5 empty] | 6
| Proper Dalacutan | [13 empty] | Completed
| Anlugan | [13 empty] | Completed
| Sitio Tingkaan, Poblacion | [13 empty] | Completed
| Purok 4 Dalacutan | [13 empty] | Completed
| Mandahican | [13 empty] | Completed
| Sitio Tagiptip, Poblacion | [13 empty] | Completed
BUKIDNON | DON CARLOS | 1 | 1 | 9.6109 |  | 9248293.25 | 9248293.25 | 9.6109 | [5 empty] | 1 | 98.20% Physical Accomplishment | as of 12/16/2019 SWA; with Variation Order; for Final Inspection | 2019-12-18
BUKIDNON | KALILANGAN | 1 | 1 | 0.8075 |  | 807500 | 807500 | 0.8075 | 1 | [5 empty] | (3 sub-projects for cancellation with LPRAT resolution submitted to RO, with letter to RO) | LGU already submitted LPRAT Resolution to the Region
| Sitio Pasayanon, Malinao | [12 empty] | 1 | Completed |  | 2018-04-16
BUKIDNON | KIBAWE | 1 | 1 | 1.4492 |  | 1449164.8 | 1449164.8 | 1.4492 | [5 empty] | 1 | Completed
BUKIDNON | KITAOTAO | 1 | 2 | 1.3 |  | 1040000 | 1040000 | 1.3 | [5 empty] | 2
| Kipilas | [13 empty] | Completed | SWA | 2017-11-15
| Balocbocan | [13 empty] | Completed | SWA | 2017-11-15
BUKIDNON | LANTAPAN | 1 | 1 | 2 |  | 2000000 | 2000000 | 2 | [5 empty] | 1 | Completed
BUKIDNON | LIBONA | 1 | 3 | 10.4 |  | 10400000 | 10298795.59 | 10.4
| San Isidro | [12 empty] | 1 | Completed
| Kiliog | [12 empty] | 1 | Completed
| Sigmatan | [12 empty] | 1 | Completed | SWA | 2017-11-15
BUKIDNON | MALITBOG | 1 | 1 | 0.94925 |  | 949250 | 949250 | 0.94925
| Sampiano | [12 empty] | 1 | Completed |  | 2018-03-20 | BT
BUKIDNON | MANOLO FORTICH | 1 | 2 | 12 |  | 12000000 | 12000000 | 12 | [5 empty] | 2
| Ticala | [13 empty] | Completed
| Minsuro | [13 empty] | Completed
BUKIDNON | MARAMAG |  |  |  |  | 1578553.85 | 1578553.85 | 1.7 | [5 empty] | 1
| Base Camp, Sitio Kalagutay | 1 | 1 | 1.7 | [10 empty] | Completed
BUKIDNON | PANGANTUCAN | 1 | 2 | 1.015 |  | 1015000 | 1015000 | 1.015
| Nabaliwa | [12 empty] | 1 | Completed | SWA | 2017-11-15
| Pigtauranan | [12 empty] | 1 | Completed
BUKIDNON | QUEZON | 1 | 2 | 10.0524 |  | 10052397.5 | 10052397.5 | 10.0524
| Dumalama, Merangeran, Minsalirac, San Jose, San Isidro, Poblacion | [12 empty] | 1 | Completed
| Magsaysay | [12 empty] | 1 | Completed | SWA | 2017-09-26
BUKIDNON | SAN FERNANDO | 1 | 3 | 1.1475 |  | 1120709.86 | 1120709.86 | 1.1475
| MHO | [12 empty] | 1 | Completed
| Sto. Domingo | [12 empty] | 1 | Completed
| Bonacao | [12 empty] | 1 | Completed
BUKIDNON | SUMILAO | 1 | 1 | 2.0235 |  | 2023000 | 2023000 | 2.0235 | [5 empty] | 1 | Completed | (LGU to submit request to utilize the remaining fund for the project)
BUKIDNON | TALAKAG | 1 | 2 | 1.2927 |  | 1292744 | 1292744 | 1.2927
| Poblacion | [12 empty] | 1 | Completed
| Tagbak | [12 empty] | 1 | Completed
BUKIDNON |  | 16 | 30 | 61.6805 | 0 | 60641833.16 | 60540628.75 | 61.6805 | 1 | 0 | 0 | 0 | 0 | 30
CAMIGUIN | CATARMAN | 1 | 1 | 0.5 |  | 500000 | 500000 | 0.5 | [5 empty] | 1 | Completed
CAMIGUIN | MAHINOG | 1 | 3 | 1.235 |  | 1235000 | 1235000 | 1.235 | [5 empty] | 3
| Owakan | [13 empty] | Completed
| San Isidro | [13 empty] | Completed
| San Miguel | [13 empty] | Completed
CAMIGUIN |  | 2 | 4 | 1.735 | 0 | 1735000 | 1735000 | 1.735 | 0 | 0 | 0 | 0 | 0 | 4
LANAO DEL NORTE | BALO-I | 1 | 1 | 0.8275 |  | 827500 | 827500 | 0.8275 | [5 empty] | 1 | Completed | Brgy. Sandor and Sigayan - Completed | 2018-05-21 | ND
LANAO DEL NORTE | BACOLOD | 1 | 1 | 2.9925 |  | 2775641.95 | 2775641.95 | 2.9925 | [5 empty] | 1 | Completed
LANAO DEL NORTE | BAROY | 1 | 4 | 3.8932 |  | 3893230 | 3893230 | 3.8932
| Salong | [12 empty] | 1 | Completed | SWA | 2019-01-10 | ND
| Maliwanag | [12 empty] | 1 | Completed
| Andil | [12 empty] | 1 | Completed
| Tinubdan | [12 empty] | 1 | Completed
LANAO DEL NORTE | KAPATAGAN | 1 | 1 | 2.21 |  | 2191549.65 | 2191549.65 | 2.21 | [5 empty] | 1 | Completed
LANAO DEL NORTE | KAUSWAGAN | 1 | 2 | 0.9975 |  | 997500 | 997500 | 0.9975 | [5 empty] | 2
| Libertad | [13 empty] | Completed
| Kawit Oriental | [13 empty] | Completed
LANAO DEL NORTE | MAGSAYSAY | 1 | 1 | 5.985 |  | 5985000 | 5985000 | 5.985 | [5 empty] | 1 | Completed | SWA | 2018-03-13
LANAO DEL NORTE | MATUNGAO | 1 | 1 | 5.9992 |  | 5924043.42 | 5924043.42 | 5.9992 | [5 empty] | 1 | Completed | SWA | 2018-06-19 | MCN
LANAO DEL NORTE | MUNAI | 1 | 1 | 0.38 |  | 380000 | 380000 | 0.38 | [5 empty] | 1 | Completed | SWA | 2017-09-05
LANAO DEL NORTE | NUNUNGAN | 1 | 2 | 3.73 |  | 3729999.75 | 3729999.75 | 3.73
| Inayawan | [12 empty] | 1 | Completed
| Dimayon | [12 empty] | 1 | Completed
LANAO DEL NORTE | PANTAR |  | 2 |  | 2.47 |  |  | 0 | 2 | [5 empty] | Cancelled: Not Obligated due to non-submission of documents
LANAO DEL NORTE | POONA PIAGAPO |  | 1 |  | 1.6975 |  |  |  | 1
LANAO DEL NORTE | SALVADOR | 1 | 2 | 9 |  | 9000000 | 9000000 | 9
| Mapantao | [12 empty] | 1 | Completed | SWA | 2018-07-24
| Panaliwad-on, Poblacion | [12 empty] | 1 | Completed | SWA | 2018-08-07
LANAO DEL NORTE | SAPAD | 1 | 1 | 7 |  | 7000000 | 7000000 | 7 | [5 empty] | 1 | Completed
LANAO DEL NORTE | TUBOD (CAPITAL) | 1 | 4 | 7.8518 |  | 7851780 | 7851780 | 7.8518 | [5 empty] | 4
| Malingao | [13 empty] | Completed
| Kakai Renabor | [13 empty] | Completed
| Palao & Dalama | [13 empty] | Completed
| Bualan | [13 empty] | Completed
LANAO DEL NORTE | ILIGAN CITY | 1 | 1 | 0.3 |  | 300000 | 300000 | 0.3 | 1 | [5 empty] | CANCELLED |  | 2020-01-24 | ND
LANAO DEL NORTE |  | 13 | 25 | 51.1668 | 4.1675 | 50856244.77 | 50856244.77 | 51.1668 | 4 | 0 | 0 | 0 | 0 | 21
MISAMIS OCCIDENTAL | ALORAN | 1 | 1 | 8 |  | 6696684.57 | 3515295.62 | 8 | [5 empty] | 1 | Completed | SWA | 5/72018
MISAMIS OCCIDENTAL | BALIANGAO | 1 | 1 | 6.4096 |  | 6306530.93 | 6189334.78 | 6.4096 | [5 empty] | 1 | Completed |  | 2019-07-12 | MCN
MISAMIS OCCIDENTAL | BONIFACIO | 1 | 9 | 4.4 |  | 3943198.87 | 3943198.87 | 4.4
| Lilo-an | [12 empty] | 1 | Completed
| Bag-ong Anonang | [12 empty] | 1 | Completed
| Calolot | [12 empty] | 1 | Completed
| Bolinsong | [12 empty] | 1 | Completed
| Tangab | [12 empty] | 1 | Completed
| Poblacion | [12 empty] | 1 | Completed
| Burakan | [12 empty] | 1 | Completed
| Tusik | [12 empty] | 1 | Completed
| Baybay | [12 empty] | 1 | Completed
MISAMIS OCCIDENTAL | CALAMBA | 1 | 1 | 1.5 |  | 1500000 | 1500000 | 1.5 | [5 empty] | 1 | Completed
MISAMIS OCCIDENTAL | CLARIN | 1 | 1 | 2.4937 |  | 2493750 | 2493750 | 2.4937 | [5 empty] | 1 | Completed
MISAMIS OCCIDENTAL | DON VICTORIANO | 1 |  |  | 2 | 1000000 | 1000000 | 2 | 1 | [5 empty] | CANCELLED |  | 2018-05-10 | MCN
MISAMIS OCCIDENTAL | JIMENEZ | 1 | 1 | 8 |  | 8000000 | 8000000 | 8 | [5 empty] | 1 | Completed
MISAMIS OCCIDENTAL | LOPEZ JAENA | 1 | 1 | 3.2 |  | 3200000 | 3200000 | 3.2 | [5 empty] | 1 | Completed
MISAMIS OCCIDENTAL | OROQUIETA CITY | 1 | 8 | 3.95 |  | 3950000 | 3105324.16 | 3.95
| San vicente Bajo | [12 empty] | 1 | Completed
| P1-Villaflor | [12 empty] | 1 | Completed
| Binuangan | [12 empty] | 1 | Completed
| Talairon | [12 empty] | 1 | Completed
| Malindang | [12 empty] | 1 | Completed
| P2-Villaflor | [12 empty] | 1 | Completed
| Dullan Sur | [12 empty] | 1 | Completed
| Tuyabang Alto | [12 empty] | 1 | Completed
MISAMIS OCCIDENTAL | PLARIDEL | 1 | 1 | 2.975 |  | 2975000 | 2975000 | 2.975 | [5 empty] | 1 | Completed
MISAMIS OCCIDENTAL | SINACABAN | 1 | 1 | 1.8 |  | 1664907 | 1685266.22 | 1.8 | [5 empty] | 1 | Completed
MISAMIS OCCIDENTAL | TUDELA | 1 | 2 | 6.384 |  | 6366550 | 6366550 | 6.384
| Matay | [12 empty] | 1 | Completed
| Gala | [12 empty] | 1 | Completed
MISAMIS OCCIDENTAL |  | 12 | 27 | 49.1124 | 2 | 48096621.37 | 43973719.65 | 51.1124 | 1 | 0 | 0 | 0 | 0 | 27
MISAMIS ORIENTAL | BALINGOAN | 1 | 1 | 3 |  | 3000000 | 3000000 | 3 | [5 empty] | 1 | Completed |  | 2018-03-20 | NP
MISAMIS ORIENTAL | CAGAYAN DE ORO CITY | 1 | 1 | 4.9 |  | 4900000 | 3920000 | 4.9 | [5 empty] | 1 | Completed | Water pipe laying problem connecting to House to be resolve on July 19, 2017 @ COWD office with the partner agencies and community representatives. (SWA) | 2017-08-01
MISAMIS ORIENTAL | CLAVERIA | 1 | 5 | 2.9325 |  | 2932500 | 2932500 | 2.9325 | [5 empty] | 5
| Aposkahoy, | [13 empty] | Completed
| Plaridel, | [13 empty] | Completed
| Landing & Parmbugas | [13 empty] | Completed
| Sta. Cruz, | [13 empty] | Completed
| Gumaod | [13 empty] | Completed
MISAMIS ORIENTAL | LAGUINDINGAN | 1 | 1 | 5.0673 |  | 4980393.59 | 4980393.59 | 5.0673 | [5 empty] | 1 | Completed
MISAMIS ORIENTAL | LIBERTAD | 1 | 6 | 1.425 |  | 1412543 | 1544722.44 | 1.425 | [5 empty] | 6
| Sitio Danao, Gimaylan, Brgy. Poblacion | [13 empty] | Completed
| Pugaan, Bitaugon, Tabo-o, Brgy. Poblacion | [13 empty] | Completed
| Pugaan, Macalob,Tambp, Brgy. Poblacion | [13 empty] | Completed
| LCS Pumping Station, Poblacion | [13 empty] | Completed
| Taytayan | [13 empty] | Completed
| Sitio Pugaan, Brgy. Poblacion | [13 empty] | Completed
MISAMIS ORIENTAL | LUGAIT | 1 | 1 | 3.5913 |  | 3591250 | 3591250 | 3.5913 | [5 empty] | 1 | Completed
MISAMIS ORIENTAL | MAGSAYSAY | 1 | 1 | 1.33 |  | 1330000 | 1330000 | 1.33 | [5 empty] | 1 | Completed
MISAMIS ORIENTAL | MANTICAO | 1 | 1 | 1 |  | 1000000 | 1000000 | 1 | [5 empty] | 1 | Completed
MISAMIS ORIENTAL | MEDINA | 1 | 4 | 4.0399 |  | 3940125 | 3940125 | 4.0399
| Portulin | [12 empty] | 1 | Completed
| San Isidro | [12 empty] | 1 | Completed
| Dig-aguyan | [12 empty] | 1 | Completed
| Duka Maanas | [12 empty] | 1 | Completed
MISAMIS ORIENTAL | OPOL | 1 | 2 | 6.8 |  | 6222797.15 | 6222797.15 | 6.8
| Poblacion | [12 empty] | 1 | Completed
| Patag | [12 empty] | 1 | Completed
MISAMIS ORIENTAL | TALISAYAN | 1 | 3 | 1.5 |  | 1500000 | 1500000 | 1.5 | [5 empty] | 3
| Puting Balas | [13 empty] | Completed
| San Jose | [13 empty] | Completed
| Sibantang | [13 empty] | Completed
MISAMIS ORIENTAL |  | 11 | 26 | 35.5859 | 0 | 34809608.74 | 33961788.18 | 35.5859 | 0 | 0 | 0 | 0 | 0 | 26
X SUB-TOTAL |  | 54 | 112 | 199.2806 | 6.1675 | 196139308.04 | 191067381.35 | 201.2806 | 6 | 0 | 0 | 0 | 0 | 108

## 2015 BUB-WATER(DONCARLOS)
REGION X
2015 BUB-WATER
as of June 26, 2020
|  |  |  | FINANCIAL |  |  |  |  | CANCELLED PROJECTS | UNDER PREP | APPROVED FS/POW or DED PREP. | PROCUREMENT | ON-GOING | COMPLETED | STATUS | REMARKS | Date Updated
PROVINCES | LGUs | NO. OF LGUs | TOTAL NO. OF PROJECTS | ALLOCATION | CANCELLED ALLOCATION | TOTAL RELEASES | TOTAL LIQUIDATION | AMOUNT OBLIGATED
BUKIDNON | BAUNGON | 1 | 1
| Langaon |  |  | 0.5 |  | 500000 | 408577.19 | 0.5 | [5 empty] | 1 | Completed | SWA | 2018-08-16
BUKIDNON | CABANGLASAN | 1 | 1
| Iba |  |  | 2.5 |  | 2500000 | 2489531.56 | 2.5 | [5 empty] | 1 | Completed | as of 3/13/19 (SWA) | 2019-03-25
BUKIDNON | DANGCAGAN | 1 | 1
| Osmeña |  |  | 0.9 |  | 900000 | 900000 | 0.9 | [5 empty] | 1 | Completed |  | 2018-05-16 | BT
BUKIDNON | DON CARLOS | 1 | 1
| Kasingot, Pualas, Cabadiangan, Kalubihon, Old & New Nonongan, Calao |  |  | 3.78 |  | 3024000 | 3021798.85 | 3.78 |  |  |  |  | 1 |  | 90.25% Physical Accomplishment | FOR CANCELLATION PER ENGR.ALAMBAN | 2020-06-05
BUKIDNON | IMPASUG ONG | 1 | 1
| Bulonay |  |  | 2 |  | 2000000 | 2000000 | 2 | [5 empty] | 1 | Completed | SWA | 2017-09-06
BUKIDNON | KADINGILAN | 1 | 1
| Piag-alaran, Poblacion |  |  | 1.5 |  | 1500000 | 1500000 | 1.5 | [5 empty] | 1 | Completed | SWA | 1/30/2018
BUKIDNON | KIBAWE | 1 | 1 | [10 empty] | 1
| So. Calacapan Spring |  |  | 2 |  | 3978656.35 | 3978656.35 | 2 | [6 empty] | Completed | SWA | 2017-12-12
| Tumaras |  |  | 2 |  |  |  | 2 | [6 empty] | Completed |  | 2018-11-01 | BT
BUKIDNON | MALITBOG | 1 | 1 |  |  |  | 0
| Kalingking |  |  | 1 |  | 1000000 | 1000000 | 1 | [5 empty] | 1 | Completed | SWA | 2017-09-11
BUKIDNON | MANOLO FORTICH | 1 | 4
| So. Bagalangit, Kalugmanan |  |  | 1 |  | 1000000 | 1000000 | 1 | [5 empty] | 1 | Completed |  | 2018-05-16 | BT
| So. Kibulawan, Kalugmanan |  |  | 5 |  | 5000000 | 4981206.63 | 5 | [5 empty] | 1 | Completed | SWA | 2017-12-12 | JB
| B. Proper-Maralum, Sankanan | [13 empty] | Completed |  | 2018-11-01 | BT
| So. Gauron, Sankanan |  |  | 7 |  | 7000000 | 6928304.47 | 7 | [5 empty] | 1 | Completed | SWA | 2018-12-19
| So. Kitam-is, Lunocan |  |  | 6.5 |  | 6500000 | 6500000 | 6.5 | [5 empty] | 1 | Completed |  | 2018-06-19 | BT
| B. Proper Lunocan | [13 empty] | Completed | SWA | 2017-12-12
BUKIDNON | MARAMAG | 1 | 1
| Panadtalan |  |  | 0.7 |  | 700000 | 700000 | 0.7 | [5 empty] | 1 | Completed |  | 2018-06-19 | BT/MCN
BUKIDNON | QUEZON | 1 | 1
| Kipaypayon, Paitan, Lumintao, Butong |  |  | 7.2 |  | 7199989.75 | 7199989.75 | 7.2 | [5 empty] | 1 | Completed
BUKIDNON | SAN FERNANDO | 1 | 1
| Tugop |  |  | 0.5 |  | 500000 | 500000 | 0.5 | [5 empty] | 1 | Completed
BUKIDNON | SUMILAO | 1 | 2
| Poblacion |  |  | 4.5 |  | 2563951.68 | 2563951.68 | 4.5 | [5 empty] | 1 | Completed |  | 2018-06-19 | BT
| Kulasi |  |  | 2.5 |  | 1461520.35 | 1461520.35 | 2.5 | [5 empty] | 1 | Completed |  | 2018-10-25 | ME
BUKIDNON | VALENCIA CITY | 1 | 2
| Brgy. Poblacion, pinatilan, Maapag, Catumbalon, mabuhay, dagatkidavao |  |  | 9.5 |  | 9500000 | 9500000 | 9.5 | [5 empty] | 1 | Completed | SWA | 2017-07-28
| Concepcion |  |  | 2 |  | 2000000 | 2000000 | 2 | [5 empty] | 1 | Completed | SWA | 2017-07-28
| San Carlos |  |  | 1.3 |  | 1300000 | 1300000 | 1.3 | [6 empty] | Completed | SWA | 2017-07-28
BUKIDNON |  | 14 | 19 | 63.88 | 0 | 60128118.13 | 59933536.83 | 63.88 | 0 | 0 | 0 | 0 | 1 | 18
CAMIGUIN | CATARMAN | 1 | 1
| Poblacion & Manduao |  |  | 1 |  | 1000000 | 1000000 | 1 | [5 empty] | 1 | Completed
CAMIGUIN | GUINSILIBAN | 1 | 1
| Butay |  |  | 4 |  | 4000000 | 3118894.26 | 4 | [5 empty] | 1 | Completed | SWA | 2017-12-19
CAMIGUIN | MAHINOG | 1 | 2
| Tupsan Pequeno |  |  | 0.5 |  | 500000 | 425322.72 | 0.5 | [5 empty] | 1 | Completed | completed as of September 13, 2018 (SWA) | 2019-02-22
| Binaliwan |  |  | 0.5 |  | 500000 | 484919.1 | 0.5 | [5 empty] | 1 | Completed | Completed as of January 11, 2019 (SWA) | 2019-02-22
CAMIGUIN | MAMBAJAO | 1 | 1
| Baylao |  |  | 3.5 |  | 3500000 | 3068836.71 | 3.5 | [5 empty] | 1 | Completed | Request for utilization of savings (SWA) | 2017-08-01
CAMIGUIN | SAGAY | 1 | 3
| Sitio Tayong & Cogon Poblacion |  |  | 0.5 |  | 500000 | 500000 | 0.5 | [5 empty] | 1 | Completed
| Sitio Sinablayan, Poblacion |  |  | 0.5 |  | 500000 | 500000 | 0.5 | [5 empty] | 1 | Completed
| Sitio Maranding, Poblacion |  |  | 0.5 |  | 500000 | 500000 | 0.5 | [5 empty] | 1 | Completed
CAMIGUIN |  | 5 | 8 | 11 | 0 | 11000000 | 9597972.79 | 11 | 0 | 0 | 0 | 0 | 0 | 8
LANAO DEL NORTE | BACOLOD | 1 | 1 | [10 empty] | 1
| Kahayag |  |  | 3.603 |  | 3344890.42 | 3344890.42 | 3.603 | [6 empty] | Completed
LANAO DEL NORTE | BALO-I | 1 |  |  | 4
| Cormatan, Sigayam, Cadagunan |  |  |  |  | 0 | 0 |  | 1 | [5 empty] | CANCELLED |  | 2018-02-07 | MCN
LANAO DEL NORTE | BAROY | 1 | 1 |  |  |  | 0 | [6 empty] | 1
| Pendulonan |  |  |  |  | 1061753.75 | 1061753.75 | [7 empty] | Completed |  | 2019-03-04 | nd
| Lindungan |  |  | 1.8918 |  | 830000 | 830000 | 1.8918 | [6 empty] | Completed | SWA | 2017-07-31
LANAO DEL NORTE | KAUSWAGAN | 1 | 1 |  |  |  | 0
| Kawit Oriental, Bagumbayan, Libertad |  |  | 1 |  | 1000000 | 1000000 | 1 | [5 empty] | 1 | Completed |  | .. | Lindao
LANAO DEL NORTE | MAIGO | 1 | 1 |  |  |  | 0
| Mahayahay |  |  | 1 |  | 1000000 | 953888.85 | 1 | [5 empty] | 1 | Completed |  | 2020-01-10 | ND
LANAO DEL NORTE | PANTAR | 1 | 2 |  |  |  | 0
| Bangcal |  |  | 5.14 |  | 4874759.39 | 4874759.39 | 5.14 | [5 empty] | 1 | Completed |  | 10/25/2018 | ME
| Pantar east |  |  | 0.56 |  |  |  | 0.56 | [5 empty] | 1 | Completed |  | 2018-06-19 | ND
LANAO DEL NORTE | TUBOD | 1 | 5
| Licapao |  |  | 1.2 |  | 960000 | 960000 | 1.2 | [5 empty] | 1 | Completed | SWA | 11/22/2018
| Sto. Niño |  |  | 0.8 |  | 800000 | 800000 | 0.8 | [5 empty] | 1 | Completed | SWA | 2017-10-24
| Pualas |  |  | 1 |  | 1000000 | 1000000 | 1 | [5 empty] | 1 | Completed | SWA | 1/29/2018
| Kalilangan |  |  | 1 |  | 1000000 | 1000000 | 1 | [5 empty] | 1 | Completed | SWA | 1/29/2018
| Pinpin |  |  | 0.8 |  | 800000 | 800000 | 0.8 | [5 empty] | 1 | Completed
LANAO DEL NORTE |  | 7 | 11 | 17.9948 | 4 | 16671403.56 | 16625292.41 | 17.9948 | 1 | 0 | 0 | 0 | 0 | 11
MISAMIS OCCIDENTAL | ALORAN | 1 | 1
| Tubod, Ibabao, Ospital, Dalisay, Paldyan, Lobogan, Tamitami, Labo, Casusan |  |  | 9.5 |  | 9500000 | 8977411.79 | 9.5 | [5 empty] | 1 | Completed | as of 12/12/2019 SWA | 2019-12-16
MISAMIS OCCIDENTAL | CALAMBA | 1 | 5 |  |  |  | 0
| San Isidro |  |  | 0.5 |  | 500000 | 499725.99 | 1 | [5 empty] | 1 | Completed | SWA | 2017-07-28
| Dapacan Alto |  |  | 1.5 |  | 1500000 | 1500000 | 0.5 | [5 empty] | 1 | Completed | SWA | 2017-12-12
| Mauswagon |  |  | 1 |  | 1000000 | 869509.7 | 1.5 | [5 empty] | 1 | Completed | SWA | 2017-12-12
| Sulipat |  |  | 1 |  | 1000000 | 947433.46 | 1 | [5 empty] | 1 | Completed | SWA | 2018-02-27
| Bunawan |  |  | 0.5 |  | 500000 | 481949.1 | 0.5 | [5 empty] | 1 | Completed | SWA | 2017-07-28
MISAMIS OCCIDENTAL | CLARIN | 1 | 1
| Guba, Malibangcao, Sigatic Daku |  |  | 3 |  | 3000000 | 2941740 | 3 | [5 empty] | 1 | Completed |  | 2018-08-06 | MOT
MISAMIS OCCIDENTAL | JIMENEZ | 1 | 1 |  |  |  | 0
| Matugas Bajo, Guintomoyan, Sibaroc |  |  | 8.5 |  | 8499762.71 | 8499762.71 | 8.5 | [5 empty] | 1 | Completed | SWA | 2017-09-05
MISAMIS OCCIDENTAL | LOPEZ JAENA | 1 | 1
| Eastern Poblacion & Puntod |  |  | 1.5 |  | 1500000 | 1500000 | 1.5 | [5 empty] | 1 | Completed | SWA | 2017-11-15
MISAMIS OCCIDENTAL | OROQUIETA CITY | 1 | 3 |  |  |  | 0
| Ciriaco Pastrano |  |  | 1 |  | 1000000 | 1000000 | 1 | [5 empty] | 1 | Completed
| Dullan Norte |  |  | 1 |  | 1000000 | 1000000 | 1 | [5 empty] | 1 | Completed | SWA | 2018-06-12
| Senote |  |  | 1 |  | 1000000 | 1000000 | 1 | [5 empty] | 1 | Completed | SWA | 2018-09-24
MISAMIS OCCIDENTAL | PLARIDEL | 1 | 1 |  |  |  | 0
| Umidos - Tipolo |  |  | 3 |  | 3000000 | 3000000 | 3 | [5 empty] | 1 | Completed
MISAMIS OCCIDENTAL | PANAON | 1 | 1
| Mohon |  |  | 1.5 |  | 1392988.06 | 1368908.06 | 1.5 | [5 empty] | 1 | Completed | SWA | 11/28/2017
MISAMIS OCCIDENTAL | TUDELA | 1 | 1 |  |  |  | 0
| Matay Tanggo, Brgy. Namut |  |  | 5 |  | 4989424.17 | 4989424.17 | 5 | [5 empty] | 1 | Completed
MISAMIS OCCIDENTAL |  | 9 | 15 | 39.5 | 0 | 39382174.94 | 38575864.98 | 39.5 | 0 | 0 | 0 | 0 | 0 | 15
MISAMIS ORIENTAL | ALUBIJID | 1 | 1
| Baybay, Loguilo & Poblacion |  |  | 9.1 |  | 9100000 | 9100000 | 9.1 | [5 empty] | 1 | Completed |  | 2018-06-20 | MCN/MO
MISAMIS ORIENTAL | BALINGASAG | 1 | 1 | [10 empty] | 1
| Linabu |  |  | 2.6564 |  | 2656427 | 2656427 | 2.6564 | [6 empty] | Completed
MISAMIS ORIENTAL | CAGAYAN DE ORO CITY | 1 | 4
| Pisag an |  |  | 0.36 |  | 360000 | 360000 | 0.36 | [5 empty] | 1 | Completed
| Tagpangi |  |  | 0.36 |  | 360000 | 360000 | 0.36 | [5 empty] | 1 | Completed
| Taglimao |  |  | 0.36 |  | 360000 | 360000 | 0.36 | [5 empty] | 1 | Completed
| Baikingon |  |  | 1.43 |  | 1430000 | 1430000 | 1.43 | [5 empty] | 1 | Completed
MISAMIS ORIENTAL | CLAVERIA | 1 | 2
| Plaridel & Gumaod |  |  | 3 |  | 3000000 | 2932015 | 3 | [5 empty] | 1 | Completed
| Mat-i |  |  | 1 |  | 1000000 | 999108.13 | 1 | [5 empty] | 1 | Completed
MISAMIS ORIENTAL | GINGOOG CITY | 1 | 1
| Bakid-bakid, Malinao, Eureka & Samay |  |  | 2.5 |  | 2395937.06 | 2290745.06 | 2.5 | [5 empty] | 1 | Completed |  | 2018-03-06 | EJD
MISAMIS ORIENTAL | GITAGUM | 1 | 1
| Poblacion |  |  | 2.7855 |  | 2785540 | 2685776.04 | 2.7855 | [5 empty] | 1 | Completed
MISAMIS ORIENTAL | JASAAN | 1 | 2
| Corales |  |  | 1 |  | 999999 | 886494.11 | 1 | [5 empty] | 1 | Completed
| Upper Jasaan |  |  | 2 |  | 1999999 | 1999999 | 2 | [5 empty] | 1 | Completed
MISAMIS ORIENTAL | KINOGUITAN | 1 | 1
| Poblacion |  |  | 7.5 |  | 7454942.13 | 7454942.13 | 7.5 | [5 empty] | 1 | Competed
MISAMIS ORIENTAL | MAGSAYSAY | 1 | 1
| Kauswagan, Cabubuhan, Poblacion |  |  | 7.5 |  | 7471549.37 | 7471549.37 | 7.5 | [5 empty] | 1 | Completed
MISAMIS ORIENTAL | MANTICAO | 1 | 1
| Poblacion |  |  | 6.75 |  | 6750000 | 6750000 | 6.75 | [5 empty] | 1 | Completed | SWA | 1/29/2018
MISAMIS ORIENTAL | MEDINA | 1 | 3
| Pahindong |  |  | 1 |  | 1000000 | 1000000 | 1 | [5 empty] | 1 | Completed |  | 2018-07-03 | MCN
| Tup-on |  |  | 1 |  | 1000000 | 1000000 | 1 | [5 empty] | 1 | Completed |  | 2018-07-03 | MCN
| Dig-aguyan |  |  | 1 |  | 1000000 | 1000000 | 1 | [5 empty] | 1 | Completed | SWA | 2017-12-12 | NP
MISAMIS ORIENTAL | NAAWAN | 1 | 1
| Don Pedro, Linangkayan, Mapulog, Maputi, Patag, Poblacion & Tuboran |  |  | 12.5 |  | 12299822 | 12299822 | 12.5 | [5 empty] | 1 | Completed |  | 2018-03-20 | NPJ
MISAMIS ORIENTAL | TAGOLOAN | 1 | 1
| Sta. Ana |  |  | 7 |  | 7000000 | 6379506.59 | 7 | [5 empty] | 1 | Completed |  | 2018-06-19 | MCN/MO
MISAMIS ORIENTAL |  | 13 | 20 | 70.802 | 0 | 70424215.56 | 69416384.43 | 70.802 | 0 | 0 | 0 | 0 | 0 | 20
X SUB-TOTAL |  | 48 | 73 | 203.1767 | 4 | 197605912.19 | 194149051.44 | 203.1767 | 1 | 0 | 0 | 0 | 1 | 72

## 2015 BUB-Others
REGION X - BUB
2015 BUB OTHERS
as of June 26, 2020
PROJECT CODE | PMO | FY | REGION | PROVINCE | CITY / MUNICIPALITY | BARANGAY | NAME OF PROJECT | PROJECT TYPE | ORIGINAL ALLOCATION | FINANCIAL | [6 empty] | CANCELLED | UNDER PREP. | APPROVED FS/POW or DED PREP. | PROCUREMENT PROCESS | ON-GOING | COMPLETED | STATUS | REMARKS | DATE UPDATED
ALLOCATION
[10 empty] | AMOUNT | RE-ALIGNED | CANCELLED | REVISED | TOTAL RELEASES | TOTAL LIQUIDATION | AMOUNT OBLIGATED
OT-15-10-13-12-000-01 | BUB-OT | 2015 | REGION_X | BUKIDNON | CITY OF MALAYBALAY |  | CONSTRUCTION OF STEEL FOOTBRIDGE (box culvert) | LOCAL BRIDGES | 740500 | 740500 |  |  | 740500 | 740500 | 740500 | 740500 | [5 empty] | 1 | COMPLETED | SWA | 2017-09-05
OT-15-10-13-21-000-01 | BUB-OT | 2015 | REGION_X | BUKIDNON | CITY OF VALENCIA |  | CONSTRUCTION OF FLOOD CONTROL STRUCTURE | FLOOD CONTROL | 500000 | 500000 |  |  | 500000 | 500000 | 500000 | 500000 | [5 empty] | 1 | COMPLETED
OT-15-10-13-02-000-01 | BUB-OT | 2015 | REGION_X | BUKIDNON | DAMULOG |  | STRENGTHENING PEOPLES ORGANIZATIONS | CAPDEV | 1500000 | 1500000 |  |  | 1500000 | 0 | 0 | 1500000 | [5 empty] | 1 | COMPLETED
OT-15-10-13-05-000-01 | BUB-OT | 2015 | REGION_X | BUKIDNON | IMPASUG_ONG |  | JUNCTION-KIMARAYO-ATUGAN FOOTBRIDGE (CAWAYAN-LA FORTUNA) | LOCAL BRIDGES | 1500000 | 1500000 |  |  | 1500000 | 1496838.63 | 1496838.63 | 1500000 | [5 empty] | 1 | COMPLETED | Inspected last August 17, 2017 (due for turnover) (SWA) | 2017-09-06 | JB
OT-15-10-13-08-000-01 | BUB-OT | 2015 | REGION_X | BUKIDNON | KIBAWE |  | CONSTRUCTION OF FOOTBRIDGE | LOCAL BRIDGES | 2000000 | 2000000 |  |  | 2000000 | 1998476.94 | 1998476.94 | 2000000 | [5 empty] | 1 | COMPLETED
OT-15-10-13-08-000-02 | BUB-OT | 2015 | REGION_X | BUKIDNON | KIBAWE |  | RESCUE EQUIPMENT | RESCUE EQUIPMENT | 500000 | 500000 |  |  | 500000 | 500000 | 500000 | 500000 | [5 empty] | 1 | COMPLETED
OT-15-10-13-10-000-01 | BUB-OT | 2015 | REGION_X | BUKIDNON | LANTAPAN |  | FOOTBRIDGE CONSTRUCTION | LOCAL BRIDGES | 670000 | 670000 |  |  | 670000 | 670000 | 670000 | 670000 | [5 empty] | 1 | COMPLETED
OT-15-10-13-13-000-01 | BUB-OT | 2015 | REGION_X | BUKIDNON | MALITBOG |  | PURCHASE OF ONE (1) UNIT RESCUE VEHICLE (KIA VAN 18 SITTERS) | RESCUE EQUIPMENT | 1300000 | 1300000 |  |  | 1300000 | 1300000 | 1300000 | 1300000 | [5 empty] | 1 | COMPLETED
OT-15-10-13-15-000-01 | BUB-OT | 2015 | REGION_X | BUKIDNON | MARAMAG |  | FLOOD CONTROL- CONSTRUCTION OF DRAINAGE SYSTEM | FLOOD CONTROL | 3000000 | 3000000 |  |  | 3000000 | 2997930.08 | 2997930.08 | 3000000 | [5 empty] | 1 | COMPLETED | SWA | 2017-07-28
OT-15-10-13-17-000-02 | BUB-OT | 2015 | REGION_X | BUKIDNON | QUEZON |  | EVACUATION FACILITY | EVACUATION CENTER | 1325000 | 1325000 |  |  | 1325000 | 1325000 | 1325000 | 1325000 | [5 empty] | 1 | COMPLETED
OT-15-10-13-17-000-03 | BUB-OT | 2015 | REGION_X | BUKIDNON | QUEZON |  | FLOOD CONTROL | FLOOD CONTROL | 2000000 | 2000000 |  |  | 2000000 | 2000000 | 2000000 | 2000000 | [5 empty] | 1 | COMPLETED
OT-15-10-13-18-000-01 | BUB-OT | 2015 | REGION_X | BUKIDNON | SAN FERNANDO |  | CONSTRUCTION OF MALAYANAN FOOTBRIDGE (PHASE II) | LOCAL BRIDGES | 600000 | 600000 |  |  | 600000 | 600000 | 600000 | 600000 | [5 empty] | 1 | COMPLETED
OT-15-10-13-18-000-02 | BUB-OT | 2015 | REGION_X | BUKIDNON | SAN FERNANDO |  | CONSTRUCTION OF HALAPITAN FOOTBRIDGE (PHASE II) | LOCAL BRIDGES | 600000 | 600000 |  |  | 600000 | 600000 | 600000 | 600000 | [5 empty] | 1 | COMPLETED
OT-15-10-13-18-000-03 | BUB-OT | 2015 | REGION_X | BUKIDNON | SAN FERNANDO |  | CONSTRUCTION OF CANDELARIA FOOTBRIDGE | LOCAL BRIDGES | 600000 | 600000 |  |  | 600000 | 600000 | 600000 | 600000 | [5 empty] | 1 | COMPLETED
OT-15-10-13-19-000-01 | BUB-OT | 2015 | REGION_X | BUKIDNON | SUMILAO |  | CONSTRUCTION OF 50 METERS STEEL FOOTBRIDGE | LOCAL BRIDGES | 1500000 | 1500000 |  |  | 1500000 | 1493713.85 | 1493713.85 | 1500000 | [5 empty] | 1 | COMPLETED | for final Inspection (SWA) | 2018-11-01 | BT
SUB-TOTAL (OTHERS) BUKIDNON: |  |  |  |  | 11 |  | 15 |  | 18335500 | 18335500 | 0 | 0 | 18335500 | 16822459.5 | 16822459.5 | 18335500 | 0 | 0 | 0 | 0 | 0 | 15
OT-15-10-13-17-000-01 | BUB-OT | 2015 | REGION_X | BUKIDNON | QUEZON |  | CORE LOCAL ROADS CONSTRUCTION/ MAINTENANCE/ REHABILITATION | LOCAL ROADS | 7200000 | 7200000 |  |  | 7200000 | 7200000 | 7200000 | 7200000 | [5 empty] | 1 | COMPLETED | SWA | 2017-09-06
SUB-TOTAL (LAR) BUKIDNON: | [6 empty] | 1 |  | 7200000 | 7200000 | 0 | 0 | 7200000 | 7200000 | 7200000 | 7200000 | 0 | 0 | 0 | 0 | 0 | 1
TOTAL (OTHERS+LAR) (BUKIDNON): |  |  |  |  | 11 |  | 16 |  | 25535500 | 25535500 | 0 | 0 | 25535500 | 24022459.5 | 24022459.5 | 25535500 | 0 | 0 | 0 | 0 | 0 | 16
OT-15-10-18-01-000-01 | BUB-OT | 2015 | REGION_X | CAMIGUIN | CATARMAN |  | LILOAN EVACUATION CENTER PROJECT | EVACUATION CENTER | 1500000 | 1500000 |  |  | 1500000 | 1500000 | 1500000 | 1500000 | [5 empty] | 1 | COMPLETED
OT-15-10-18-02-000-01 | BUB-OT | 2015 | REGION_X | CAMIGUIN | GUINSILIBAN |  | EQUIPMENTS (COMMUNICATION AND RESCUE) OF BRGY DISASTER COMMAND CENTER AND MOBILITY IN 7 BRGYS | DRRM EQUIPMENT | 500000 | 500000 |  |  | 500000 | 500000 | 500000 | 500000 | [5 empty] | 1 | COMPLETED
OT-15-10-18-04-000-01 | BUB-OT | 2015 | REGION_X | CAMIGUIN | MAMBAJAO |  | RESCUE EQUIPMENT | RESCUE EQUIPMENT | 1175000 | 1175000 |  |  | 1175000 | 1170976 | 1170976 | 1175000 | [5 empty] | 1 | COMPLETED |  | 2018-02-12 | CT/MCN
OT-15-10-18-05-000-01 | BUB-OT | 2015 | REGION_X | CAMIGUIN | SAGAY |  | EVACUATION CENTER | EVACUATION CENTER | 500000 | 500000 |  |  | 500000 | 500000 | 500000 | 500000 | [5 empty] | 1 | COMPLETED
OT-15-10-18-05-000-02 | BUB-OT | 2015 | REGION_X | CAMIGUIN | SAGAY |  | RESCUE EQUIPMENT: PROCUREMENT OF EQUIPMENT | RESCUE EQUIPMENT | 500000 | 500000 |  |  | 500000 | 500000 | 500000 | 500000 | [5 empty] | 1 | COMPLETED
TOTAL (OTHERS) (CAMIGUIN): |  |  |  |  | 4 |  | 5 |  | 4175000 | 4175000 | 0 | 0 | 4175000 | 4170976 | 4170976 | 4175000 |  | 0 | 0 | 0 | 0 | 5
OT-15-10-35-02-000-01 | BUB-OT | 2015 | REGION_X | LANAO DEL NORTE | BALO_I |  | CONSTRUCTION OF FOOTBRIDGE | LOCAL BRIDGES | 500000 | 500000 |  | 500000 |  | 0 | 0 |  | 1 | [5 empty] | CANCELLED |  | 2018-07-10 | MCN
OT-15-10-35-04-000-01 | BUB-OT | 2015 | REGION_X | LANAO DEL NORTE | CITY OF ILIGAN |  | VALUES ENHANCEMENT & CAPACITY BUILDING FOR CIVIL SOCIETY ORGANIZATIONS | CAPDEV | 800000 | 800000 |  |  | 800000 | 0 | 0 | 800000 | [5 empty] | 1 | COMPLETED
OT-15-10-35-04-000-02 | BUB-OT | 2015 | REGION_X | LANAO DEL NORTE | CITY OF ILIGAN | Felomina | IMPROVEMENT OF PUBLIC BUILDING TO BECOME RESILIENT EVACUATION-READY WITH COMPLETE EMERGENCY & SURVIVAL FACILITIES | EVACUATION CENTER | 7700000 | 7700000 |  |  | 7700000 | 6160000 | 5087468.91 | 7700000 | [5 empty] | 1 | CANCELLED |  | 2019-12-06 | ND
[6 empty] | Puga-an | [16 empty] | CANCELLED |  | 2019-12-06 | ND
[6 empty] | Tibanga | [16 empty] | COMPLETED | Date Finished: 2-13-2019 (SWA) | 2019-03-20 | ND 2/22/2019
[6 empty] | Santiago | [16 empty] | COMPLETED | as of 2/13/2019 (SWA) | 2019-03-20
[6 empty] | Acmac | [16 empty] | COMPLETED | Date Finished: 11-16-2018 (SWA0 | 2019-03-20 | ND 2/22/2019
[6 empty] | Hinaplanon | [16 empty] | CANCELLED |  | 2020-01-24 | ND
[6 empty] | Dalipuga | [16 empty] | COMPLETED | Date Finished: 01-12-2019 (SWA) | 2019-03-20 | ND 2/22/2019
OT-15-10-35-08-000-01 | BUB-OT | 2015 | REGION_X | LANAO DEL NORTE | KOLAMBUGAN |  | SEAWALL PROJECT | FLOOD CONTROL | 12500000 | 12500000 |  |  | 12500000 | 11051672.43 | 11051672.43 | 12500000 | [5 empty] | 1 | COMPLETED | Preparations for the Project-Turn Over are now being laid down. (SWA) | 10/19/2017
OT-15-10-35-09-000-01 | BUB-OT | 2015 | REGION_X | LANAO DEL NORTE | LALA |  | CONSTRUCTION OF HANGING BRIDGE @ SIMPAK (PUROK 10-PUROK11) | LOCAL BRIDGES | 1600000 | 1600000 |  |  | 1600000 | 1582677.68 | 1582677.68 | 1600000 | [5 empty] | 1 | COMPLETED
OT-15-10-35-10-000-01 | BUB-OT | 2015 | REGION_X | LANAO DEL NORTE | LINAMON |  | CONSTRUCTION OF EVACUATION CENTER (UPPER MAGO-ONG-UBALDO LOT) | EVACUATION CENTER | 1201600 | 1201600 |  |  | 1201600 | 1196559.38 | 1196559.38 | 1201600 | [5 empty] | 1 | COMPLETED
OT-15-10-35-12-000-01 | BUB-OT | 2015 | REGION_X | LANAO DEL NORTE | MAIGO |  | MAIGO PUBLIC MARKET RENOVATION | ECONOMIC FACILITIES | 1000000 | 1000000 |  |  | 1000000 | 1000000 | 1000000 | 1000000 | [5 empty] | 1 | COMPLETED
OT-15-10-35-12-000-02 | BUB-OT | 2015 | REGION_X | LANAO DEL NORTE | MAIGO |  | FLOOD CONTROL DREDDGING | FLOOD CONTROL | 1700000 | 1700000 |  |  | 1700000 | 1700000 | 1700000 | 1700000 | [5 empty] | 1 | COMPLETED
OT-15-10-35-12-000-04 | BUB-OT | 2015 | REGION_X | LANAO DEL NORTE | MAIGO |  | RUBBER BOAT/RESCUE EQUIPMENT | RESCUE EQUIPMENT | 700000 | 700000 |  |  | 700000 | 700000 | 700000 | 700000 | [5 empty] | 1 | COMPLETED
OT-15-10-35-12-000-05 | BUB-OT | 2015 | REGION_X | LANAO DEL NORTE | MAIGO |  | FLOOD CONTROL AT BUCANA | FLOOD CONTROL | 1500000 | 1500000 |  |  | 1500000 | 1500000 | 1500000 | 1500000 | [5 empty] | 1 | COMPLETED
OT-15-10-35-16-000-01 | BUB-OT | 2015 | REGION_X | LANAO DEL NORTE | PANTAO RAGAT |  | EVACUATION FACILITIES | EVACUATION CENTER | 2200000 | 2200000 |  |  | 2200000 | 2166154.87 | 2166154.87 | 2200000 | [5 empty] | 1 | COMPLETED
OT-15-10-35-16-000-02 | BUB-OT | 2015 | REGION_X | LANAO DEL NORTE | PANTAO RAGAT |  | PROCUREMENT OF RESCUE EQUIPMENT (FOTON CAR) DUMP TRUCK 1 UNIT | RESCUE EQUIPMENT | 1500000 | 1500000 |  |  | 1500000 | 1496964.86 | 1496964.86 | 1500000 | [5 empty] | 1 | COMPLETED
OT-15-10-35-18-000-01 | BUB-OT | 2015 | REGION_X | LANAO DEL NORTE | SALVADOR |  | CONSTRUCTION OF EVACUATION CENTER | EVACUATION CENTER | 7500000 | 7500000 |  |  | 7500000 | 7170017.52 | 7170017.52 | 7500000 | [5 empty] | 1 | COMPLETED | SWA | 1/29/2018
OT-15-10-35-18-000-02 | BUB-OT | 2015 | REGION_X | LANAO DEL NORTE | SALVADOR |  | CONSTRUCTION OF PROTECTION WALL-FLOOD CONTROL IN POBLACION, SALVADOR LDN | FLOOD CONTROL | 5000000 | 5000000 |  |  | 5000000 | 4989620.29 | 4989620.29 | 5000000 | [5 empty] | 1 | COMPLETED
OT-15-10-35-21-000-01 | BUB-OT | 2015 | REGION_X | LANAO DEL NORTE | TANGCAL |  | EVACUATION CENTER | EVACUATION CENTER | 3000000 | 3000000 |  |  | 3000000 | 2914475.74 | 2400000 | 3000000 | [5 empty] | 1 | COMPLETED | SWA | 2017-09-05
OT-15-10-35-22-000-01 | BUB-OT | 2015 | REGION_X | LANAO DEL NORTE | TUBOD |  | CONSTRUCTION OF FOOTBRIDGE | LOCAL BRIDGES | 2800000 | 2800000 |  |  | 2800000 | 2240000 | 2240000 | 2800000 | [5 empty] | 1 | COMPLETED
SUB-TOTAL (OTHERS) LANAO DEL NORTE: |  |  |  |  | 10 |  | 16 |  | 51201600 | 51201600 | 0 | 500000 | 50701600 | 45868142.77 | 44281135.94 | 50701600 | 1 | 0 | 0 | 0 | 0 | 15
OT-15-10-35-02-000-02 | BUB-OT | 2015 | REGION_X | LANAO DEL NORTE | BALO_I |  | CONCRETING OF BARANGAY CORMATAN TO BARANGAY SIGAYAN FMR | LOCAL ROADS | 1000000 | 1000000 |  | 1000000 |  | - | - |  | 1 | [5 empty] | CANCELLED |  | 2018-07-10 | MCN
OT-15-10-35-12-000-03 | BUB-OT | 2015 | REGION_X | LANAO DEL NORTE | MAIGO |  | CONCRETING OF PUROK POBLACION | LOCAL ROADS | 1500000 | 1500000 |  |  | 1500000 | 1500000 | 1500000 | 1500000 | [5 empty] | 1 | COMPLETED
SUB-TOTAL (LAR) LANAO DEL NORTE: | [6 empty] | 2 |  | 2500000 | 2500000 | 0 | 1000000 | 1500000 | 1500000 | 1500000 | 1500000 | 1 | 0 | 0 | 0 | 0 | 1
TOTAL (OTHERS+LAR) (LANAO DEL NORTE): |  |  |  |  | 10 |  | 18 |  | 53701600 | 53701600 | 0 | 1500000 | 52201600 | 47368142.77 | 45781135.94 | 52201600 | 2 | 0 | 0 | 0 | 0 | 16
OT-15-10-42-01-000-01 | BUB-OT | 2015 | REGION_X | MISAMIS OCCIDENTAL | ALORAN |  | REPAIR OF DALISAY-PALAYAN HANGING FOOTBRIDGE | LOCAL BRIDGES | 500000 | 500000 |  |  | 500000 | 500000 | 500000 | 500000 | [5 empty] | 1 | COMPLETED
OT-15-10-42-02-000-01 | BUB-OT | 2015 | REGION_X | MISAMIS OCCIDENTAL | BALIANGAO |  | PROPOSED EVACUATION FACILITY (1 UNIT EVACUATION CENTER) (NORTHERN POBLACION) | EVACUATION CENTER | 500000 | 500000 |  |  | 500000 | 500000 | 500000 | 500000 | [5 empty] | 1 | COMPLETED
OT-15-10-42-02-000-02 | BUB-OT | 2015 | REGION_X | MISAMIS OCCIDENTAL | BALIANGAO |  | PROPOSED EVACUATION FACILITY (1 UNIT EVACUATION CENTER) (NABUROS) | EVACUATION CENTER | 500000 | 500000 |  |  | 500000 | 500000 | 500000 | 500000 | [5 empty] | 1 | COMPLETED
OT-15-10-42-02-000-03 | BUB-OT | 2015 | REGION_X | MISAMIS OCCIDENTAL | BALIANGAO |  | PROPOSED EVACUATION FACILITY (1 UNIT EVACUATION CENTER) (SOUTHERN POBLACION) | EVACUATION CENTER | 500000 | 500000 |  |  | 500000 | 500000 | 500000 | 500000 | [5 empty] | 1 | COMPLETED | as of 7/4/2018 (SWA) | 2019-02-26
OT-15-10-42-02-000-04 | BUB-OT | 2015 | REGION_X | MISAMIS OCCIDENTAL | BALIANGAO |  | PROPOSED EVACUATION FACILITY (1 UNIT EVACUATION CENTER) (MUNICIPAL GROUND) | EVACUATION CENTER | 1100000 | 1100000 |  |  | 1100000 | 1100000 | 1100000 | 1100000 | [5 empty] | 1 | COMPLETED | SWA | 12/21/2018
OT-15-10-42-02-000-05 | BUB-OT | 2015 | REGION_X | MISAMIS OCCIDENTAL | BALIANGAO |  | PROPOSED RESCUE EQUIPMENT (1 MINI DUMP TRUCK) | RESCUE EQUIPMENT | 650000 | 650000 |  |  | 650000 | 650000 | 650000 | 650000 | [5 empty] | 1 | COMPLETED
OT-15-10-42-02-000-06 | BUB-OT | 2015 | REGION_X | MISAMIS OCCIDENTAL | BALIANGAO |  | PROPOSED 1 SET RESCUE EQUIPMENT PRESCRIBED BY OFFICE OF CIVIL DEFENSE DND | RESCUE EQUIPMENT | 1000000 | 1000000 |  |  | 1000000 | 1000000 | 704500 | 1000000 | [5 empty] | 1 | COMPLETED
OT-15-10-42-03-000-01 | BUB-OT | 2015 | REGION_X | MISAMIS OCCIDENTAL | BONIFACIO |  | FLOOD CONTROL | FLOOD CONTROL | 2000000 | 2000000 |  |  | 2000000 | 2000000 | 2000000 | 2000000 | [5 empty] | 1 | COMPLETED
OT-15-10-42-04-000-01 | BUB-OT | 2015 | REGION_X | MISAMIS OCCIDENTAL | CALAMBA |  | CONSTRUCTION OF HANGING BRIDGE | LOCAL BRIDGES | 900000 | 900000 |  |  | 900000 | 900000 | 900000 | 900000 | [5 empty] | 1 | COMPLETED | SWA | 12/20/2018
OT-15-10-42-04-000-02 | BUB-OT | 2015 | REGION_X | MISAMIS OCCIDENTAL | CALAMBA |  | IMPROVEMENT OF EVACUATION CENTER (BRGY. SALVADOR) | EVACUATION CENTER | 750000 | 750000 |  |  | 750000 | 750000 | 741925.63 | 750000 | [5 empty] | 1 | COMPLETED | SWA | 2017-08-16
OT-15-10-42-04-000-03 | BUB-OT | 2015 | REGION_X | MISAMIS OCCIDENTAL | CALAMBA |  | IMPROVEMENT OF EVACUATION CENTER (BRGY. SOLINOG) | EVACUATION CENTER | 500000 | 500000 |  |  | 500000 | 500000 | 443633 | 500000 | [5 empty] | 1 | COMPLETED | SWA | 2017-07-28
OT-15-10-42-04-000-04 | BUB-OT | 2015 | REGION_X | MISAMIS OCCIDENTAL | CALAMBA |  | IMPROVEMENT OF EVACUATION CENTER (SOUTHWESTERN POBLACION) | EVACUATION CENTER | 500000 | 500000 |  |  | 500000 | 500000 | 434790.94 | 500000 | [5 empty] | 1 | COMPLETED | SWA | 2017-07-28
OT-15-10-42-04-000-05 | BUB-OT | 2015 | REGION_X | MISAMIS OCCIDENTAL | CALAMBA |  | CONSTRUCTION OF DRAINAGE CANAL | FLOOD CONTROL | 400000 | 400000 |  |  | 400000 | 400000 | 399534 | 400000 | [5 empty] | 1 | COMPLETED
OT-15-10-42-07-000-02 | BUB-OT | 2015 | REGION_X | MISAMIS OCCIDENTAL | JIMENEZ |  | REHABILITATION OF FLOOD CONTROL-RIZAL STREET | FLOOD CONTROL | 500000 | 500000 |  |  | 500000 | 500000 | 500000 | 500000 | [5 empty] | 1 | COMPLETED
OT-15-10-42-12-000-01 | BUB-OT | 2015 | REGION_X | MISAMIS OCCIDENTAL | PLARIDEL |  | CONSTRUCTION OF DEBOLOC-TIPOLO FOOTBRIDGE | LOCAL BRIDGES | 1500000 | 1500000 |  |  | 1500000 | 1500000 | 1500000 | 1500000 | [5 empty] | 1 | COMPLETED
OT-15-10-42-16-000-01 | BUB-OT | 2015 | REGION_X | MISAMIS OCCIDENTAL | TUDELA |  | FOOTBRIDGE | LOCAL BRIDGES | 500000 | 500000 |  |  | 500000 | 500000 | 500000 | 500000 | [5 empty] | 1 | COMPLETED
OT-15-10-42-16-000-02 | BUB-OT | 2015 | REGION_X | MISAMIS OCCIDENTAL | TUDELA |  | CONSTRUCTION OF FLOOD CONTROL | FLOOD CONTROL | 700000 | 700000 |  |  | 700000 | 700000 | 700000 | 700000 | [5 empty] | 1 | COMPLETED
OT-15-10-42-16-000-03 | BUB-OT | 2015 | REGION_X | MISAMIS OCCIDENTAL | TUDELA |  | CONCRETE DRAINAGE CANAL-MUNICIPAL HALL GROUNDS | FLOOD CONTROL | 1000000 | 1000000 |  |  | 1000000 | 1000000 | 1000000 | 1000000 | [5 empty] | 1 | COMPLETED
SUB-TOTAL (OTHERS) MIS.OCC: |  |  |  |  | 7 |  | 18 |  | 14000000 | 14000000 | 0 | 0 | 14000000 | 14000000 | 13574383.57 | 14000000 | 0 | 0 | 0 | 0 | 0 | 18
OT-15-10-42-07-000-01 | BUB-OT | 2015 | REGION_X | MISAMIS OCCIDENTAL | JIMENEZ |  | CONCRETING BARANGAY NACIONAL-LASTA STREET | LOCAL ROADS | 2000000 | 2000000 |  |  | 2000000 | 2000000 | 2000000 | 2000000 | [5 empty] | 1 | COMPLETED
SUB-TOTAL (LAR) MIS.OCC: | [6 empty] | 1 |  | 2000000 | 2000000 | 0 | 0 | 2000000 | 2000000 | 2000000 | 2000000 | 0 | 0 | 0 | 0 | 0 | 1
TOTAL (OTHERS+LAR) (MISAMIS OCCIDENTAL): |  |  |  |  | 7 |  | 19 |  | 16000000 | 16000000 | 0 | 0 | 16000000 | 16000000 | 15574383.57 | 16000000 | 0 | 0 | 0 | 0 | 0 | 19
OT-15-10-43-02-000-03 | BUB-OT | 2015 | REGION_X | MISAMIS ORIENTAL | BALINGASAG |  | CONSTRUCTION OF ARAAY-LANTAD SPILLWAY | FLOOD CONTROL | 2680000 | 2680000 |  |  | 2680000 | 2680000 | 2680000 | 2680000 | [5 empty] | 1 | COMPLETED
OT-15-10-43-02-000-04 | BUB-OT | 2015 | REGION_X | MISAMIS ORIENTAL | BALINGASAG |  | CONSTRUCTION OF LINED CANAL ALONG MALVAR ST. - BRGY 1 | FLOOD CONTROL | 1424913 | 1424913 |  |  | 1424913 | 1424913 | 1424913 | 1424912.96 | [5 empty] | 1 | COMPLETED
OT-15-10-43-02-000-05 | BUB-OT | 2015 | REGION_X | MISAMIS ORIENTAL | BALINGASAG |  | CONSTRUCTION OF LINED CANAL ALONG REGALADO ST. - BRGY 2 | FLOOD CONTROL | 2135018 | 2135018 |  |  | 2135018 | 2135018 | 2135018 | 2135018.16 | [5 empty] | 1 | COMPLETED
OT-15-10-43-02-000-06 | BUB-OT | 2015 | REGION_X | MISAMIS ORIENTAL | BALINGASAG |  | CONSTRUCTION OF LINED CANAL ALONG MADROÑO ST. - BRGY 5 | FLOOD CONTROL | 1048642 | 1048642 |  |  | 1048642 | 1048642 | 1048642 | 1048641.8 | [5 empty] | 1 | COMPLETED
OT-15-10-43-03-000-01 | BUB-OT | 2015 | REGION_X | MISAMIS ORIENTAL | BALINGOAN |  | EVACUATION FACILITY | EVACUATION CENTER | 7500000 | 7500000 |  |  | 7500000 | 7288588 | 7288588 | 7500000 | [5 empty] | 1 | COMPLETED |  | 2019-07-12 | npjr
OT-15-10-43-04-000-01 | BUB-OT | 2015 | REGION_X | MISAMIS ORIENTAL | BINUANGAN |  | FLOOD CONTROL | FLOOD CONTROL | 12500000 | 12500000 |  |  | 12500000 | 12461686.42 | 12461686.42 | 12500000 | [5 empty] | 1 | COMPLETED
OT-15-10-43-05-000-01 | BUB-OT | 2015 | REGION_X | MISAMIS ORIENTAL | CITY OF CAGAYAN DE ORO |  | EVACUATION CENTER | EVACUATION CENTER | 7140000 | 7140000 |  |  | 7140000 | 7140000 | 7140000 | 7140000 | [5 empty] | 1 | COMPLETED
OT-15-10-43-05-000-02 | BUB-OT | 2015 | REGION_X | MISAMIS ORIENTAL | CITY OF CAGAYAN DE ORO |  | BOTTLE FOR LIFE: A SAFEGUARD KIT TO SURVIVE PROJECT | DRRM EQUIPMENT | 830000 | 830000 |  |  | 830000 | 807242.5 | 807242.5 | 830000 | [5 empty] | 1 | COMPLETED
OT-15-10-43-08-000-01 | BUB-OT | 2015 | REGION_X | MISAMIS ORIENTAL | CITY OF GINGOOG |  | FLOOD CONTROL INFRASTRUCTURES | FLOOD CONTROL | 3163600 | 3163600 |  |  | 3163600 | 3163600 | 3163600 | 3163600 | [5 empty] | 1 | COMPLETED
[7 empty] | Brgy. 24 | [15 empty] | COMPLETED
[7 empty] | Brgy.1 | [15 empty] | COMPLETED
[7 empty] | Brgy. 9 | [15 empty] | COMPLETED
[7 empty] | Brgy.8 | [15 empty] | COMPLETED
[7 empty] | Brgy. 24A | [15 empty] | COMPLETED
[7 empty] | Brgy.16 | [15 empty] | COMPLETED
OT-15-10-43-11-000-01 | BUB-OT | 2015 | REGION_X | MISAMIS ORIENTAL | JASAAN |  | CONSTRUCTION OF 1.5 X 100M FOOTBRIDGE IN SAN ISIDRO-SOLANA | LOCAL BRIDGES | 3000000 | 3000000 |  |  | 3000000 | 2997000 | 2997000 | 3000000 | [5 empty] | 1 | COMPLETED
OT-15-10-43-11-000-02 | BUB-OT | 2015 | REGION_X | MISAMIS ORIENTAL | JASAAN |  | CONSTRUCTION OF 1.5 X 100M FOOTBRIDGE IN SAN NICOLAS | LOCAL BRIDGES | 4000000 | 4000000 |  |  | 4000000 | 3995000 | 3522353.55 | 4000000 | [5 empty] | 1 | COMPLETED
OT-15-10-43-12-000-01 | BUB-OT | 2015 | REGION_X | MISAMIS ORIENTAL | KINOGUITAN |  | CONSTRUCTION OF SEAWALL | FLOOD CONTROL | 5000000 | 5000000 |  |  | 5000000 | 4964443.99 | 4964443.99 | 5000000 | [5 empty] | 1 | COMPLETED
OT-15-10-43-15-000-01 | BUB-OT | 2015 | REGION_X | MISAMIS ORIENTAL | LIBERTAD |  | CONSTRUCTION OF CONCRETE OPEN CANAL/DRAINAGE | FLOOD CONTROL | 1010000 | 1010000 |  |  | 1010000 | 873443.51 | 873443.51 | 1010000 | [5 empty] | 1 | COMPLETED
OT-15-10-43-16-000-01 | BUB-OT | 2015 | REGION_X | MISAMIS ORIENTAL | LUGAIT |  | FLOOD CONTROL | FLOOD CONTROL | 3000000 | 3000000 |  |  | 3000000 | 2998199.06 | 2998199.06 | 3000000 | [5 empty] | 1 | COMPLETED
|  | 2015 | REGION_X | MISAMIS ORIENTAL | MEDINA |  | PROPOSE CONSTRUCTION REHABILITATION OF PERMANENT BRIDGE | LOCAL BRIDGES | 1000000 | 1000000 |  |  | 1000000 | 1000000 | 1000000 | 1000000 | [5 empty] | 1 | COMPLETED | SWA | 2017-10-24
OT-15-10-43-19-000-02 | BUB-OT | 2015 | REGION_X | MISAMIS ORIENTAL | MEDINA |  | PROPOSE CONSTRUCTION/ REHABILITATION OF DRAINAGE SYSTEM | FLOOD CONTROL | 2000000 | 2000000 |  |  | 2000000 | 2000000 | 2000000 | 2000000 | [5 empty] | 1 | COMPLETED |  | 2018-06-20 | MCN
OT-15-10-43-25-000-01 | BUB-OT | 2015 | REGION_X | MISAMIS ORIENTAL | TALISAYAN |  | CONSTRUCTION OF STANDARD EVACUATION CENTER (STA. INES) | EVACUATION CENTER | 3000000 | 3000000 |  |  | 3000000 | 2700000 | 2696370.67 | 3000000 | [5 empty] | 1 | COMPLETED | as of 3/25/2019 (SWA) | 2019-04-01
OT-15-10-43-25-000-02 | BUB-OT | 2015 | REGION_X | MISAMIS ORIENTAL | TALISAYAN |  | CONSTRUCTION OF STANDARD EVACUATION CENTER (POBLACION) | EVACUATION CENTER | 3000000 | 3000000 |  |  | 3000000 | 2700000 | 2700000 | 3000000 | [5 empty] | 1 | COMPLETED | as of 3/25/2019 (SWA) | 2019-04-01
OT-15-10-43-25-000-03 | BUB-OT | 2015 | REGION_X | MISAMIS ORIENTAL | TALISAYAN |  | CONSTRUCTION OF STANDARD EVACUATION CENTER (SAN JOSE) | EVACUATION CENTER | 3000000 | 3000000 |  |  | 3000000 | 2700000 | 2700000 | 3000000 | [5 empty] | 1 | COMPLETED | as of 7/2019 (SWA) | 7/26/2019
OT-15-10-43-25-000-04 | BUB-OT | 2015 | REGION_X | MISAMIS ORIENTAL | TALISAYAN |  | CONSTRUCTION OF SEAWALL | FLOOD CONTROL | 1500000 | 1500000 |  |  | 1500000 | 1310000 | 1310000 | 1500000 | [5 empty] | 1 | COMPLETED |  | 2018-06-20 | MT
OT-15-10-43-26-000-01 | BUB-OT | 2015 | REGION_X | MISAMIS ORIENTAL | VILLANUEVA |  | SOLIGAO TUBURAN 2 CREEK | FLOOD CONTROL | 2500000 | 2500000 |  |  | 2500000 | 2497826.65 | 2497826.65 | 2500000 | [5 empty] | 1 | COMPLETED
OT-15-10-43-26-000-02 | BUB-OT | 2015 | REGION_X | MISAMIS ORIENTAL | VILLANUEVA |  | UPPER DAYAWAN-TUBIGAN CREEK | FLOOD CONTROL | 3500000 | 3500000 |  |  | 3500000 | 3498000.34 | 3498000.34 | 3500000 | [5 empty] | 1 | COMPLETED
OT-15-10-43-26-000-03 | BUB-OT | 2015 | REGION_X | MISAMIS ORIENTAL | VILLANUEVA |  | AMLEY, DAYAWAN-TAG-ANGA CREEK | FLOOD CONTROL | 1500000 | 1500000 |  |  | 1500000 | 1499561.2 | 1499561.2 | 1500000 | [5 empty] | 1 | COMPLETED
SUB-TOTAL (OTHERS) MIS.OR: |  |  |  |  | 12 |  | 23 |  | 75432173 | 75432173 | 0 | 0 | 75432173 | 73883164.67 | 73406888.89 | 75432172.92 | 0 | 0 | 0 | 0 | 0 | 23
OT-15-10-43-02-000-01 | BUB-OT | 2015 | REGION_X | MISAMIS ORIENTAL | BALINGASAG |  | CONCRETING OF QUEZON BARANGAY ROAD | LOCAL ROADS | 2000000 | 2000000 |  |  | 2000000 | 2,000, 000.00 | 2,000, 000.00 | 2000000 | [5 empty] | 1 | COMPLETED
OT-15-10-43-02-000-02 | BUB-OT | 2015 | REGION_X | MISAMIS ORIENTAL | BALINGASAG |  | CONCRETING OF KIBALOS-SAN ISIDRO BARANGAY ROAD | LOCAL ROADS | 2000000 | 2000000 |  |  | 2000000 | 2,000, 000.00 | 2,000, 000.00 | 2000000 | [5 empty] | 1 | COMPLETED
SUB-TOTAL (LAR) MIS.OR: | [6 empty] | 2 |  | 4000000 | 4000000 | 0 | 0 | 4000000 | 0 | 0 | 4000000 | 0 | 0 | 0 | 0 | 0 | 2
TOTAL (OTHERS+LAR) MISAMIS ORIENTAL: |  |  |  |  | 12 |  | 25 |  | 79432173 | 79432173 | 0 | 0 | 79432173 | 73883164.67 | 73406888.89 | 79432172.92 | 0 | 0 | 0 | 0 | 0 | 25
GRAND_TOTAL |  |  |  |  | 44 |  | 83 |  | 178844273 | 178844273 | 0 | 1500000 | 177344273 | 165444742.94 | 162955843.9 | 177344272.92 | 2 | 0 | 0 | 0 | 0 | 81

## 2016 BUB-Others
REGION X - BUB
2016 BUB OTHERS
as of June 26, 2020
PROJECT CODE | PMO | FY | REGION | PROVINCE | CITY / MUNICIPALITY | BARANGAY | NAME OF PROJECT | PROJECT TYPE | ORIGINAL ALLOCATION | FINANCIAL | [6 empty] | CANCELLED | UNDER PREP. | APPROVED FS/POW or DED PREP. | PROCUREMENT PROCESS | ON-GOING | COMPLETED | STATUS | REMARKS | DATE UPDATED
ALLOCATION
[10 empty] | AMOUNT | RE-ALIGNED | CANCELLED | REVISED | TOTAL RELEASES | TOTAL LIQUIDATION | AMOUNT OBLIGATED
OT-16-10-13-09-000-01 | 16 | 2016 | REGION X | BUKIDNON | KITAOTAO | Municipal Wide | RAPID COMMUNITY BASED MONITORING SYSTEM (RCBMS) | CAPDEV/ CBMS | 500000 | 500000 |  |  | 500000 | 500000 | 499940 | 500000 | 1 | [5 empty] | ISSUED NOTICE OF CANCELLATION RE MC 2020-052 | Update form LGCDD | 2020-02-26
OT-16-10-13-10-000-01 | 16 | 2016 | REGION X | BUKIDNON | LANTAPAN | Municipal Wide | COMMUNITY BASED MONITORING SYSTEM (CBMS) THROUGH CBMS APPLICATION AND CBMS PAPER TRACKS | CAPDEV/ CBMS | 1500000 | 1500000 |  |  | 1500000 | 1500000 | 1500000 | 1500000 | 1 | [5 empty] | ISSUED NOTICE OF CANCELLATION RE MC 2020-052 | Update form LGCDD | 2020-02-26
OT-16-10-13-15-000-01 | 16 | 2016 | REGION X | BUKIDNON | MARAMAG | Municipal Wide | Community Based Monitoring System | CAPDEV/ CBMS | 2350000 | 2350000 |  |  | 2350000 | 2350000 | 2290177 | 2350000 | [5 empty] | 1 | ISSUED NOTICE OF LIQUIDATION/ COMPLETED | Update form LGCDD | 2020-02-26
OT-16-10-13-17-000-01 | 16 | 2016 | REGION X | BUKIDNON | QUEZON | Municipal Wide | CBMS | CAPDEV/ CBMS | 2125000 | 2125000 |  |  | 2125000 | 2125000 | 2096534 | 2125000 | 1 | [5 empty] | ISSUED NOTICE OF CANCELLATION RE MC 2020-052 | Update form LGCDD | 2020-02-26
SUB-TOTAL |  |  |  |  | 4 |  | 4 |  | 6475000 | 6475000 | 0 | 0 | 6475000 | 6475000 | 5321060.25 | 6475000 | 3 | 0 | 0 | 0 | 0 | 1
OT-16-10-35-01-000-01 | 16 | 2016 | REGION X | LANAO DEL NORTE | BACOLOD | Municipal wide | Community Based Monitoring System (CBMS) | CAPDEV/ CBMS | 600000 | 600000 |  |  | 600000 | 600000 | - | 600000 | 1 | [5 empty] | ISSUED NOTICE OF CANCELLATION RE MC 2020-052 | Update form LGCDD | 2020-02-26
OT-16-10-35-02-000-01 | 16 | 2016 | REGION X | LANAO DEL NORTE | BALO-I | Municipal wide | Community Based Monitoring System (CBMS) | CAPDEV/ CBMS | 800000 | 800000 |  |  | 800000 | 800000 | - | 800000 | 1 | [5 empty] | ISSUED NOTICE OF CANCELLATION RE MC 2020-052 | Update form LGCDD | 2020-02-26
OT-16-10-35-03-000-01 | 16 | 2016 | REGION X | LANAO DEL NORTE | BAROY | Municipal wide | Community Based Monitoring System (CBMS) | CAPDEV/ CBMS | 1500000 | 1500000 |  |  | 1500000 | 1500000 | 1212886.76 | 1500000 | 1 | [5 empty] | ISSUED NOTICE OF CANCELLATION RE MC 2020-052 | Update form LGCDD | 2020-02-26
OT-16-10-35-04-000-01 | 16 | 2016 | REGION X | LANAO DEL NORTE | CITY OF ILIGAN | Municipal wide | UPDATING COMMUNITY BASED MONITORING SYSTEM | CAPDEV/ CBMS | 1000000 | 1000000 |  |  | 1000000 | 1000000 | - | 1000000 | 1 | [5 empty] | ISSUED NOTICE OF CANCELLATION RE MC 2020-052 | Update form LGCDD | 2020-02-26
OT-16-10-35-05-000-01 | 16 | 2016 | REGION X | LANAO DEL NORTE | KAPATAGAN | Municipal wide | Acquisition of State-of-the-Art Community Based Monitoring System (CBMS) | CAPDEV/ CBMS | 1250000 | 1250000 |  |  | 1250000 | 1250000 | 1250000 | 1250000 | 1 | [5 empty] | ISSUED NOTICE OF CANCELLATION RE MC 2020-052 | Update form LGCDD | 2020-02-26
OT-16-10-35-07-000-01 | 16 | 2016 | REGION X | LANAO DEL NORTE | KAUSWAGAN | Municipal wide | Community Based Monitoring System (CBMS) | CAPDEV/ CBMS | 900000 | 900000 |  |  | 900000 | 900000 | 900000 | 900000 | 1 | [5 empty] | ISSUED NOTICE OF CANCELLATION RE MC 2020-052 | Update form LGCDD | 2020-02-26
OT-16-10-35-08-000-01 | 16 | 2016 | REGION X | LANAO DEL NORTE | KOLAMBUGAN | Kolambugan | Community Based Monitoring System (CBMS) | CAPDEV/ CBMS | 542160 | 542160 |  |  | 542160 | 542160 | 542160 | 542160 | [5 empty] | 1 | COMPLETED | Update form LGCDD | 2020-02-26
SUB-TOTAL |  |  |  |  | 7 |  | 7 |  | 6592160 | 6592160 | 0 | 0 | 6592160 | 6592160 | 3546070.26 | 6592160 | 6 | 0 | 0 | 0 | 0 | 1
OT-16-10-42-03-000-01 | 16 | 2016 | REGION X | MISAMIS OCCIDENTAL | BONIFACIO | Municipal wide | COMMUNITY BASED MONITORING SYSTEM | CAPDEV/ CBMS | 700000 | 700000 |  |  | 700000 | 700000 | 571793 | 700000 | 1 | [5 empty] | ISSUED NOTICE OF CANCELLATION RE MC 2020-052 | Update form LGCDD | 2020-02-26
OT-16-10-42-04-000-01 | 16 | 2016 | REGION X | MISAMIS OCCIDENTAL | CALAMBA | Municipal-wide | COMMUNITY BASED MONITORING SYSTEM | CAPDEV/ CBMS | 500000 | 500000 |  |  | 500000 | 500000 | 417618 | 500000 | 1 | [5 empty] | ISSUED NOTICE OF CANCELLATION RE MC 2020-052 | Update form LGCDD | 2020-02-26
OT-16-10-42-05-000-02 | 16 | 2016 | REGION X | MISAMIS OCCIDENTAL | CLARIN | Municipal-wide | COMMUNITY BASED MONITORING SYSTEM | CAPDEV/ CBMS | 1000000 | 1000000 |  |  | 1000000 | 1000000 | 945904.23 | 1000000 | 1 | [5 empty] | ISSUED NOTICE OF CANCELLATION RE MC 2020-052 | Update form LGCDD | 2020-02-26
OT-16-10-42-17-000-01 | 16 | 2016 | REGION X | MISAMIS OCCIDENTAL | DON VICTORIANO CHIONGBIAN (DON MARIANO MARCOS) | Municipal-wide | COMMUNITY BASED MONITORING SYSTEM | CAPDEV/ CBMS | 541000 | 541000 |  |  | 541000 | 541000 | - | 541000 | 1 | [5 empty] | ISSUED NOTICE OF CANCELLATION RE MC 2020-052 | Update form LGCDD | 2020-02-26
OT-16-10-42-07-000-01 | 16 | 2016 | REGION X | MISAMIS OCCIDENTAL | JIMENEZ | 24 barangays | COMMUNITY BASED MONITORING SYSTEM | CAPDEV/ CBMS | 500000 | 500000 |  |  | 500000 | 500000 | 500000 | 500000 | 1 | [5 empty] | ISSUED NOTICE OF CANCELLATION RE MC 2020-052 | Update form LGCDD | 2020-02-26
OT-16-10-42-08-000-01 | 16 | 2016 | REGION X | MISAMIS OCCIDENTAL | LOPEZ JAENA | Municipal -wide | CBMS. CBMS APP / PAPERS | CAPDEV/ CBMS | 540000 | 540000 |  |  | 540000 | 540000 | 193080 | 540000 | 1 | [5 empty] | ISSUED NOTICE OF CANCELLATION RE MC 2020-052 | Update form LGCDD | 2020-02-26
OT-16-10-42-09-000-02 | 16 | 2016 | REGION X | MISAMIS OCCIDENTAL | CITY OF OROQUIETA (Capital) |  | COMMUNITY BASED MONITORING SYSTEM (CBMS) THROUGH CBMS APPLICATION AND CBMS TRACK | CAPDEV/ CBMS | 1700000 | 1700000 |  |  | 1700000 | 1700000 | 1262679.1 | 2700000 | [5 empty] | 1 | ISSUED NOTICE OF LIQUIDATION/ COMPLETED | Update form LGCDD | 2020-02-26
SUB-TOTAL |  |  |  |  | 7 |  | 7 |  | 5481000 | 5481000 | 0 | 0 | 5481000 | 5481000 | 2525396.1 | 6481000 | 6 | 0 | 0 | 0 | 0 | 1
OT-16-10-43-03-000-01 | 16 | 2016 | REGION X | MISAMIS ORIENTAL | BALINGOAN | 9 barangays | Rapid Community Based Monitoring System (CBMS) | CAPDEV/ CBMS | 500000 | 500000 |  |  | 500000 | 500000 | 463069.05 | 500000 | 1 | [5 empty] | ISSUED NOTICE OF CANCELLATION RE MC 2020-052 | Update form LGCDD | 2020-02-26
OT-16-10-43-05-000-02 | 16 | 2016 | REGION X | MISAMIS ORIENTAL | CITY OF CAGAYAN DE ORO (Capital) | City-wide | COMMUNITY BASED MONITORING SYSTEM | CAPDEV/ CBMS | 1500000 | 1500000 |  |  | 1500000 | 1500000 | 1499998.5 | 1500000 | 1 | [5 empty] | ISSUED NOTICE OF CANCELLATION RE MC 2020-052 | Update form LGCDD | 2020-02-26
OT-16-10-43-12-000-01 | 16 | 2016 | REGION X | MISAMIS ORIENTAL | KINOGUITAN | Municipal wide | Establishment of CBMS | CAPDEV/ CBMS | 500000 | 500000 |  |  | 500000 | 500000 | 466295.2 | 500000 | 1 | [5 empty] | ISSUED NOTICE OF CANCELLATION RE MC 2020-052 | Update form LGCDD | 2020-02-26
OT-16-10-43-17-000-01 | 16 | 2016 | REGION X | MISAMIS ORIENTAL | MAGSAYSAY (LINUGOS) | Municipal wide | COMMUNITY BASED MONITORING SYSTEM (CBMS) | CAPDEV/ CBMS | 800000 | 800000 |  |  | 800000 | 800000 | 800000 | 800000 | [5 empty] | 1 | COMPLETED | Update form LGCDD | 2020-02-26
OT-16-10-43-23-000-01 | 16 | 2016 | REGION X | MISAMIS ORIENTAL | SUGBONGCOGON | Ampianga, Alicomohan, Kiraging, Sta. Cruz, Mimbuahan, Kidampas, Kaulayan, Poblacion, Silad & Mangga | Community Based Monitoring system | CAPDEV/ CBMS | 500000 | 500000 |  |  | 500000 | 500000 | 395780 | 500000 | 1 | [5 empty] | ISSUED NOTICE OF CANCELLATION RE MC 2020-052 | Update form LGCDD | 2020-02-26
OT-16-10-43-24-000-01 | 16 | 2016 | REGION X | MISAMIS ORIENTAL | TAGOLOAN | Municipal wide | Community Based Monitoring System | CAPDEV/ CBMS | 1568000 | 1568000 |  |  | 1568000 | 1568000 | 1384430.25 | 1568000 | 1 | [5 empty] | ISSUED NOTICE OF CANCELLATION RE MC 2020-052 | Update form LGCDD | 2020-02-26
OT-16-10-43-25-000-01 | 16 | 2016 | REGION X | MISAMIS ORIENTAL | TALISAYAN | 18 Brgys | Community Based Monitoring System | CAPDEV/ CBMS | 648000 | 648000 |  |  | 648000 | 648000 | 630632.37 | 648000 | 1 | [5 empty] | ISSUED NOTICE OF CANCELLATION RE MC 2020-052 | Update form LGCDD | 2020-02-26
SUB-TOTAL |  |  |  |  | 7 |  | 7 |  | 6016000 | 6016000 | 0 | 0 | 6016000 | 6016000 | 3233373.97 | 6016000 | 6 | 0 | 0 | 0 | 0 | 1
[5 empty] | 25 |  | 25 |  | 24564160 | 24564160 | 0 | 0 | 24564160 | 24564160 | 14625900.58 | 25564160 | 21 | 0 | 0 | 0 | 0 | 4
OT-16-10-13-03-000-01 | BUB-OT | 2016 | REGION_X | BUKIDNON | DANGCAGAN |  | Renovation/Repair of IP Evacuation Center | EVACUATION CENTER | 700000 | 700000 |  |  | 700000 | 700000 | 700000 | 700000 | [5 empty] | 1 | COMPLETED | SWA | 2017-01-12
SUB-TOTAL |  |  |  |  | 1 |  | 1 |  | 700000 | 700000 | 0 | 0 | 700000 | 700000 | 700000 | 700000 | 0 | 0 | 0 | 0 | 0 | 1
OT-16-10-18-02-000-01 | BUB-OT | 2016 | REGION_X | CAMIGUIN | GUINSILIBAN |  | Evacuation Center @ South Poblacion | EVACUATION CENTER | 3300000 | 3300000 |  |  | 3300000 | 2989956.83 | 3239372.48 | 3300000 | [5 empty] | 1 | COMPLETED | AS OF 02/07/2020 SWA | 2020-03-17
OT-16-10-18-05-000-01 | BUB-OT | 2016 | REGION_X | CAMIGUIN | SAGAY |  | Evacuation Facility: 25 pcs. Cubicles (2-double deck) | EVACUATION CENTER | 1500000 | 1500000 |  |  | 1500000 | 1500000 | 1500000 | 1500000 | [5 empty] | 1 | COMPLETED | SWA | 2017-10-04 | Flor
SUB-TOTAL |  |  |  |  | 2 |  | 2 |  | 4800000 | 4800000 | 0 | 0 | 4800000 | 4489956.83 | 4739372.48 | 4800000 | 0 | 0 | 0 | 0 | 0 | 2
OT-16-10-35-11-000-01 | BUB-OT | 2016 | REGION_X | LANAO_DEL_NORTE | MAGSAYSAY |  | Construction of Crisis Center | EVACUATION CENTER | 5000000 | 5000000 |  |  | 5000000 | 5000000 | 5000000 | 5000000 | [5 empty] | 1 | COMPLETED | SWA | 2017-10-24
SUB-TOTAL |  |  |  |  | 1 |  | 1 |  | 5000000 | 5000000 | 0 | 0 | 5000000 | 5000000 | 5000000 | 5000000 | 0 | 0 | 0 | 0 | 0 | 1
OT-16-10-42-02-000-04 | BUB-OT | 2016 | REGION_X | MISAMIS OCCIDENTAL | BALIANGAO |  | PROPOSED EVACUATION FACILITIES - BRGY. MUNICIPAL GROUND | EVACUATION CENTER | 2000000 | 2000000 |  |  | 2000000 | 1928567.2 | 1928567.2 | 2000000 | [5 empty] | 1 | COMPLETED |  | 2019-07-15 | KE
OT-16-10-42-02-000-02 | BUB-OT | 2016 | REGION_X | MISAMIS OCCIDENTAL | BALIANGAO |  | PROPOSED EVACUATION FACILITIES - BRGY. NABUROS | EVACUATION CENTER | 500000 | 500000 |  |  | 500000 | 465500 | 465500 | 500000 | [5 empty] | 1 | COMPLETED
OT-16-10-42-02-000-01 | BUB-OT | 2016 | REGION_X | MISAMIS OCCIDENTAL | BALIANGAO |  | PROPOSED EVACUATION FACILITIES - BRGY. POBLACION | EVACUATION CENTER | 500000 | 500000 |  |  | 500000 | 461750 | 461750 | 500000 | [5 empty] | 1 | COMPLETED
OT-16-10-42-02-000-03 | BUB-OT | 2016 | REGION_X | MISAMIS OCCIDENTAL | BALIANGAO |  | PROPOSED EVACUATION FACILITIES - BRGY. SOUTHERN POBLACION | EVACUATION CENTER | 500000 | 500000 |  |  | 500000 | 475893.18 | 400000 | 500000 | [5 empty] | 1 | COMPLETED | as of 7/4/2017 (SWA) | 2019-02-26
OT-16-10-42-04-000-02 | BUB-OT | 2016 | REGION_X | MISAMIS OCCIDENTAL | CALAMBA |  | IMPROVEMENT OF MULTI-PURPOSE BUILDING | EVACUATION CENTER | 700000 | 700000 |  |  | 700000 | 700000 | 698803.24 | 700000 | [5 empty] | 1 | COMPLETED | for Final Inspection | 2017-12-12
OT-16-10-42-09-000-01 | BUB-OT | 2016 | REGION_X | MISAMIS OCCIDENTAL | CITY OF OROQUIETA |  | EVACUATION FACILITY - TYPE A (PHASE I) | EVACUATION CENTER | 2700000 | 2700000 |  |  | 2700000 | 2160000 | 1892860.94 | 2700000 | [5 empty] | 1 | COMPLETED | as of 2/15/2019 (SWA) | 2019-08-08
OT-16-10-42-05-000-01 | BUB-OT | 2016 | REGION_X | MISAMIS OCCIDENTAL | CLARIN |  | IMPROVEMENT OF MUNICIPAL EVACUATION CENTER (REFURBISHING) | EVACUATION CENTER | 5000000 | 5000000 |  |  | 5000000 | 4883989.06 | 4883989.06 | 5000000 | [5 empty] | 1 | COMPLETED | SWA | 10/17/2018
OT-16-10-42-12-000-01 | BUB-OT | 2016 | REGION_X | MISAMIS OCCIDENTAL | PLARIDEL |  | CONSTRUCTION OF MULTI-PURPOSE / EVACUATION CENTER AT BRGY. UNIDOS | EVACUATION CENTER | 1500000 | 1500000 |  |  | 1500000 | 1497763.36 | 1497763.36 | 1500000 | [5 empty] | 1 | COMPLETED
OT-16-10-42-16-000-01 | BUB-OT | 2016 | REGION_X | MISAMIS OCCIDENTAL | TUDELA |  | CONSTRUCTION OF EVACUATION CENTER | EVACUATION CENTER | 1773000 | 1773000 |  |  | 1773000 | 1742537.28 | 1742537.28 | 1773000 | [5 empty] | 1 | COMPLETED
SUB-TOTAL |  |  |  |  | 6 |  | 9 |  | 15173000 | 15173000 | 0 | 0 | 15173000 | 14316000.08 | 13971771.08 | 15173000 | 0 | 0 | 0 | 0 | 0 | 9
OT-16-10-43-01-000-01 | BUB-OT | 2016 | REGION_X | MISAMIS ORIENTAL | ALUBIJID |  | Evacuation facility | EVACUATION CENTER | 5000000 | 5000000 |  |  | 5000000 | 4562641.93 | 4562641.93 | 5000000 | [5 empty] | 1 | COMPLETED |  | 2019-07-12 | npjr
OT-16-10-43-05-000-01 | BUB-OT | 2016 | REGION_X | MISAMIS ORIENTAL | CITY OF CAGAYAN DE ORO |  | MULTI-PURPOSE EVACUATION CENTER | EVACUATION CENTER | 3000000 | 3000000 |  |  | 3000000 | 2400000 | 2400000 | 3000000 | [5 empty] | 1 | COMPLETED | Project completed; but SWA is only 80% and 10% remaining fund has not yet requested. LGU already informed but not yet complied | 2018-06-20 | MOT
OT-16-10-43-08-000-01 | BUB-OT | 2016 | REGION_X | MISAMIS ORIENTAL | CITY OF GINGOOG |  | EVACUATION FACILITY | EVACUATION CENTER | 5000000 | 5000000 |  |  | 5000000 | 4986850.65 | 4986850.6 | 5000000 | [5 empty] | 1 | COMPLETED | as of 5/15/2019 SWA | 2019-07-29
OT-16-10-43-10-000-01 | BUB-OT | 2016 | REGION_X | MISAMIS ORIENTAL | INITAO |  | Evacuation Facilities | EVACUATION CENTER | 8500000 | 8500000 |  |  | 8500000 | 8111705.6 | 8111705.65 | 8500000 | [5 empty] | 1 | COMPLETED | SWA | 2017-12-12
OT-16-10-43-19-000-01 | BUB-OT | 2016 | REGION_X | MISAMIS ORIENTAL | MEDINA |  | Improvement of Covered Court | EVACUATION CENTER | 4000000 | 4000000 |  |  | 4000000 | 4000000 | 4000000 | 7200000 | [5 empty] | 1 | COMPLETED |  | 2018-03-20 | MOT
SUB-TOTAL |  |  |  |  | 5 |  | 5 |  | 25500000 | 25500000 | 0 | 0 | 25500000 | 24061198.18 | 24061198.18 | 28700000 | 0 | 0 | 0 | 0 | 0 | 5
[5 empty] | 15 |  | 18 |  | 51173000 | 51173000 | 0 | 0 | 51173000 | 48567155.09 | 48472341.74 | 54373000 | 0 | 0 | 0 | 0 | 0 | 18
GRAND_TOTAL |  |  |  |  | 40 |  | 43 |  | 75737160 | 75737160 | 0 | 0 | 75737160 | 73131315.09 | 63098242.32 | 79937160 | 21 | 0 | 0 | 0 | 0 | 22

## 2016 BUB-WATER
REGION X
2016 BUB-WATER
as of June 26, 2020
|  |  |  | FINANCIAL |  |  |  |  | CANCELLED PROJECTS | UNDER PREP | APPROVED FS/POW or DED PREP. | PROCUREMENT | ON-GOING | COMPLETED | STATUS | REMARKS | Date Updated
PROVINCES | LGUs | NO. OF LGUs | TOTAL NO. OF PROJECTS | ALLOCATION | CANCELLED ALLOCATION | TOTAL RELEASES | TOTAL LIQUIDATION | AMOUNT OBLIGATED
BUKIDNON | CABANGLASAN | 1 | 1 | 5 |  |  |  | 5
| Iba |  |  |  |  | 4948573.02 | 4948573.02 | [6 empty] | 1 | Completed | AS OF 9/9/2019 | 2019-10-11
BUKIDNON | CABANGLASAN | 1 | 1 | 3.4 |  | 3400000 | 3307621.34 | 3.4 | [5 empty] | 1
| Mauswagon |  |  |  |  | 0 | [8 empty] | Completed | SWA | 2017-09-26
| Freedom | [13 empty] | Completed | SWA
| Canangaan |  |  |  |  | 0 | [8 empty] | Completed | SWA | 2017-09-26
| Lambagan | [13 empty] | Completed |  | 2018-05-16 | BT
BUKIDNON | DON CARLOS | 1 | 1 | 11 |  |  |  | 11 | [5 empty] | 1
| Calaocalao, New Nongnongan & Kalubihon |  |  |  |  | 8800000 | 9291766.68 | [7 empty] | Completed | AS OF 1/31/2020 SWA | 2020-02-12
BUKIDNON | IMPASUGONG | 1 | 2 |  |  |  |  | 2.5
| Cawayan & Kibenton |  |  | 2.5 |  | 2500000 | 2500000 | [6 empty] | 1 | Completed | SWA | 2018-06-19
| Kalabugao |  |  | 3.5 |  | 3500000 | 3500000 | 3.5 | [5 empty] | 1 | Completed | SWA | 2018-04-17
BUKIDNON | KALILANGAN | 1 | 1 | 2.2 |  |  |  | 2.2
| Malinao, Forchacu 3, Pontor, & Darusalam (Sitio Maulawe, Ninoy Aquino) |  |  |  |  | 2200000 | 2200000 | [6 empty] | 1 | Completed | SWA | 2018-12-11
BUKIDNON | KITAOTAO | 1 | 1 | 8 |  | 0 |  | 8 |  |  |  |  | 1
| Poblacion |  |  |  |  | 6400000 | 6400000 | [7 empty] | 90.15% Physical Accomplishment |  | 2020-01-30 | MONTHLY MEETING
BUKIDNON | LANTAPAN | 1 | 1 | 10 |  | 0 |  | 10 | [5 empty] | 1
| Sitio San vicente, Kaatuan, Upper Alanib, Batangason, Baclayon, Gahub Baclayon, Upper Balila, & Insibay Poblacion |  |  |  |  | 9811677.76 | 9811677.76 | [7 empty] | Completed | SWA | 2018-07-23
BUKIDNON | LIBONA | 1 | 2 |  |  | 0 |  | 4.1
| Gango and Kinawe |  |  | 4.1 |  | 4100000 | 3077169 | [6 empty] | 1 | Completed | SWA | 2018-06-18
| Sil-ipon |  |  | 10.9 |  | 9893919.35 | 9272993.43 | 10.9 | [5 empty] | 1 | Completed |  | 2019-05-28 | JKB
BUKIDNON | MALAYBALAY CITY | 1 | 2
| Miglamin |  |  | 2.5 |  | 2492423.99 | 2492423.99 | 2.5 | [5 empty] | 1 | Completed | SWA | 2018-03-20 | BT
| Managok |  |  | 5 |  | 4979977.66 | 4979977.66 | 5 | [5 empty] | 1 | Completed | SWA | 2018-03-20 | BT
BUKIDNON | MANOLO FORTICH | 1 | 3 |  |  | 0
| Dalirig/So. Abyawan |  |  | 6.925 |  | 6925000 | 5905740.93 | 6.925 | [5 empty] | 1 | Completed | AS OF 12/23/2019 SWA | 2020-01-24
| Tankulan |  |  | 3 |  | 3000000 | 2999872.02 | 3 | [5 empty] | 1 | Completed | as of 9/28/2019 (SWA) | 2019-10-10
| Diclum |  |  | 3 |  | 3000000 | 2400000 | 3 | [5 empty] | 1 | Completed | as of 9/28/2019 (SWA) | 2019-10-10
BUKIDNON | MARAMAG | 1 | 1
| Anahawon |  |  | 2.5 |  | 2497416 | 2497416 | 2.5 | [5 empty] | 1 | Completed | SWA | 2018-10-09
BUKIDNON | SUMILAO | 1 | 2 |  |  | 0
| Vista Villa and San Roque |  |  | 9 |  | 8280316.86 | 8280316.86 | 9 | [5 empty] | 1 | Completed | Villa Vista and San Roque-Completed | 2018-09-26 | SWA
| Poblacion |  |  | 2.5 |  | 2500000 | 2500000 | 2.5 | [5 empty] | 1 | Completed | SWA | 2018-09-26
BUKIDNON | TALAKAG | 1 | 1 | 24 |  |  |  | 24
| 1, 2, 3, 4, 5, Cosina, Cacaon, Dagumbaan, San Isidro, San Antonio, Sto. Niño, Lingion |  |  |  |  | 19200000 | 18225288.41 |  | 1 | [5 empty] | CANCELLED |  | 2020-06-06 | ENGR. ALAMBAN
BUKIDNON | VALENCIA CITY | 1 | 2
| Kahaponan |  |  | 5 |  | 5000000 | 5000000 | 5 | [5 empty] | 1 | Completed | SWA | 2018-07-17
| San Carlos |  |  | 6 |  | 6000000 | 6000000 | 6 | [5 empty] | 1 | Completed | SWA | 2018-05-31
| Concepcion | [13 empty] | Completed | SWA | 2018-10-16
BUKIDNON |  | 14 | 21 | 130.025 | 0 | 119429304.64 | 115590837.1 | 130.025 | 1 | 0 | 0 | 0 | 1 | 19
CAMIGUIN | MAHINOG | 1 | 1
| Poblacion |  |  | 4 |  | 3998938.96 | 3124401.74 | 4 | [5 empty] | 1 | Completed | SWA | 2018-08-14
CAMIGUIN |  | 1 | 1 | 4 | 0 | 3998938.96 | 3124401.74 | 4 | 0 | 0 | 0 | 0 | 0 | 1
LANAO DEL NORTE | BACOLOD | 1 | 1
| Babalaya |  |  | 3.6 |  | 3279310.47 | 3279310.47 | 3.6 | [5 empty] | 1 | Completed
LANAO DEL NORTE | BAROY | 1 | 1 | 3 |  | 0 | 0
| Brgy. Cabasagan, River Side, Salong, bato |  |  |  |  | 2531759.7 | 2531759.7 | 3 | [5 empty] | 1 | Completed | River side-100% (SWA) 2/7/2019 | 2019-07-19
[16 empty] | Salong-COMPLETED |  | CL
Cabasagan-100% (SWA) 2/7/2019
LANAO DEL NORTE | ILIGAN CITY | 1 | 1 | 5 |  |  |  | 5
| Buru-un |  |  |  |  | 4636000 | 2379431.24 | [6 empty] | 1 | Completed | Project Completed and operational last November 12, 2018 - as of 6/30/2019 update from Office of the ICWS | 7/26/2019
| Saray | [13 empty] | Completed | Project Completed and operational last February 18, 2019 - as of 6/30/2019 update from Office of the ICWS | 7/26/2019
| Sta. Elena | [13 empty] | Completed | Project Completed and operational last April 11, 2019 - as of 6/30/2019 update from Office of the ICWS | 7/26/2019
| Sta. Filomena | [13 empty] | Completed | Project Completed and operational last May 28, 2018 - as of 6/30/2019 update from Office of the ICWS | 7/26/2019
| Acmac | [13 empty] | CANCELLED |  | 2020-01-24 | ND
| Dalipuga | [13 empty] | Completed | Project Completed and operational last April 15, 2019 - as of 6/30/2019 update from Office of the ICWS | 7/26/2019
| Puga-an | [13 empty] | CANCELLED |  | 2020-01-24 | ND
LANAO DEL NORTE | KAPATAGAN | 1 | 1
| Kidalos |  |  | 2.5 |  | 2500000 | 2500000 | 2.5 | [5 empty] | 1 | Completed | SWA | 2018-03-13
LANAO DEL NORTE | LALA | 1 | 1 |  |  | 0 | 0
| Cabasagan |  |  | 7.76 |  | 6329790.38 | 6329790.38 | 7.76 | [5 empty] | 1 | Completed |  | 10/25/2018 | ME
LANAO DEL NORTE | MAIGO | 1 | 1 |  |  | 0 | 0
| Maliwanag |  |  | 4 |  | 3200000 | 3200000 | 4 | [5 empty] | 1 | Completed |  | 2020-01-24 | CL
LANAO DEL NORTE | SULTAN NAGA DIMAPORO | 1 | 1 |  |  | 0 | 0
| Brgy. Campo Islam, Sultan Naga Dimaporo |  |  | 4.7498 |  | 4482127.05 | 4482127.05 | 4.7498 | [5 empty] | 1 | Completed | SWA | 2017-09-26
LANAO DEL NORTE | TAGOLOAN | 1 | 1 |  |  |  | 0
| Brgy Darimbang |  |  | 3 |  | 3000000 | 2669687.79 | 3 | [5 empty] | 1 | Completed | For final Inspection | 2018-05-21 | JE/SWA
LANAO DEL NORTE |  | 8 | 8 | 33.6098 | 0 | 29958987.6 | 27372106.63 | 33.6098 | 0 | 0 | 0 | 0 | 0 | 8
MISAMIS OCCIDENTAL | ALORAN | 1 | 1 |  |  | 0 | 0
| Tuburan, Tawi tawai, maular,conat |  |  | 9 |  | 8605765.99 | 8605765.99 | 9 |  |  |  |  | 1 |  | 90.04% Physical Accomplishment | LGU COUNTERPART ISSUE | 2020-01-23 | CB
MISAMIS OCCIDENTAL | BONIFACIO | 1 | 1
| Poblacion, Digson & D. Fernan |  |  | 3.56 |  | 3550088 | 3550088 | 3.56 | [5 empty] | 1 | Completed |  | 2018-08-06 | MOT
MISAMIS OCCIDENTAL | CALAMBA | 1 | 1 |  |  | 0
| Municipal-wide |  |  | 3.9 |  | 3120000 | 3120000 | 3.9 | [5 empty] | 1 | Completed | as of 3/8/2019 (SWA) | 2019-03-29
MISAMIS OCCIDENTAL | JIMENEZ | 1 | 1 |  |  | 0
| Dicoloc, Butuay, Palilan |  |  | 9 |  | 9000000 | 9000000 | 9 | [5 empty] | 1 | Completed | SWA | 2017-09-05
MISAMIS OCCIDENTAL | LOPEZ JAENA | 1 | 1 |  |  | 0
| Municipal waters Puntod-man Bajo |  |  | 7 |  | 6514976.54 | 6514976.54 | 7 | [5 empty] | 1 | Completed | as of 6/13/2019 (SWA) | 2019-06-14
MISAMIS OCCIDENTAL | PANAON | 1 | 1 |  |  | 0
| Municipal-wide |  |  | 6.5 |  | 5200000 | 3371441.81 | 6.5 |  |  |  |  | 1 |  | 80% Physical Accomplishment | AS OF 12/18/2019 SWA | 2020-01-02
MISAMIS OCCIDENTAL | PLARIDEL | 1 | 1 |  |  | 0
| Unidos-Mangidkid -Sitio Balainlao (bato) |  |  | 2.5 |  | 2500000 | 2500000 | 2.5 | [5 empty] | 1 | Completed
MISAMIS OCCIDENTAL | TANGUB CITY | 1 | 1
| 3 barangays |  |  | 5 |  | 4000000 | 4000000 | 5 | [5 empty] | 1 | Completed | AS OF 1/20/2020 SWA | 2020-02-03
MISAMIS OCCIDENTAL | TUDELA | 1 | 1
| Matay, Tongo-Namut |  |  | 10 |  | 9856594.5 | 9856594.5 | 10 | [5 empty] | 1 | Completed
MISAMIS OCCIDENTAL |  | 9 | 9 | 56.46 | 0 | 52347425.03 | 50518866.84 | 56.46 | 0 | 0 | 0 | 0 | 2 | 7
MISAMIS ORIENTAL | BALINGOAN | 1 | 1
| 9 barangays |  |  | 4.5 |  | 4500000 | 4500000 | 4.5 | [5 empty] | 1 | Completed |  | 2020-01-23 | NPJ
MISAMIS ORIENTAL | CLAVERIA | 1 | 2
| Poblacion |  |  | 3.5 |  | 3500000 | 2800000 | 3.5 | [5 empty] | 1 | Completed |  | 2020-01-24 | NPJ
| Brgys Bulahan, Tripolohon & Don Gregorio Pelaez |  |  | 3 |  | 3000000 | 2373282.35 | 3 | [5 empty] | 1 | Completed |  | 2020-01-24 | NPJ
MISAMIS ORIENTAL | GITAGUM | 1 | 1 |  |  | 0
| Poblacion |  |  | 3 |  | 3000000 | 3000000 | 3 | [5 empty] | 1 | COMPLETED
MISAMIS ORIENTAL | JASAAN | 1 | 2 |  |  | 0
| Natubo |  |  | 5 |  | 4993572.29 | 4993572.29 | 5 | [5 empty] | 1 | COMPLETED | SWA | 2017-09-11 | NPJ
| Bobontugan |  |  | 2.3 |  | 2300000 | 2584336.34 | 2.3 | [5 empty] | 1 | COMPLETED | SWA | 2017-09-11 | NPJ
MISAMIS ORIENTAL | KINOGUITAN | 1 | 1
| Municipal wide |  |  | 14.5 |  | 14352106.69 | 12701957.71 | 14.5 | [5 empty] | 1 | COMPLETED |  | 2019-07-12 | npjr
MISAMIS ORIENTAL | LIBERTAD | 1 | 1 | 10 |  | 9117355.27 | 7259244.35 | 10 | [5 empty] | 1 | COMPLETED
| Lubluban | [14 empty] | Lubluban - 100% (as of 7/22/2019-SWA) | 2019-08-12
| Kimalok | [14 empty] | Kimalok - 100% (as of 7/22/2019-summary monthly accomp. Report) | 2019-08-12
| Tangkub | [14 empty] | Tangkub - 100% (as of 7/22/2019-SWA) | 2019-08-12
| Poblacion | [14 empty] | Poblacion - 100% (as of 7/22/2019-SWA) | 2019-08-12
| Gimaylan | [14 empty] | Gimaylan - 100% (as of 7/22/2019-summary monthly accomp. Report) | 2019-08-12
| Sto. Niño | [14 empty] | Sto. Nino - 100% (as of 7/22/2019-SWA) | 2019-08-12
| Taytayan | [14 empty] | Taytayan - 100% (as of 7/22/2019-summary monthly accomp. Report) | 2019-08-12
| Retablo | [14 empty] | Retablo - 100% (as of 7/22/2019-summary monthly accomp. Report) | 2019-08-12
| Dulong | [14 empty] | Dulong - 100% (as of 7/22/2019-SWA) | 2019-08-12
MISAMIS ORIENTAL | MAGSAYSAY | 1 | 1
| Kibungsod, Consuelo, San Isidro, Damayuhan, Villa Felipa & Cabalawan |  |  | 10 |  | 10000000 | 10000000 | 10 | [5 empty] | 1 | COMPLETED | SWA | 2018-06-21
MISAMIS ORIENTAL | MANTICAO | 1 | 1
| Poblacion |  |  | 4 |  | 3997692.45 | 3997692.45 | 4 | [5 empty] | 1 | COMPLETED | SWA | 2018-08-15
MISAMIS ORIENTAL |  | 8 | 10 | 59.8 | 0 | 58760726.7 | 54210085.49 | 59.8 | 0 | 0 | 0 | 0 | 0 | 10
SUB-TOTAL |  | 40 | 49 | 283.8948 | 0 | 264495382.93 | 250816297.8 | 283.8948 | 1 | 0 | 0 | 0 | 3 | 45

## 2016 LGSF-Others
REGION X - BUB
2016 LGSF-OTHERS
as of June 26, 2020
PROJECT CODE | PMO | FY | REGION | PROVINCE | CITY / MUNICIPALITY | BARANGAY | NAME OF PROJECT | PROJECT DESCRIPTION | PROJECT TYPE | ORIGINAL ALLOCATION | OBLIGATION | DISBURSEMENT | CANCELLED | UNDER PREP | APPROVED FS/POW or DED PREP. | PROCUREMENT | ON-GOING | COMPLETED | STATUS | REMARKS | Date Updated
BUKIDNON
OL-16-10-13-01-000-01 | L-OT | 2016 | REGION_X | BUKIDNON | BAUNGON |  | Concreting of Barangay Access Road (ICES Junction to BNHS, 550m.) |  |  | 6600000 | [7 empty] | 1 | COMPLETED | completed as of 5/2018 (SWA) | 2018-06-18
OL-16-10-13-22-000-01 | L-OT | 2016 | REGION_X | BUKIDNON | CABANGLASAN |  | Road Concreting from Townsite Proper to Old Poblacion |  |  | 4000000 | [7 empty] | 1 | COMPLETED | completed as of 3-9-2018 (SWA) | 2018-05-08
OL-16-10-13-02-000-01 | L-OT | 2016 | REGION_X | BUKIDNON | DAMULOG |  | Rehabilitation of Crossing Kinapat to Lumatong FMR |  |  | 500000 | [7 empty] | 1 | COMPLETED | SWA | 2017-12-19
OL-16-10-13-02-000-02 | L-OT | 2016 | REGION_X | BUKIDNON | DAMULOG |  | Rehabilitation of Aludas FMR |  |  | 1000000 | [7 empty] | 1 | COMPLETED | SWA | 2017-12-19
OL-16-10-13-02-000-03 | L-OT | 2016 | REGION_X | BUKIDNON | DAMULOG |  | Rehabilitation of Kidama to Basag FMR |  |  | 2000000 | [7 empty] | 1 | COMPLETED | SWA | 2018-11-16
OL-16-10-13-02-000-04 | L-OT | 2016 | REGION_X | BUKIDNON | DAMULOG |  | Rehabilitation of Tukod to Inlabo FMR |  |  | 2000000 |  |  | 1 | [5 empty] | CANCELLED | Letter dated 6/19/2019; Returned to BTr | 2019-06-21 | FCLA
OL-16-10-13-02-000-05 | L-OT | 2016 | REGION_X | BUKIDNON | DAMULOG |  | Rehabilitation of Angga-an to Turonan FMR |  |  | 2000000 | [7 empty] | 1 | COMPLETED | SWA | 2018-11-16
OL-16-10-13-02-000-06 | L-OT | 2016 | REGION_X | BUKIDNON | DAMULOG |  | Rehabilitation of P-1 to P-5 FMR at LAGANDANG |  |  | 1425000 | [7 empty] | 1 | COMPLETED |  | 2018-10-26 | ME
OL-16-10-13-03-000-01 | L-OT | 2016 | REGION_X | BUKIDNON | DANGCAGAN |  | Core Local Road Rehabilitation |  |  | 6060000 | [7 empty] | 1 | COMPLETED | Dolorosa, San Vicente and Bugwak-Completed | 2018-09-13 | Monthly report
OL-16-10-13-06-000-01 | L-OT | 2016 | REGION_X | BUKIDNON | KADINGILAN |  | 1. Concreting of Barangay Road - 0.150 KM Crossing Pay-as to Payao Road Section |  | Roads/ Bridges - LGSF | 1650000 | [7 empty] | 1 | COMPLETED | SWA | 2018-07-10
OL-16-10-13-06-000-02 | L-OT | 2016 | REGION_X | BUKIDNON | KADINGILAN |  | 2. Concreting of Barangay Road - 0.150 KM Crossing Bagor to Payao Road Section |  | Roads/ Bridges - LGSF | 1650000 | [7 empty] | 1 | COMPLETED | SWA | 2018-07-10
OL-16-10-13-06-000-03 | L-OT | 2016 | REGION_X | BUKIDNON | KADINGILAN |  | 3. Concreting of Barangay Road - 0.100 KM Mabuhay to Bolisong Road Secion |  | Roads/ Bridges - LGSF | 1100000 | [7 empty] | 1 | COMPLETED | SWA | 2018-05-08
OL-16-10-13-06-000-04 | L-OT | 2016 | REGION_X | BUKIDNON | KADINGILAN |  | 4. Concreting of Barangay Road - 0.170 KM Macao Road Section |  | Roads/ Bridges - LGSF | 1870000 | [7 empty] | 1 | COMPLETED | SWA | 2018-02-13
OL-16-10-13-06-000-05 | L-OT | 2016 | REGION_X | BUKIDNON | KADINGILAN |  | 5. Concreting of Barangay Road - 0.100 KM Matampay Road Section |  | Roads/ Bridges - LGSF | 1100000 | [7 empty] | 1 | COMPLETED | as of 8/21/2018 (SWA) | 2019-04-16
OL-16-10-13-06-000-06 | L-OT | 2016 | REGION_X | BUKIDNON | KADINGILAN |  | 6. Concreting of Barangay Road - 0.150 Cabadiangan Road junction Kibalangon and Matampay Road |  | Roads/ Bridges - LGSF | 1650000 | [7 empty] | 1 | COMPLETED | SWA | 2018-05-08
OL-16-10-13-06-000-07 | L-OT | 2016 | REGION_X | BUKIDNON | KADINGILAN |  | 7. Concreting of Barangay Road - 0.100 KM Kibalogan Road Section |  | Roads/ Bridges - LGSF | 1100000 | [7 empty] | 1 | COMPLETED | SWA | 2018-07-26
OL-16-10-13-06-000-08 | L-OT | 2016 | REGION_X | BUKIDNON | KADINGILAN |  | 8. Concreting of Barangay Road - 0.100 KM Poblacion to Salvacion Road Section |  | Roads/ Bridges - LGSF | 971500 | [7 empty] | 1 | COMPLETED | as of 8/21/2018 (SWA) | 2019-04-15
OL-16-10-13-06-000-09 | L-OT | 2016 | REGION_X | BUKIDNON | KADINGILAN |  | 9. Concreting of Barangay Road - 0.100 KM Baroy to Sibonga Road Section |  | Roads/ Bridges - LGSF | 1100000 | [7 empty] | 1 | COMPLETED | SWA | 2018-07-26
OL-16-10-13-06-000-10 | L-OT | 2016 | REGION_X | BUKIDNON | KADINGILAN |  | 10. Concreting of Barangay Road - 0.100 KM Husayan Road Section |  | Roads/ Bridges - LGSF | 1100000 | [7 empty] | 1 | COMPLETED | SWA | 2018-07-10
PL-16-10-13-07-000-01 | L-OT | 2016 | REGION_X | BUKIDNON | KALILANGAN |  | Core LOCAL ROAD CONSTRUCTION (INFASTRUCTURE) |  | Roads/ Bridges - LGSF | 6550000 | [7 empty] | 1 | COMPLETED | Ninoy Aquino-100% (SWA) | 2019-03-27
West Poblacion-100% (SWA)
Macaopao-100% (as of 1/24/2019) (SWA)
Barorawan-100% (SWA)
Bangbang-100% (SWA)
OL-16-10-13-08-000-02 | L-OT | 2016 | REGION_X | BUKIDNON | KIBAWE |  | Road Rehabilitaion |  | Roads/ Bridges - LGSF | 5000000 | [7 empty] | 1 | COMPLETED | SWA | 2018-04-12
OL-16-10-13-09-000-01 | L-OT | 2016 | REGION_X | BUKIDNON | KITAOTAO |  | Core Local Road Concreting |  | Roads/ Bridges - LGSF | 3500000 | [7 empty] | 1 | COMPLETED |  | 2018-05-16 | BT
OL-16-10-13-16-000-01 | L-OT | 2016 | REGION_X | BUKIDNON | PANGANTUCAN |  | Concreting of Road Portulin |  | Roads/ Bridges - LGSF | 3600000 | [7 empty] | 1 | COMPLETED |  | 12/21/2018 | JB
OL-16-10-13-16-000-02 | L-OT | 2016 | REGION_X | BUKIDNON | PANGANTUCAN |  | Concreting of Road Pigtauranan |  | Roads/ Bridges - LGSF | 2400000 | [7 empty] | 1 | COMPLETED |  | 2018-05-16 | BT
OL-16-10-13-16-000-03 | L-OT | 2016 | REGION_X | BUKIDNON | PANGANTUCAN |  | Concreting of Road Concepcion |  | Roads/ Bridges - LGSF | 1200000 | [7 empty] | 1 | COMPLETED | SWA | 11/29/2017
OL-16-10-13-17-000-02 | L-OT | 2016 | REGION_X | BUKIDNON | QUEZON |  | Core Local Roads |  | Roads/ Bridges - LGSF | 850000 |  |  | 1 | [5 empty] | CANCELLED |  | 12/20/2018 | JB
OL-16-10-13-17-000-03 | L-OT | 2016 | REGION_X | BUKIDNON | QUEZON |  | Core Local Roads |  | Roads/ Bridges - LGSF | 850000 |  |  | 1 | [5 empty] | CANCELLED |  | 12/20/2018 | JB
OL-16-10-13-17-000-04 | L-OT | 2016 | REGION_X | BUKIDNON | QUEZON |  | Core Local Roads |  | Roads/ Bridges - LGSF | 5505000 | [7 empty] | 1 | COMPLETED | SWA | 2018-05-08
OL-16-10-13-17-000-05 | L-OT | 2016 | REGION_X | BUKIDNON | QUEZON |  | Core Local Roads |  | Roads/ Bridges - LGSF | 8500000 | [7 empty] | 1 | COMPLETED | as of 4/23/2019 (SWA) | 2019-05-10
OL-16-10-13-21-000-02 | L-OT | 2016 | REGION_X | BUKIDNON | CITY OF VALENCIA |  | CONSTRUCTION OF SECONDARY ROAD IN BARANGAY POBLACION |  | Roads/ Bridges - LGSF | 10000000 | 10000000 | 10000000 | [5 empty] | 1 | COMPLETED | SWA | 2018-07-17
SUB-TOTAL (LAR) BUKIDNON: |  |  |  |  | 11 |  | 30 |  |  | 86831500 | 10000000 | 10000000 | 3 | 0 | 0 | 0 | 0 | 27
LO-16-10-13-04-000-1 | L-OT | 2016 | REGION_X | BUKIDNON | DON CARLOS |  | RESCUE EQUIPMENT 10 WHEELER DUMP (4 WHEEL DRIVE) | 1 unit disaster equipment for disaster response | Rescue Vehicle | 3200000 |  | - | 1 | [5 empty] | CANCELLED | Returned to BTr | 2019-06-26 | FCLA
LO-16-10-13-04-000-2 | L-OT | 2016 | REGION_X | BUKIDNON | DON CARLOS |  | PROCUREMENT OF 4.6 MTS. SMALL FIBERGLASS BOAT | 1 unit disaster equipment for water disaster | Rescue Vehicle | 1000000 |  | - | 1 | [5 empty] | CANCELLED | Returned to BTr | 2019-06-26 | FCLA
OL-16-10-13-05-000-01 | L-OT | 2016 | REGION_X | BUKIDNON | IMPASUG-ONG |  | Habiogan Footbridge |  |  | 1500000 | [7 empty] | 1 | COMPLETED | as of completed as of 9/19/2018 | 2019-01-15 | MAT
OL-16-10-13-07-000-02 | L-OT | 2016 | REGION_X | BUKIDNON | KALILANGAN | Kinura | CONSTRUCTION OF FOOTBRIDGE |  | Roads/ Bridges - LGSF | 500000 | [7 empty] | 1 | COMPLETED | completed as of 4/30/2018 | 2019-01-15 | MAT
| L-OT | 2016 | REGION_X | BUKIDNON | KALILANGAN |  | IRRIGATION FACILITIES |  |  | 500000 |  |  | 1 | [5 empty] | CANCELLED | Returned to BTr | 2019-06-26 | FCLA
OL-16-10-13-08-000-01 | L-OT | 2016 | REGION_X | BUKIDNON | KIBAWE |  | Footbridge |  | Roads/ Bridges - LGSF | 500000 | [7 empty] | 1 | COMPLETED | SWA | 2017-12-12
LO-16-10-13-13-000-1 | L-OT | 2016 | REGION_X | BUKIDNON | MALITBOG | Omagling & Poblacion | Flood Control Project (Phase I) | 195 meter Flood Control | Flood Control | 3900000 | 3900000 | 3900000 | [5 empty] | 1 | COMPLETED |  | 2018-03-20 | BT
LO-16-10-13-15-016-1 | L-OT | 2016 | REGION_X | BUKIDNON | MARAMAG | San Miguel | Flood Control - Construction of Drainage System | Drainage system constructed | Flood Control | 500000 | 500000 | 500000 | [5 empty] | 1 | COMPLETED |  | 2018-03-20 | BT
OL-16-10-13-16-000-04 | L-OT | 2016 | REGION_X | BUKIDNON | PANGANTUCAN |  | Flood Control |  | Flood Control - LGSF | 600000 | [7 empty] | 1 | COMPLETED |  | 2018-06-21 | MOT
OL-16-10-13-17-000-01 | L-OT | 2016 | REGION_X | BUKIDNON | QUEZON |  | Flood Control |  | Flood Control - LGSF | 2125000 | [7 empty] | 1 | COMPLETED | completed as of 7/11/2018 (SWA) | 2019-01-15
OL-16-10-13-18-000-01 | L-OT | 2016 | REGION_X | BUKIDNON | SAN FERNANDO |  | Construction of Lower Macabongbong Footbridge |  | Roads/ Bridges - LGSF | 500000 | [7 empty] | 1 | COMPLETED | SWA | 2019-01-28
OL-16-10-13-18-000-02 | L-OT | 2016 | REGION_X | BUKIDNON | SAN FERNANDO |  | Construction of Halapitan Footbridge (Phase III) |  | Roads/ Bridges - LGSF | 500000 | [7 empty] | 1 | COMPLETED
OL-16-10-13-18-000-03 | L-OT | 2016 | REGION_X | BUKIDNON | SAN FERNANDO |  | Construction of Candelaria Footbridge (Phase II) |  | Roads/ Bridges - LGSF | 500000 | [7 empty] | 1 | COMPLETED
PL-16-10-13-18-000-03 | L-OT | 2016 | REGION_X | BUKIDNON | SAN FERNANDO |  | Construction of Malayanan Footbridge (Phase II) |  | Roads/ Bridges - LGSF | 500000 | [7 empty] | 1 | COMPLETED
LO-16-10-13-21-007-1 | L-OT | 2016 | REGION_X | BUKIDNON | CITY OF VALENCIA | Concepcion | CONSTRUCTION OF BOX CULVERT | Constructed a Single Barrel Box Culvert in Barangay Concepcion | Flood Control | 1500000 | 1500000 | 1500000 | [5 empty] | 1 | COMPLETED | SWA | 2018-03-27
SUB-TOTAL (OTHERS) BUKIDNON: |  |  |  |  | 5 |  | 15 |  |  | 17825000 | 5900000 | 5900000 | 3 | 0 | 0 | 0 | 0 | 12
TOTAL (OTHERS+LAR) (BUKIDNON) |  |  |  |  | 16 |  | 45 |  |  | 104656500 | 15900000 | 15900000 | 6 | 0 | 0 | 0 | 0 | 39
CAMIGUIN
OL-16-10-18-01-000-01 | L-OT | 2016 | REGION_X | CAMIGUIN | CATARMAN |  | Concreting of Quidag-um Barangay Road connecting Pasanan Barangay Road (Phase II) |  | Roads/ Bridges - LGSF | 12000000 | [7 empty] | 1 | COMPLETED
OL-16-10-18-02-000-02 | L-OT | 2016 | REGION_X | CAMIGUIN | GUINSILIBAN |  | Core Local Road to Nursery |  | Roads/ Bridges - LGSF | 3000000 | [7 empty] | 1 | COMPLETED |  | 2018-09-26 | KA
OL-16-10-18-03-000-01 | L-OT | 2016 | REGION_X | CAMIGUIN | MAHINOG |  | Core Local Road Construction - Concreting in Benoni |  | Roads/ Bridges - LGSF | 1000000 | [7 empty] | 1 | COMPLETED
OL-16-10-18-03-000-02 | L-OT | 2016 | REGION_X | CAMIGUIN | MAHINOG |  | Core Local Road Construction - Concreting in Poblacion |  | Roads/ Bridges - LGSF | 1000000 | [7 empty] | 1 | COMPLETED
OL-16-10-18-03-000-03 | L-OT | 2016 | REGION_X | CAMIGUIN | MAHINOG |  | Core Local Road Construction - Concreting in Tacangon, Poblacion |  | Roads/ Bridges - LGSF | 500000 | [7 empty] | 1 | COMPLETED
OL-16-10-18-03-000-04 | L-OT | 2016 | REGION_X | CAMIGUIN | MAHINOG |  | Core Local Road Construction - Concreting in Upper San Roque - NHA, Benoni |  | Roads/ Bridges - LGSF | 1000000 | [7 empty] | 1 | COMPLETED
OL-16-10-18-03-000-05 | L-OT | 2016 | REGION_X | CAMIGUIN | MAHINOG |  | Core Local Road Construction - Concreting in Tubod |  | Roads/ Bridges - LGSF | 500000 | [7 empty] | 1 | COMPLETED
OL-16-10-18-03-000-06 | L-OT | 2016 | REGION_X | CAMIGUIN | MAHINOG |  | Core Local Road Construction - Concreting in Hubangon |  | Roads/ Bridges - LGSF | 1200000 | [7 empty] | 1 | COMPLETED
OL-16-10-18-04-000-01 | L-OT | 2016 | REGION_X | CAMIGUIN | MAMBAJAO (Capital) |  | Concreting of Binunsaran - Campana Core Road |  | Roads/ Bridges - LGSF | 2500000 | [7 empty] | 1 | COMPLETED | SWA | 2018-09-11
OL-16-10-18-04-000-02 | L-OT | 2016 | REGION_X | CAMIGUIN | MAMBAJAO (Capital) |  | Concreting of Itum - Tabogtabog Core Road |  | Roads/ Bridges - LGSF | 3000000 | [7 empty] | 1 | COMPLETED | SWA | 2017-12-27
OL-16-10-18-05-000-03 | L-OT | 2016 | REGION_X | CAMIGUIN | SAGAY |  | Concreting of Municipal of Barangay Mayana Road connecting Cemetery Road, Poblacion, Sagay |  | Roads/ Bridges - LGSF | 2000000 | [7 empty] | 1 | COMPLETED
OL-16-10-18-05-000-04 | L-OT | 2016 | REGION_X | CAMIGUIN | SAGAY |  | Concreting of Municipal Road - Baltazar St. |  | Roads/ Bridges - LGSF | 2500000 | [7 empty] | 1 | COMPLETED | SWA | 2017-09-04
OL-16-10-18-05-000-05 | L-OT | 2016 | REGION_X | CAMIGUIN | SAGAY |  | Concreting of Municipal Road - Bonifacio St. |  | Roads/ Bridges - LGSF | 1000000 | [7 empty] | 1 | COMPLETED | SWA | 2017-08-01
OL-16-10-18-05-000-06 | L-OT | 2016 | REGION_X | CAMIGUIN | SAGAY |  | Core Local Road Construction: Road Opening of Suazo St. from Corner of Rosario St. to T. Claudio with Gravelling and RipRapping |  | Roads/ Bridges - LGSF | 2750000 | [7 empty] | 1 | COMPLETED | SWA | 2017-09-04
SUB-TOTAL (LAR) CAMIGUIN: |  |  |  |  | 5 |  | 14 |  |  | 33950000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14
| L-OT | 2016 | REGION_X | CAMIGUIN | GUINSILIBAN | Municipal wide | Rescue Vehicle with Complete Rescue Equipment | Rescue equipments & 7 units Rescue Vehicle | Rescue Vehicle | 1550000 |  | - | 1 | [5 empty] | CANCELLED |  | 2019-05-29 | KA
LO-16-10-18-02-001-2 | L-OT | 2016 | REGION_X | CAMIGUIN | GUINSILIBAN | North & South Poblacion | River Control (Brgys. North & South Poblacion) | 130 linear meter structural concrete river control | Flood Control | 2000000 |  | - | [5 empty] | 1 | COMPLETED |  | 2020-06-26 | ENGR.ALPAS
LO-16-10-18-05-009-1 | L-OT | 2016 | REGION_X | CAMIGUIN | SAGAY | Municipal-wide | Rescue Equipment: Acquisition of Brgy. Disaster Rescue Vehicle | 1 rescue vehicle for every barangay acquired | Rescue Vehicle | 2250000 | 2250000 | 2250000 | [5 empty] | 1 | COMPLETED
LO-16-10-18-05-009-2 | L-OT | 2016 | REGION_X | CAMIGUIN | SAGAY | Municipal-wide | Rescue Equipment: Procurement of Disaster Equipments for 9 Brgys. | Disaster equipment procured | DRRM Equipment | 1500000 | 1500000 | 1500000 | [5 empty] | 1 | COMPLETED
SUB-TOTAL (OTHERS) CAMIGUIN: | [6 empty] | 4 |  |  | 7300000 | 3750000 | 3750000 | 1 | 0 | 0 | 0 | 0 | 3
TOTAL (OTHERS+LAR) (CAMIGUIN) |  |  |  |  | 5 |  | 18 |  |  | 41250000 | 3750000 | 3750000 | 1 | 0 | 0 | 0 | 0 | 17
LANAO DEL NORTE
OL-16-10-35-01-000-02 | L-OT | 2016 | REGION_X | LANAO DEL NORTE | BACOLOD |  | Concreting of Access Road | Roads/ Bridges - LGSF |  | 4000000 | [7 empty] | 1 | COMPLETED
OL-16-10-35-02-000-01 | L-OT | 2016 | REGION_X | LANAO DEL NORTE | BALO-I |  | Concreting Cormatan to Sigayan FMR | Roads/ Bridges - LGSF |  | 1000000 | [7 empty] | 1 | COMPLETED | as of 11-30-2018 (SWA) | 2019-02-01 | ND
OL-16-10-35-02-000-02 | L-OT | 2016 | REGION_X | LANAO DEL NORTE | BALO-I |  | Concreting of Doro Street to Lap-lap Street | Roads/ Bridges - LGSF |  | 500000 | [7 empty] | 1 | COMPLETED | as of 11-30-2018 (SWA) | 2019-02-01 | ND
OL-16-10-35-02-000-03 | L-OT | 2016 | REGION_X | LANAO DEL NORTE | BALO-I |  | Road Rehabilitation of Sarip Alawi to Landa FMR | Roads/ Bridges - LGSF |  | 500000 | [7 empty] | 1 | COMPLETED | as of September 5, 2018 (SWA) | 2019-02-01 | ND
OL-16-10-35-02-000-04 | L-OT | 2016 | REGION_X | LANAO DEL NORTE | BALO-I |  | Concreting of Baloi National High School to National Highway Road | Roads/ Bridges - LGSF |  | 500000 | [7 empty] | 1 | COMPLETED | as of 11-30-2018 (SWA) | 2019-02-01 | ND
OL-16-10-35-02-000-05 | L-OT | 2016 | REGION_X | LANAO DEL NORTE | BALO-I |  | Road Rehabilitation of Cormatan to Sarip Alawi | Roads/ Bridges - LGSF |  | 500000 | [7 empty] | 1 | COMPLETED | as of September 5, 2018 (SWA) | 2019-02-01 | ND
OL-16-10-35-02-000-06 | L-OT | 2016 | REGION_X | LANAO DEL NORTE | BALO-I |  | Concreting of Pilombayan to Gomampong Street | Roads/ Bridges - LGSF |  | 500000 | [7 empty] | 1 | COMPLETED | as of 11-30-2018 (SWA) | 2019-02-01 | ND
OL-16-10-35-03-000-01 | L-OT | 2016 | REGION_X | LANAO DEL NORTE | BAROY |  | Concreting of Barangay Cabasagan to Barangay Pendulonan Road | Roads/ Bridges - LGSF |  | 1500000 | [7 empty] | 1 | COMPLETED | SWA | 2017-08-23
OL-16-10-35-03-000-02 | L-OT | 2016 | REGION_X | LANAO DEL NORTE | BAROY |  | Concreting of Riverside Barangay Road | Roads/ Bridges - LGSF |  | 1500000 | [7 empty] | 1 | COMPLETED | SWA | 2017-09-26
OL-16-10-35-03-000-03 | L-OT | 2016 | REGION_X | LANAO DEL NORTE | BAROY |  | Concreting of of Upper Sagadan Barangay Road | Roads/ Bridges - LGSF |  | 1500000 | [7 empty] | 1 | COMPLETED
OL-16-10-35-03-000-04 | L-OT | 2016 | REGION_X | LANAO DEL NORTE | BAROY |  | Rehabilitation of Barangay Road (Princesa Pange) | Roads/ Bridges - LGSF |  | 1500000 | [7 empty] | 1 | COMPLETED | SWA | 11/16/2017
OL-16-10-35-08-000-01 | L-OT | 2016 | REGION_X | LANAO DEL NORTE | KOLAMBUGAN |  | Gravelling of Inuduran Farm to Market Road | Roads/ Bridges - LGSF |  | 3000000 | [7 empty] | 1 | Completed
OL-16-10-35-10-000-01 | L-OT | 2016 | REGION_X | LANAO DEL NORTE | LINAMON |  | Upgrading of Farm to Market Road (construction of 880 m FMR) | Roads/ Bridges - LGSF |  | 6100000 | [7 empty] | 1 | Completed
OL-16-10-35-11-000-01 | L-OT | 2016 | REGION_X | LANAO DEL NORTE | MAGSAYSAY |  | Concreting of 900 Linear Meters Farm to Market Road Barangay Somiorang | Roads/ Bridges - LGSF |  | 8200000 | [7 empty] | 1 | Completed | as of December 31, 2018 (SWA) | 2019-02-01
OL-16-10-35-13-000-01 | L-OT | 2016 | REGION_X | LANAO DEL NORTE | MATUNGAO |  | Concreting of Pasayanon to Lower Batal Access Road | Roads/ Bridges - LGSF |  | 10000000 | [7 empty] | 1 | COMPLETED | SWA | 2017-08-23
OL-16-10-35-13-000-02 | L-OT | 2016 | REGION_X | LANAO DEL NORTE | MATUNGAO |  | Concreting of Barangay Cadayonan Circumferential Access Road | Roads/ Bridges - LGSF |  | 5000000 | [7 empty] | 1 | COMPLETED | SWA | 2017-08-23
OL-16-10-35-14-000-01 | L-OT | 2016 | REGION_X | LANAO DEL NORTE | MUNAI |  | Local Road Concreting | Roads/ Bridges - LGSF |  | 10500000 | [7 empty] | 1 | COMPLETED | SWA
OL-16-10-35-15-000-01 | L-OT | 2016 | REGION_X | LANAO DEL NORTE | NUNUNGAN |  | Concreting of Local Access Road (Barangay Katubuan to Abaga) | Roads/ Bridges - LGSF |  | 3000000 | [7 empty] | 1 | COMPLETED | as of august 16, 2018 (SWA) | 2019-02-01 | ND
OL-16-10-35-15-000-02 | L-OT | 2016 | REGION_X | LANAO DEL NORTE | NUNUNGAN |  | Concreting of Local Access Road (Barangay Abaga to Paridi) | Roads/ Bridges - LGSF |  | 3000000 | [7 empty] | 1 | COMPLETED | as of august 16, 2018 (SWA) | 2019-02-01 | ND
OL-16-10-35-15-000-03 | L-OT | 2016 | REGION_X | LANAO DEL NORTE | NUNUNGAN |  | Concreting of Local Access Road (Barangay Poblacion to Putadon) | Roads/ Bridges - LGSF |  | 3000000 | [7 empty] | 1 | COMPLETED | as of august 16, 2018 (SWA) | 2019-02-01 | ND
OL-16-10-35-15-000-04 | L-OT | 2016 | REGION_X | LANAO DEL NORTE | NUNUNGAN |  | Concreting of Local Access Road (Barangay Paridi to Masibay) | Roads/ Bridges - LGSF |  | 3000000 | [7 empty] | 1 | COMPLETED | as of august 16, 2018 (SWA) | 2019-02-01 | ND
OL-16-10-35-15-000-05 | L-OT | 2016 | REGION_X | LANAO DEL NORTE | NUNUNGAN |  | Concreting of Local Access Road (Barangay Putadon to Katubuan) | Roads/ Bridges - LGSF |  | 3000000 | [7 empty] | 1 | COMPLETED | as of august 16, 2018 (SWA) | 2019-02-01 | ND
OL-16-10-35-16-000-01 | L-OT | 2016 | REGION_X | LANAO DEL NORTE | PANTAO-RAGAT |  | Concreting of Farm to Market Road of Barangay Dilimbayan Road | Roads/ Bridges - LGSF |  | 8000000 | [7 empty] | 1 | COMPLETED
OL-16-10-35-17-000-01 | L-OT | 2016 | REGION_X | LANAO DEL NORTE | POONA PAGAPO |  | 1.6 KM Road Concreting (Barangay Denaig) | Roads/ Bridges - LGSF |  | 14519616 | [7 empty] | 1 | COMPLETED | SWA | 12/22/2018
OL-16-10-35-18-000-02 | L-OT | 2016 | REGION_X | LANAO DEL NORTE | SALVADOR |  | Core Local Road Construction: Concrete Road | Roads/ Bridges - LGSF |  | 6000000 | [7 empty] | 1 | COMPLETED
OL-16-10-35-19-000-03 | L-OT | 2016 | REGION_X | LANAO DEL NORTE | SAPAD |  | Core Local Road Rehabilitation - Concrete Road | Roads/ Bridges - LGSF |  | 6000000 | [7 empty] | 1 | COMPLETED | SWA | 2017-08-15
OL-16-10-35-20-000-01 | L-OT | 2016 | REGION_X | LANAO DEL NORTE | TAGOLOAN |  | Concreting of Cabsaran to Darimbang Panalawan Local Road | Roads/ Bridges - LGSF |  | 10400000 | [7 empty] | 1 | COMPLETED |  | 2018-10-25 | ME
OL-16-10-35-21-000-01 | L-OT | A | REGION_X | LANAO DEL NORTE | TANGCAL |  | 1,200 I.m Concreting of Bubong Access Road | Roads/ Bridges - LGSF |  | 12000000 | [7 empty] | 1 | COMPLETED | Cause of delay: Bad weather condition | 2019-02-18 | nd/fcla
OL-16-10-35-21-000-02 | L-OT | 2016 | REGION_X | LANAO DEL NORTE | TANGCAL |  | 300 I.m Concreting of Poblacion Street Access Road | Roads/ Bridges - LGSF |  | 3000000 | [7 empty] | 1 | COMPLETED | as of 11-30-2018 (SWA) | 2019-02-01 | ND
SUB-TOTAL (LAR) LANAO DEL NORTE: |  |  |  |  | 16 |  | 29 |  |  | 131219616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29
LO-16-10-35-01-000-1 | L-OT | 2016 | REGION_X | LANAO DEL NORTE | BACOLOD | Municipal wide | Purchase of Rescue Equipment | upgrade rescue equipment in cases of emergency. | Rescue Vehicle | 4000000 | 4000000 | 4000000 | [5 empty] | 1 | COMPLETED |  | 2018-05-21 | ND
LO-16-10-35-02-023-1 | L-OT | 2016 | REGION_X | LANAO DEL NORTE | BALOI | Brgy. West Pob. | Construction of U-Type Darainage Canal (Brgy. West) | Provide Flood Control | Flood Control | 750000 |  | - | [5 empty] | 1 | COMPLETED | as od 12-31-2018 (SWA) | 2019-02-01 | ND
LO-16-10-35-07-000-1 | L-OT | 2016 | REGION_X | LANAO DEL NORTE | KAUSWAGAN | Municipal wide | Rescue Equipment | procured 4.6M small fiber glass boat, inflatable rubber boat, rescue vehicle/dump truck | Rescue Vehicle | 4600000 |  | - | [5 empty] | 1 | Completed |  | 2018-07-11 | PGLDN
LO-16-10-35-10-005-1 | L-OT | 2016 | REGION_X | LANAO DEL NORTE | LINAMON | Poblacion | Seawall Protection / Construction | seawall const. | Flood Control | 2500000 | 2500000 | 2500000 | [5 empty] | 1 | Completed
LO-16-10-35-12-000-1 | L-OT | 2016 | REGION_X | LANAO DEL NORTE | MAIGO | Brgy. Balagtasa - Segapod | Construction of Sea Wall / Flood Control | 1 unit | Flood Control | 8000000 | 8000000 | 8000000 | [5 empty] | 1 | COMPLETED
OL-16-10-35-18-000-01 | L-OT | 2016 | REGION_X | LANAO DEL NORTE | SALVADOR |  | Flood Control: Construction of Drainage Canal | Flood Control - LGSF |  | 3600000 | [7 empty] | 1 | COMPLETED
LO-16-10-35-19-019-1 | L-OT | 2016 | REGION_X | LANAO DEL NORTE | SAPAD | SDA church to P-11, Poblacion, Sapad | Construction of U - Type Drainage Canal | 750 Linear Meter | Flood Control | 1892000 | 1892000 | 1892000 | [5 empty] | 1 | COMPLETED | SWA | 2017-08-15
LO-16-10-35-19-016-2 | L-OT | 2016 | REGION_X | LANAO DEL NORTE | SAPAD | Pancilan, Sapad | Construction of U - Type Drainage Canal | 500 Linear Meter | Flood Control | 1000000 | 1000000 | 1000000 | [5 empty] | 1 | COMPLETED | SWA | 2017-08-15
LO-16-10-35-06-028-1 | L-OT | 2016 | REGION_X | LANAO DEL NORTE | SULTAN NAGA DIMAPORO (KAROMATAN) | Brgy. Poblacion, Sultan Naga Dimaporo | Flood Control (Construction of Drainange Canal) | Trapezoidal Concrete Drainage | Flood Control | 5000000 |  | - | [5 empty] | 1 | COMPLETED | SWA | 2017-08-15
OL-16-10-35-22-000-01 | L-OT | 2016 | REGION_X | LANAO DEL NORTE | TUBOD (Capital) |  | Construction of Footbridge | Roads/ Bridges - LGSF |  | 4520000 | [7 empty] | 1 | COMPLETED | SWA | 2018-07-11
SUB-TOTAL (OTHERS) LANAO DEL NORTE: |  |  |  |  | 3 |  | 10 |  |  | 35862000 | 17392000 | 17392000 | 0 | 0 | 0 | 0 | 0 | 10
TOTAL (OTHERS+LAR) (LANAO DEL NORTE) |  |  |  |  | 19 |  | 39 |  |  | 167081616 | 17392000 | 17392000 | 0 | 0 | 0 | 0 | 0 | 39
MISAMIS OCCIDENTAL
OL-16-10-42-01-000-01 | L-OT | 2016 | REGION_X | MISAMIS OCCIDENTAL | ALORAN |  | CONCRETING OF DALISAY ACCESS ROAD | Roads/ Bridges - LGSF |  | 600000 | [7 empty] | 1 | Completed
OL-16-10-42-01-000-02 | L-OT | 2016 | REGION_X | MISAMIS OCCIDENTAL | ALORAN |  | CONCRETING OF MANAMONG (ESPERANZA - SILANGIT ROAD) | Roads/ Bridges - LGSF |  | 1000000 | [7 empty] | 1 | Completed
OL-16-10-42-01-000-03 | L-OT | 2016 | REGION_X | MISAMIS OCCIDENTAL | ALORAN |  | CONCRETING OF IBABAO LOCAL ACCESS ROAD | Roads/ Bridges - LGSF |  | 3400000 | [7 empty] | 1 | Completed
OL-16-10-42-02-000-01 | L-OT | 2016 | REGION_X | MISAMIS OCCIDENTAL | BALIANGAO |  | PROPOSED CORE LOCAL ROAD REHABILITATION - BARANGAY DEL PILAR | Roads/ Bridges - LGSF |  | 1300000 | [7 empty] | 1 | Completed | (Without issuance of no objection letter by DILG) | 2017-09-06 | RV
OL-16-10-42-02-000-02 | L-OT | 2016 | REGION_X | MISAMIS OCCIDENTAL | BALIANGAO |  | PROPOSED CORE LOCAL ROAD REHABILITATION - BARANGAY LUMIPAC | Roads/ Bridges - LGSF |  | 1300000 | [7 empty] | 1 | Completed |  | 2017-09-06 | RV
OL-16-10-42-02-000-03 | L-OT | 2016 | REGION_X | MISAMIS OCCIDENTAL | BALIANGAO |  | PROPOSED CORE LOCAL ROAD REHABILITATION - BARANGAY SINIAN | Roads/ Bridges - LGSF |  | 1300000 | [7 empty] | 1 | Completed |  | 2017-09-06 | RV
OL-16-10-42-02-000-04 | L-OT | 2016 | REGION_X | MISAMIS OCCIDENTAL | BALIANGAO |  | PROPOSED CORE LOCAL ROAD REHABILITATION - BARANGAY LANDING | Roads/ Bridges - LGSF |  | 1300000 | [7 empty] | 1 | Completed |  | 2017-09-06 | RV
OL-16-10-42-02-000-05 | L-OT | 2016 | REGION_X | MISAMIS OCCIDENTAL | BALIANGAO |  | PROPOSED CORE LOCAL ROAD REHABILITATION - BARANGAY MAGSAYSAY | Roads/ Bridges - LGSF |  | 1300000 | [7 empty] | 1 | Completed |  | 2017-09-06 | RV
OL-16-10-42-02-000-06 | L-OT | 2016 | REGION_X | MISAMIS OCCIDENTAL | BALIANGAO |  | PROPOSED CORE LOCAL ROAD REHABILITATION - BARANGAY SULONG | Roads/ Bridges - LGSF |  | 1300000 | [7 empty] | 1 | Completed |  | 2017-09-06 | RV
OL-16-10-42-02-000-07 | L-OT | 2016 | REGION_X | MISAMIS OCCIDENTAL | BALIANGAO |  | PROPOSED CORE LOCAL ROAD REHABILITATION - BARANGAY PUNTA MIRAY | Roads/ Bridges - LGSF |  | 1300000 | [7 empty] | 1 | Completed |  | 2017-09-06 | RV
OL-16-10-42-02-000-08 | L-OT | 2016 | REGION_X | MISAMIS OCCIDENTAL | BALIANGAO |  | PROPOSED CORE LOCAL ROAD REHABILITATION - BARANGAY LUSOT | Roads/ Bridges - LGSF |  | 1300000 | [7 empty] | 1 | Completed |  | 2017-09-06 | RV
OL-16-10-42-04-000-01 | L-OT | 2016 | REGION_X | MISAMIS OCCIDENTAL | CALAMBA |  | CONCRETING OF PANGILINAN AND REBOSURA STREET | Roads/ Bridges - LGSF |  | 1100000 | [7 empty] | 1 | Completed |  | 2018-09-27 | KE/ Trans. Letter
OL-16-10-42-04-000-02 | L-OT | 2016 | REGION_X | MISAMIS OCCIDENTAL | CALAMBA |  | CONCRETING OF FAUSTINO CALES STREET | Roads/ Bridges - LGSF |  | 1200000 | [7 empty] | 1 | Completed |  | 2018-09-27 | KE/ Trans. Letter
OL-16-10-42-04-000-03 | L-OT | 2016 | REGION_X | MISAMIS OCCIDENTAL | CALAMBA |  | CONCRETING OF PORFERIO BRANZUELA STREET | Roads/ Bridges - LGSF |  | 1000000 | [7 empty] | 1 | Completed |  | 2018-09-27 | KE/ Trans. Letter
OL-16-10-42-04-000-04 | L-OT | 2016 | REGION_X | MISAMIS OCCIDENTAL | CALAMBA |  | CONCRETING OF SEMION CLAPANO STREET | Roads/ Bridges - LGSF |  | 1000000 | [7 empty] | 1 | Completed |  | 2018-09-27 | KE/ Trans. Letter
OL-16-10-42-04-000-05 | L-OT | 2016 | REGION_X | MISAMIS OCCIDENTAL | CALAMBA |  | CONCRETING OF SOLINOG CORE LOCAL ROAD | Roads/ Bridges - LGSF |  | 1000000 | [7 empty] | 1 | Completed |  | 2018-09-27 | KE/ Trans. Letter
OL-16-10-42-04-000-06 | L-OT | 2016 | REGION_X | MISAMIS OCCIDENTAL | CALAMBA |  | CONCRETING OF SILOY CORE LOCAL ROAD TO MAN MADE LAKE | Roads/ Bridges - LGSF |  | 800000 | [7 empty] | 1 | Completed |  | 2018-09-27 | KE/ Trans. Letter
OL-16-10-42-05-000-02 | L-OT | 2016 | REGION_X | MISAMIS OCCIDENTAL | CLARIN |  | CONSTRUCTION OF CORE LOCAL ROADS | Roads/ Bridges - LGSF |  | 4000000 | [7 empty] | 1 | Completed | as of 12/19/2019 from Certificate of Project Completion and SWA | 2019-06-26
OL-16-10-42-06-000-01 | L-OT | 2016 | REGION_X | MISAMIS OCCIDENTAL | CONCEPCION |  | Construction of Local Road (Brgy. Virayan) | Roads/ Bridges - LGSF |  | 15000000 | [6 empty] | 1 |  | 40.17% PHYSICAL ACCOMPLISHMENT | AS OF 06/08/2020 | 2020-06-26 | K.E
OL-16-10-42-17-000-01 | L-OT | 2016 | REGION_X | MISAMIS OCCIDENTAL | DON VICTORIANO | Lampasan - Lalud | Concreting of Lampasan-Lalud Road Project | Roads/ Bridges - LGSF |  | 10909000 | [7 empty] | 1 | Completed | as of 7/4/2019 (Certificate of Project Completion & SWA) | 2019-06-26
OL-16-10-42-07-000-01 | L-OT | 2016 | REGION_X | MISAMIS OCCIDENTAL | JIMENEZ |  | CONCRETING OF BONIFACIO ST., BARANGAY STA. CRUZ | Roads/ Bridges - LGSF |  | 500000 | [7 empty] | 1 | Completed
OL-16-10-42-07-000-02 | L-OT | 2016 | REGION_X | MISAMIS OCCIDENTAL | JIMENEZ |  | CONCRETING OF BARANGAY GATA - DICOLOC ROAD - ACCESS ROAD TO THE MUNICIPAL SLAUGHTERHOUSE | Roads/ Bridges - LGSF |  | 500000 | [7 empty] | 1 | Completed
OL-16-10-42-07-000-03 | L-OT | 2016 | REGION_X | MISAMIS OCCIDENTAL | JIMENEZ |  | CONCRETING OF CALDERON ST., BARANGAY NACIONAL | Roads/ Bridges - LGSF |  | 1000000 | [7 empty] | 1 | Completed
OL-16-10-42-07-000-04 | L-OT | 2016 | REGION_X | MISAMIS OCCIDENTAL | JIMENEZ |  | ROAD CONCRETING - DEL PILAR ST. | Roads/ Bridges - LGSF |  | 500000 | [7 empty] | 1 | Completed
OL-16-10-42-10-000-01 | L-OT | 2016 | REGION_X | MISAMIS OCCIDENTAL | CITY OF OZAMIS |  | CORE LOCAL ROAD PROGRAM | Roads/ Bridges - LGSF |  | 13000000 | [7 empty] | 1 | Completed | 12 Brgys.-Completed (SWA) | 2018-08-22
OL-16-10-42-11-000-01 | L-OT | 2016 | REGION_X | MISAMIS OCCIDENTAL | PANAON |  | ROAD CONCRETING | Roads/ Bridges - LGSF |  | 1200000 | [7 empty] | 1 | Completed
OL-16-10-42-13-000-01 | L-OT | 2016 | REGION_X | MISAMIS OCCIDENTAL | SAPANG DALAGA |  | CORE LOCAL ROAD CONSTRUCTION | Roads/ Bridges - LGSF |  | 14500000 | [7 empty] | 1 | Completed
OL-16-10-42-14-000-01 | L-OT | 2016 | REGION_X | MISAMIS OCCIDENTAL | SINACABAN |  | CONCRETING OF 1.5 KM LOCAL ROAD AT PUROK 2 TO PUROK 5 BARANGAY TIPAN |  |  | 15000000 | [7 empty] | 1 | Completed | SWA | 2017-08-16
OL-16-10-42-15-000-01 | L-OT | 2016 | REGION_X | MISAMIS OCCIDENTAL | TANGUB CITY |  | CORE LOCAL ROAD CONSTRUCTION | Roads/ Bridges - LGSF |  | 7200000 | [7 empty] | 1 | Completed | SWA | 2017-09-04 | CB
SUB-TOTAL (LAR) MIS.OCC: |  |  |  |  | 12 |  | 29 |  |  | 104809000 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 28
LO-16-10-42-02-011-1 | L-OT | 2016 | REGION_X | MISAMIS OCCIDENTAL | BALIANGAO | Municipal-wide | PROPOSED RESCUE EQUIPMENT | Purchase of 1 unit equipment | Rescue Vehicle | 1100000 | 1100000 | 1100000 | [5 empty] | 1 | Completed
PL-16-10-42-03-000-01 | L-OT | 2016 | REGION_X | MISAMIS OCCIDENTAL | BONIFACIO |  | BARANGAY WATER SYSTEM ASSOCIATION CAPACITY BUILDING | CAPDEV |  | 500000 | [7 empty] | 1 | Completed |  | 2019-02-08 | KE
OL-16-10-42-05-000-01 | L-OT | 2016 | REGION_X | MISAMIS OCCIDENTAL | CLARIN |  | CONSTRUCTION OF FOOT BRIDGE | Roads/ Bridges - LGSF |  | 1000000 | [7 empty] | 1 | Completed | as of 11/20/2019 Completion report and SWA | 2019-06-26
OL-16-10-42-17-000-02 | L-OT | 2016 | REGION_X | MISAMIS OCCIDENTAL | DON VICTORIANO |  | CONSTRUCTION OF FOOT BRIDGE - NAPANGAN CREEK | Roads/ Bridges - LGSF |  | 1000000 |  |  | 1 | [5 empty] | CANCELLED |  | 2019-12-16 | CEB
OL-16-10-42-17-000-03 | L-OT | 2016 | REGION_X | MISAMIS OCCIDENTAL | DON VICTORIANO |  | CONSTRUCTION OF FOOT BRIDGE - DIMOROK RIVER | Roads/ Bridges - LGSF |  | 1000000 |  |  | 1 | [5 empty] | CANCELLED |  | 2019-12-16 | CEB
LO-16-10-42-08-017-1 | L-OT | 2016 | REGION_X | MISAMIS OCCIDENTAL | LOPEZ JAENA | Mansabay Bajo | FLOOD CONTROL | Construction / Installation of U-Type Drainage Canal |  | 500000 | [7 empty] | 1 | Completed | SWA | 2018-07-10
SUB-TOTAL (OTHERS) MIS.OCC: |  |  |  |  | 2 |  | 6 |  |  | 5100000 | 1100000 | 1100000 | 2 | 0 | 0 | 0 | 0 | 4
TOTAL (OTHERS+LAR) (MISAMIS OCCIDENTAL) |  |  |  |  | 14 |  | 35 |  |  | 109909000 | 1100000 | 1100000 | 2 | 0 | 0 | 0 | 1 | 32
MISAMIS ORIENTAL
OL-16-10-43-02-000-01 | L-OT | 2016 | REGION_X | MISAMIS ORIENTAL | BALINGASAG |  | Concreting of Tugas-Tugason Linabu-Juan Road | Roads/ Bridges - LGSF |  | 13500000 | [7 empty] | 1 | COMPLETED |  | 2017-07-19
OL-16-10-43-02-000-02 | L-OT | 2016 | REGION_X | MISAMIS ORIENTAL | BALINGASAG |  | Concreting of San Isidro - Tangis Road | Roads/ Bridges - LGSF |  | 7500000 | [7 empty] | 1 | COMPLETED
OL-16-10-43-02-000-03 | L-OT | 2016 | REGION_X | MISAMIS ORIENTAL | BALINGASAG |  | Concreting of Cala-cala Cogon Road | Roads/ Bridges - LGSF |  | 1500000 | [7 empty] | 1 | COMPLETED
OL-16-10-43-03-000-01 | L-OT | 2016 | REGION_X | MISAMIS ORIENTAL | BALINGOAN |  | Core Local Road Construction/ Maintenance Rehabilitation | Roads/ Bridges - LGSF |  | 10000000 | [7 empty] | 1 | COMPLETED | as of 2/15/2019 (SWA) | 2019-03-20
OL-16-10-43-04-000-01 | L-OT | 2016 | REGION_X | MISAMIS ORIENTAL | BINUANGAN |  | CORE LOCAL ROAD CONSTRUCTION | Roads/ Bridges - LGSF |  | 9500000 | [7 empty] | 1 | COMPLETED
OL-16-10-43-06-000-01 | L-OT | 2016 | REGION_X | MISAMIS ORIENTAL | CLAVERIA |  | Concreting of Sitio Migbanday - Barangay Luma Road | Roads/ Bridges - LGSF |  | 2500000 | [7 empty] | 1 | COMPLETED |  | 2018-12-11 | EJD/ PO
OL-16-10-43-06-000-02 | L-OT | 2016 | REGION_X | MISAMIS ORIENTAL | CLAVERIA |  | Concreting of Junction Provincial Road Sitio Limbusan | Roads/ Bridges - LGSF |  | 2000000 | [7 empty] | 1 | COMPLETED |  | 2019-07-15 | mis.or. LFP drive
OL-16-10-43-06-000-03 | L-OT | 2016 | REGION_X | MISAMIS ORIENTAL | CLAVERIA |  | Concreting of Purok 1, 2 Barangay Road | Roads/ Bridges - LGSF |  | 2000000 | [7 empty] | 1 | COMPLETED | SWA | 2018-12-11 | EJD/ PO
OL-16-10-43-07-000-01 | L-OT | 2016 | REGION_X | MISAMIS ORIENTAL | CITY OF EL SALVADOR |  | Concreting of Kalabalabay to San Francisco de Asis Road | Roads/ Bridges - LGSF |  | 15000000 | [7 empty] | 1 | COMPLETED |  | 2018-12-11 | EJD/ PO
OL-16-10-43-09-000-01 | L-OT | 2016 | REGION_X | MISAMIS ORIENTAL | GITAGUM |  | Concreting of Barangay Road | Roads/ Bridges - LGSF |  | 2339125 | [7 empty] | 1 | COMPLETED
OL-16-10-43-09-000-02 | L-OT | 2016 | REGION_X | MISAMIS ORIENTAL | GITAGUM |  | Construction of Barangay Road BarangayPob P6 | Roads/ Bridges - LGSF |  | 3043000 | [7 empty] | 1 | COMPLETED
OL-16-10-43-09-000-03 | L-OT | 2016 | REGION_X | MISAMIS ORIENTAL | GITAGUM |  | Concreting of Barangay Road Barangay Quezon | Roads/ Bridges - LGSF |  | 500000 | [7 empty] | 1 | COMPLETED
OL-16-10-43-11-000-01 | L-OT | 2016 | REGION_X | MISAMIS ORIENTAL | JASAAN |  | ROAD CONCRETING - BARANGAY I.S. CRUZ | Roads/ Bridges - LGSF |  | 3500000 | [7 empty] | 1 | COMPLETED
OL-16-10-43-11-000-02 | L-OT | 2016 | REGION_X | MISAMIS ORIENTAL | JASAAN |  | ROAD CONCRETING - BARANGAY BOBONTUGAN | Roads/ Bridges - LGSF |  | 1000000 | [7 empty] | 1 | COMPLETED
OL-16-10-43-13-000-01 | L-OT | 2016 | REGION_X | MISAMIS ORIENTAL | LAGONGLONG |  | Concreting of Tabok-Sapong FMR | Roads/ Bridges - LGSF |  | 5000000 | [7 empty] | 1 | COMPLETED |  | 2018-05-21 | EJD
OL-16-10-43-13-000-02 | L-OT | 2016 | REGION_X | MISAMIS ORIENTAL | LAGONGLONG |  | Concreting of Manaol Circumferential Road | Roads/ Bridges - LGSF |  | 5000000 | [7 empty] | 1 | COMPLETED |  | 2018-05-21 | EJD
OL-16-10-43-13-000-03 | L-OT | 2016 | REGION_X | MISAMIS ORIENTAL | LAGONGLONG |  | Concreting of Highway-Kabulawan FMR | Roads/ Bridges - LGSF |  | 3000000 | [7 empty] | 1 | COMPLETED |  | 2018-05-21 | EJD
OL-16-10-43-13-000-04 | L-OT | 2016 | REGION_X | MISAMIS ORIENTAL | LAGONGLONG |  | Concreting of Umagos-RoaRoa FMR | Roads/ Bridges - LGSF |  | 2000000 | [7 empty] | 1 | COMPLETED |  | 2018-06-20 | MOT
OL-16-10-43-14-000-01 | L-OT | 2016 | REGION_X | MISAMIS ORIENTAL | LAGUINDINGAN |  | IMPROVEMENT/ REHABILITATION/ CONCRETING OF JUNCTION AROMAHON PROVINCIAL ROAD BOUND TO TIANO PROPERTY, PUROK 4, AROMAHON, BARANGAY ROAD | Roads/ Bridges - LGSF |  | 2500000 | [7 empty] | 1 | COMPLETED | SWA | 10/25/2018
OL-16-10-43-14-000-02 | L-OT | 2016 | REGION_X | MISAMIS ORIENTAL | LAGUINDINGAN |  | IMPROVEMENT/ REHABILITATION/ CONCRETING OF PORTION JUNCTION AROMAHON ACCESS ROAD LEADING TO GK DIAMOND RELOCATION SITE, KIBAGHOT, LAGUINDINGAN MIS. OR. | Roads/ Bridges - LGSF |  | 2500000 | [7 empty] | 1 | COMPLETED | SWA | 10/25/2018
OL-16-10-43-14-000-03 | L-OT | 2016 | REGION_X | MISAMIS ORIENTAL | LAGUINDINGAN |  | IMPROVEMENT / REHABILITATION/ CONCRETING OF PUROK 4, SAMBULAWAN DIVERSION ROAD ALONG BLESSED VIRGIN FATIMA LOCATED AT SAMBULAWAN, LAGUINDINGAN. | Roads/ Bridges - LGSF |  | 2500000 | [7 empty] | 1 | COMPLETED | SWA | 2018-04-19
OL-16-10-43-14-000-04 | L-OT | 2016 | REGION_X | MISAMIS ORIENTAL | LAGUINDINGAN |  | IMPROVEMENT / REHABILITATION/ CONCRETING OF PUROK 5, LAPAD BARANGAY ROAD | Roads/ Bridges - LGSF |  | 2500000 | [7 empty] | 1 | COMPLETED | SWA | 10/25/2018
OL-16-10-43-14-000-05 | L-OT | 2016 | REGION_X | MISAMIS ORIENTAL | LAGUINDINGAN |  | IMPROVEMENT/ REHABILITATION/ CONCRETING OF MAUSWAGON ELEMENTARY SCHOOL BARANGAY ROAD LEADING TO PUROK 4, MAUSWAGON BARANGAY ROAD | Roads/ Bridges - LGSF |  | 2500000 | [7 empty] | 1 | COMPLETED | SWA | 2018-05-31
OL-16-10-43-14-000-06 | L-OT | 2016 | REGION_X | MISAMIS ORIENTAL | LAGUINDINGAN |  | IMPROVEMENT/ REHABILITATION/ CONCRETING OF PUROK 5 BARANGAY ROAD LOCATED AT POBLACION, LAGUINDINGAN MIS. OR. | Roads/ Bridges - LGSF |  | 2500000 | [7 empty] | 1 | COMPLETED | SWA | 2018-05-31
OL-16-10-43-16-000-02 | L-OT | 2016 | REGION_X | MISAMIS ORIENTAL | LUGAIT |  | Concreting of Market to Bliss road | Roads/ Bridges - LGSF |  | 2000000 | [7 empty] | 1 | COMPLETED | SWA | 2018-07-10
OL-16-10-43-16-000-03 | L-OT | 2016 | REGION_X | MISAMIS ORIENTAL | LUGAIT |  | Concreting of Tangison Road | Roads/ Bridges - LGSF |  | 3000000 | [7 empty] | 1 | COMPLETED | SWA | 2018-09-03
OL-16-10-43-16-000-04 | L-OT | 2016 | REGION_X | MISAMIS ORIENTAL | LUGAIT |  | Concreting of Kaluknayan Road | Roads/ Bridges - LGSF |  | 3000000 | [7 empty] | 1 | COMPLETED | SWA | 2017-08-23
OL-16-10-43-16-000-05 | L-OT | 2016 | REGION_X | MISAMIS ORIENTAL | LUGAIT |  | Concreting of Kuyanapan Road | Roads/ Bridges - LGSF |  | 2000000 | [7 empty] | 1 | COMPLETED | SWA | 2018-09-03
OL-16-10-43-18-000-02 | L-OT | 2016 | REGION_X | MISAMIS ORIENTAL | MANTICAO |  | Road Concreting | Roads/ Bridges - LGSF |  | 9000000 | [7 empty] | 1 | COMPLETED | SWA | 12/29/2017
OL-16-10-43-19-000-01 | L-OT | 2016 | REGION_X | MISAMIS ORIENTAL | MEDINA | Pahindong | Proposed Concrete Pavement of Access road | Roads/ Bridges - LGSF |  | 1000000 | [7 empty] | 1 | COMPLETED |  | 10/25/2018 | ME
OL-16-10-43-19-000-02 | L-OT | 2016 | REGION_X | MISAMIS ORIENTAL | MEDINA | Tup-on | Proposed Concrete Pavement of Access road | Roads/ Bridges - LGSF |  | 1000000 | [7 empty] | 1 | COMPLETED | SWA | 2018-09-10
OL-16-10-43-19-000-03 | L-OT | 2016 | REGION_X | MISAMIS ORIENTAL | MEDINA |  | Proposed Concrete Pavement of Access road | Roads/ Bridges - LGSF |  | 1000000 | [7 empty] | 1 | COMPLETED |  | 2018-06-25 | NP
OL-16-10-43-19-000-04 | L-OT | 2016 | REGION_X | MISAMIS ORIENTAL | MEDINA |  | Proposed Concrete Pavement of Access road | Roads/ Bridges - LGSF |  | 1000000 | [7 empty] | 1 | COMPLETED |  | 2018-06-25 | NP
OL-16-10-43-19-000-05 | L-OT | 2016 | REGION_X | MISAMIS ORIENTAL | MEDINA |  | Proposed Concrete Pavement of Access road | Roads/ Bridges - LGSF |  | 1000000 | [7 empty] | 1 | COMPLETED |  | 2018-06-25 | NP
OL-16-10-43-19-000-06 | L-OT | 2016 | REGION_X | MISAMIS ORIENTAL | MEDINA |  | Proposed Concrete Pavement of Access road | Roads/ Bridges - LGSF |  | 1000000 | [7 empty] | 1 | COMPLETED |  | 2018-06-25 | NP
OL-16-10-43-19-000-07 | L-OT | 2016 | REGION_X | MISAMIS ORIENTAL | MEDINA | Tambagan | Proposed Concrete Pavement of Access road | Roads/ Bridges - LGSF |  | 500000 | [7 empty] | 1 | COMPLETED | SWA | 2018-09-10
OL-16-10-43-19-000-08 | L-OT | 2016 | REGION_X | MISAMIS ORIENTAL | MEDINA |  | Proposed Concrete Pavement of Access road | Roads/ Bridges - LGSF |  | 500000 | [7 empty] | 1 | COMPLETED |  | 2018-06-25 | NP
OL-16-10-43-19-000-09 | L-OT | 2016 | REGION_X | MISAMIS ORIENTAL | MEDINA |  | Proposed Concrete Pavement of Access road | Roads/ Bridges - LGSF |  | 500000 | [7 empty] | 1 | COMPLETED |  | 2018-06-25 | NP
OL-16-10-43-19-000-10 | L-OT | 2016 | REGION_X | MISAMIS ORIENTAL | MEDINA |  | Proposed Concrete Pavement of Access road | Roads/ Bridges - LGSF |  | 500000 | [7 empty] | 1 | COMPLETED |  | 2018-06-25 | NP
OL-16-10-43-19-000-11 | L-OT | 2016 | REGION_X | MISAMIS ORIENTAL | MEDINA |  | Proposed Concrete Pavement of Access road | Roads/ Bridges - LGSF |  | 500000 | [7 empty] | 1 | COMPLETED |  | 2018-06-25 | NP
OL-16-10-43-19-000-12 | L-OT | 2016 | REGION_X | MISAMIS ORIENTAL | MEDINA |  | Proposed Concrete Pavement of Access road | Roads/ Bridges - LGSF |  | 500000 | [7 empty] | 1 | COMPLETED |  | 2018-06-25 | NP
OL-16-10-43-19-000-14 | L-OT | 2016 | REGION_X | MISAMIS ORIENTAL | OPOL |  | Core Local Road Construction | Roads/ Bridges - LGSF |  | 10000000 | [7 empty] | 1 | COMPLETED
OL-16-10-43-22-000-01 | L-OT | 2016 | REGION_X | MISAMIS ORIENTAL | SALAY | Poblacion | Concreting of Access Road | Roads/ Bridges - LGSF |  | 15000000 | [7 empty] | 1 | COMPLETED |  | 2019-07-15 | mis.or. LFP drive
OL-16-10-43-23-000-01 | L-OT | 2016 | REGION_X | MISAMIS ORIENTAL | SUGBONGCOGON |  | Concreting of Purok 1 Kiraging, Sugbongcogon Access Road | Roads/ Bridges - LGSF |  | 2000000 | [7 empty] | 1 | COMPLETED
OL-16-10-43-23-000-02 | L-OT | 2016 | REGION_X | MISAMIS ORIENTAL | SUGBONGCOGON |  | Concreting of Purok 6 Sitio Caamulan Pob Sugbongcogon access Road | Roads/ Bridges - LGSF |  | 5000000 | [7 empty] | 1 | COMPLETED
OL-16-10-43-23-000-03 | L-OT | 2016 | REGION_X | MISAMIS ORIENTAL | SUGBONGCOGON |  | Concreting of Sitio Tiningalan, Pob Sugbongcogon Access Road | Roads/ Bridges - LGSF |  | 2000000 | [7 empty] | 1 | COMPLETED
OL-16-10-43-23-000-04 | L-OT | 2016 | REGION_X | MISAMIS ORIENTAL | SUGBONGCOGON |  | Concreting of Purok 2, Mimbuahan, Sugbongcogon Access Road | Roads/ Bridges - LGSF |  | 2000000 | [7 empty] | 1 | COMPLETED
OL-16-10-43-23-000-05 | L-OT | 2016 | REGION_X | MISAMIS ORIENTAL | SUGBONGCOGON |  | Concreting of P5 Magga Sugbongcogon Access Road | Roads/ Bridges - LGSF |  | 3000000 | [7 empty] | 1 | COMPLETED
OL-16-10-43-25-000-01 | L-OT | 2016 | REGION_X | MISAMIS ORIENTAL | TALISAYAN |  | Core Local Road Construction | Roads/ Bridges - LGSF |  | 3000000 | [7 empty] | 1 | COMPLETED |  | 2019-10-29 | NPJR
OL-16-10-43-25-000-02 | L-OT | 2016 | REGION_X | MISAMIS ORIENTAL | TALISAYAN |  | Core Local Road Construction | Roads/ Bridges - LGSF |  | 2000000 | [7 empty] | 1 | COMPLETED |  | 2019-10-29 | NPJR
OL-16-10-43-26-000-01 | L-OT | 2016 | REGION_X | MISAMIS ORIENTAL | VILLANUEVA |  | Nangka-Tagbalogo-Dayawan Road | Roads/ Bridges - LGSF |  | 15000000 | [7 empty] | 1 | COMPLETED
SUB-TOTAL (LAR) MIS.OR: |  |  |  |  | 17 |  | 51 |  |  | 190882125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51
LO-16-10-43-01-010-1 | L-OT | 2016 | REGION_X | MISAMIS ORIENTAL | ALUBIJID | Poblacion | Provision of Flood Control | Construction of 175Lm. Riverbank Protection Structure | Flood Control | 10000000 | 10000000 | 10000000 | [5 empty] | 1 | COMPLETED
LO-16-10-43-02-000-1 | L-OT | 2016 | REGION_X | MISAMIS ORIENTAL | BALINGASAG | Poblacion | Acquisition of Rescue vehicle | 1 unit rescue vehicle (RIO) acquired | Rescue Vehicle | 1500000 | [7 empty] | 1 | COMPLETED
LO-16-10-43-05-000-1 | L-OT | 2016 | REGION_X | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (Capital) | Zone 8, Brgy. Cugman | CONSTRUCTION OF SEA WALL GROUTED RIP-RAP FOR ZONE 8, CUGMAN, CDOC | 2,000 m. grouted rip-rap sea-wall | Flood Control | 2500000 |  | - | [5 empty] | 1 | COMPLETED |  | 2018-08-22 | EJD
LO-16-10-43-05-000-2 | L-OT | 2016 | REGION_X | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (Capital) | City-wide | CAPACITY DEVELOPMENT FOR LPRAT - CSO | CSOs in the City. Establishment of operational and administative systems and facilities for LPRAT-CSOs. Strengthening of CSO constituency up to Brgy level to ensure CSO participation at all levels. | CAPDEV | 3500000 |  | - | [5 empty] | 1 | COMPLETED |  | 10/25/2018 | ME
LO-16-10-43-08-000-1 | L-OT | 2016 | REGION_X | MISAMIS ORIENTAL | GINGOOG CITY | selected brgys | DRAINAGE CANAL | 68 families living in low lying brgys/urban poor | Flood Control | 3405400 |  | - | [5 empty] | 1 | COMPLETED | as of 12/15/2018 | 2019-03-20
LO-16-10-43-08-000-2 | L-OT | 2016 | REGION_X | MISAMIS ORIENTAL | GINGOOG CITY | selected brgys | FLOOD CONTROL REHAB OF EXISTING | 48 families living in low lying brgys/urban poor | Flood Control | 2905400 |  | - | [5 empty] | 1 | COMPLETED | as of 11/15/2018 (SWA) | 2019-03-20
LO-16-10-43-16-007-1 | L-OT | 2016 | REGION_X | MISAMIS ORIENTAL | LUGAIT | Poblacion | Construction of flood control | Construction of Base and Grouted Rip-Rap Flood Control L= 84 Lm. | Flood Control | 4000000 |  | - | [5 empty] | 1 | COMPLETED | SWA | 2018-09-03
LO-16-10-43-18-000-1 | L-OT | 2016 | REGION_X | MISAMIS ORIENTAL | MANTICAO | Municipal wide | Rescue Vehicle | Rescue vehicle acquired | Rescue Vehicle | 2000000 | 2000000 | 2000000 | [5 empty] | 1 | COMPLETED |  | 2017-07-19
OL-16-10-43-19-000-13 | L-OT | 2016 | REGION_X | MISAMIS ORIENTAL | MEDINA |  | Proposed Construction/ Rehab of Drainage system | Roads/ Bridges - LGSF |  | 2000000 | [7 empty] | 1 | COMPLETED | SWA | 2018-08-15
LO-16-10-43-24-010-1 | L-OT | 2016 | REGION_X | MISAMIS ORIENTAL | TAGOLOAN | Municipal wide | Hauler Vehicle for 10 Barangays | 10 units | Rescue Vehicle | 2000000 | 2000000 | 2000000 | 1 | [5 empty] | CANCELLED | Reverted and Remitted the Unutilized fund to the Bureau of the Treasury | 2019-12-03
SUB-TOTAL (OTHERS) MIS.OR: |  |  |  |  | 4 |  | 10 |  |  | 33810800 | 14000000 | 14000000 | 1 | 0 | 0 | 0 | 0 | 9
TOTAL (OTHERS+LAR) (MISAMIS ORIENTAL |  |  |  |  | 21 |  | 61 |  |  | 224692925 | 14000000 | 14000000 | 1 | 0 | 0 | 0 | 0 | 60
GRAND_TOTAL | [6 empty] | 198 |  |  | 647590041 | 52142000 | 52142000 | 10 | 0 | 0 | 0 | 1 | 187

## 2016 LGSF-WATER COMPLETED
REGION X
2016 LGSF-WATER
as of June 26, 2020
PROVINCE |  | CITY/ MUNICIPALITY |  | No. of Sub-project/s | BARANGAY | Total Agency Budget | NCA Release Status | Batch | Amount Obligated | Amount Un-obligated | Disbursement | CANCELLED | APPROVED DED/POW or DED PREP. | PROCUREMENT | ON-GOING | COMPLETED | STATUS | REMARKS | Date updated
BUKIDNON
1 | BUKIDNON | 1 | DAMULOG | 2 | Sampagar | 1000000 | NCA Released | Batch 1 | 1000000 | 0 | 1000000 | 1 |  |  |  |  | CANCELLED | Fund returned to BTR | 2019-05-28 | JKB
| BUKIDNON |  | DAMULOG |  | Poblacion | 700000 | NCA Released | Batch 1 | 700000 | 0 | 700000 |  |  |  |  | 1 | Completed | SWA | 2017-12-19
| BUKIDNON | 2 | KADINGILAN | 2 | Poblacion | 600000 | x |  |  | 600000 | 0 |  |  |  |  | 1 | Completed | as of 4/21/2019 (SWA) | 2019-05-10
| BUKIDNON | 3 | KALILANGAN |  | Canitoan & Mahayahay | 500000 | x |  |  | 500000 | 0 |  |  |  |  | 1 | Completed |  | 2018-06-19 | BT
| BUKIDNON | 4 | KIBAWE | 1 | Labuagon & New Kidapawan | 1905000 | x |  |  | 1905000 | 0 |  |  |  |  | 1 | Completed | as of 5/22/2019 (SWA) | 2019-05-24
| BUKIDNON | 5 | MANOLO FORTICH | 2 | Lunocan | 1000000 | NCA Released | Batch 1 | 1000000 | 0 | 1000000 |  |  |  |  | 1 | Completed |  | 2018-03-21 | FCLA
| BUKIDNON |  | MANOLO FORTICH |  | Maluko | 1000000 | NCA Released | Batch 1 | 1000000 | 0 | 1000000 |  |  |  |  | 1 | Completed |  | 2018-03-21 | FCLA
| BUKIDNON | 6 | PANGANTUCAN | 7 | Malipayon | 1000000 | x |  |  | 1000000 | 0 |  |  |  |  | 1 | Completed | as of 4/12/2019 (SWA) | 2019-06-21
| BUKIDNON |  | PANGANTUCAN |  | Gandingan | 1000000 | x |  |  | 1000000 | 0 |  |  |  |  | 1 | Completed |  | 12/21/2018 | JB
| BUKIDNON |  | PANGANTUCAN |  | Kipaducan | 1000000 | x |  |  | 1000000 | 0 |  |  |  |  | 1 | Completed |  | 12/21/2018 | JB
| BUKIDNON |  | PANGANTUCAN |  | Langcataon | 1500000 | x |  |  | 1500000 | 0 |  |  |  |  | 1 | Completed |  | 12/21/2018 | JB
| BUKIDNON |  | PANGANTUCAN |  | Madaya | 1000000 | x |  |  | 1000000 | 0 |  |  |  |  | 1 | Completed | as of 4/12/2019 (SWA) | 2019-06-21
| BUKIDNON |  | PANGANTUCAN |  | Barandias /Balangigay | 1000000 | x |  |  | 1000000 | 0 |  |  |  |  | 1 | Completed | SWA | 2018-06-21
| BUKIDNON |  | PANGANTUCAN |  | New Eden | 500000 | x |  |  | 500000 | 0 |  |  |  |  | 1 | Completed | SWA | 2018-07-27
| BUKIDNON | 7 | SAN FERNANDO | 2 | Sitio Salumayag, Dapiloan, Lugawon and Balao | 1400000 | NCA Released | Batch 1 | 1400000 | 0 | 1400000 |  |  |  |  | 1 | Completed |  | 2019-05-28 | JKB
| BUKIDNON |  | SAN FERNANDO |  | Simsimon, Kalagangan | 850000 | NCA Released | Batch 1 | 850000 | 0 | 850000 |  |  |  |  | 1 | Completed |  | 2019-05-28 | JKB
|  |  |  | 16 |  | 15955000 |  |  | 5950000 | 10005000 | 5950000 | 1 | 0 | 0 | 0 | 15
CAMIGUIN
2 | CAMIGUIN | 8 | CATARMAN | 1 | Quila-a Alga | 500000 | NCA Released | Batch 1 | 500000 | 0 | 500000 |  |  |  |  | 1 | Completed |  | 2017-10-04 | Flor
| CAMIGUIN | 9 | GUINSILIBAN | 1 | Butay | 2000000 | x |  |  | 2000000 | 0 |  |  |  |  | 1 | Completed | AS OF 02/7/2020 | 2020-03-17
| CAMIGUIN | 10 | MAHINOG | 1 |  | 1000000 | NCA Released | Batch 1 | 1000000 | 0 | 1000000 |  |  |  |  | 1 | Completed | SWA | 2018-08-15
| CAMIGUIN | 11 | MAMBAJAO (Capital) | 6 | Naasag | 1000000 | NCA Released | Batch 1 | 1000000 | 0 | 1000000 |  |  |  |  | 1 | Completed | SWA | 2017-12-27 | Flor
| CAMIGUIN |  | MAMBAJAO (Capital) |  | Bug-ong | 1000000 | NCA Released | Batch 1 | 1000000 | 0 | 1000000 |  |  |  |  | 1 | Completed | SWA | 2017-12-27 | Flor
| CAMIGUIN |  | MAMBAJAO (Capital) |  | Kuguita | 1000000 | NCA Released | Batch 1 | 1000000 | 0 | 1000000 |  |  |  |  | 1 | Completed | SWA | 2017-12-27 | Flor
| CAMIGUIN |  | MAMBAJAO (Capital) |  | Tupsan | 1000000 | NCA Released | Batch 1 | 1000000 |  | 1000000 |  |  |  |  | 1 | Completed | SWA | 2018-09-11
| CAMIGUIN |  | MAMBAJAO (Capital) |  | Magting | 1500000 | NCA Released | Batch 1 | 1500000 | 0 | 1500000 |  |  |  |  | 1 | Completed |  | 2018-06-20 | CT
| CAMIGUIN |  | MAMBAJAO (Capital) |  | Balbagon | 1500000 | NCA Released | Batch 1 | 1500000 | 0 | 1500000 |  |  |  |  | 1 | Completed | SWA | 2017-12-27
|  |  |  | 9 |  | 10500000 |  |  | 8500000 | 2000000 | 8500000 |  | 0 | 0 | 0 | 9
LANAO DEL NORTE
3 | LANAO DEL NORTE | 12 | BACOLOD | 1 | Alegria, Bacolod Lanao del Norte | 1400000 | NCA Released | Batch 1 | 1400000 | 0 | 1400000 |  |  |  |  | 1 | Completed
| LANAO DEL NORTE | 13 | BALOI | 2 | Bulao | 500000 | x |  |  | 500000 | 0 |  |  |  |  | 1 | Completed | Completed as of January 31, 2019 | 2019-10-14 | AL
| LANAO DEL NORTE |  | BALOI |  | Bangko | 500000 | x |  |  | 500000 | 0 |  |  |  |  | 1 | Completed | Completed as of January 31, 2019 | 2019-10-14 | AL
| LANAO DEL NORTE | 14 | LINAMON | 1 | Purukan & Bosque | 1230000 | NCA Released | Batch 1 | 1230000 | 0 | 1230000 |  |  |  |  | 1 | Completed |  | 2017-11-21 | ND
| LANAO DEL NORTE | 15 | PANTAO RAGAT | 1 |  | 2000000 | x |  |  | 2000000 | 0 |  |  |  |  | 1 | Completed | SWA | 2018-07-26
| LANAO DEL NORTE | 16 | TUBOD (Capital) | 5 | Barakanas | 595000 | NCA Released | Batch 1 | 595000 | 0 | 595000 |  |  |  |  | 1 | Completed
| LANAO DEL NORTE |  | TUBOD (Capital) |  | Baris (Lumangculob) | 595000 | NCA Released | Batch 1 | 595000 | 0 | 595000 |  |  |  |  | 1 | Completed | SWA | 01/14/2019
| LANAO DEL NORTE |  | TUBOD |  | Kakai Renabor | 680000 | NCA Released | Batch 1 | 680000 | 0 | 680000 |  |  |  |  | 1 | Completed
| LANAO DEL NORTE |  | TUBOD |  | Tangueguiron | 1700000 | NCA Released | Batch 1 | 1700000 | 0 | 1700000 |  |  |  |  | 1 | Completed | SWA | 2018-03-13
| LANAO DEL NORTE |  | TUBOD |  | Taden | 1275000 | NCA Released | Batch 1 | 1275000 | 0 | 1275000 |  |  |  |  | 1 | Completed | SWA | 1/29/2018
|  |  |  | 10 |  | 10475000 |  |  | 7475000 | 3000000 | 7475000 |  | 0 | 0 | 0 | 10
MISAMIS OCCIDENTAL
| MISAMIS OCCIDENTAL | 17 | BONIFACIO | 1 | Lower Usogan | 1000000 | x |  |  | 1000000 | 0 |  |  |  |  | 1 | Completed | SWA | 12/20/2018
| MISAMIS OCCIDENTAL | 18 | PANAON | 1 | Map-an | 1400000 | x |  |  | 1400000 | 0 |  |  |  |  | 1 | Completed | 3/25/2019 SWA | 2019-08-01
|  |  |  | 2 |  | 2400000 |  |  | 0 | 2400000 | 0 |  | 0 | 0 | 0 | 2
MISAMIS ORIENTAL
5 | MISAMIS ORIENTAL | 19 | CAGAYAN DE ORO CITY (Capital) | 6 | Brgy. Taglimao | 800000 | x |  |  | 800000 | 0 |  |  |  |  | 1 | Completed |  | 2017-10-10 | MOT
| MISAMIS ORIENTAL |  | CAGAYAN DE ORO CITY (Capital) |  | Sitio Palan, Brgy. Lumbia | 2000000 | x |  |  | 2000000 | 0 |  |  |  |  | 1 | Completed | turn over COWD | 2019-12-06 | NPJ/EJD
| MISAMIS ORIENTAL |  | CAGAYAN DE ORO CITY (Capital) |  | Brgy. Tumpagon | 800000 | x |  |  | 800000 | 0 |  |  |  |  | 1 | Completed | Proposed for Level III (SWA) | 2017-08-01
| MISAMIS ORIENTAL |  | CAGAYAN DE ORO CITY (Capital) |  | Sitio Tipolohon, Brgy. Camaman-an | 800000 | x |  |  | 800000 | 0 |  |  |  |  | 1 | Completed | turn over COWD | 2019-07-15 | mis.or. LFP Drive
| MISAMIS ORIENTAL |  | CAGAYAN DE ORO CITY (Capital) |  | Sitio Bulahan, Dansolihon | 500000 | x |  |  | 500000 | 0 |  |  |  |  | 1 | Completed |  | 2018-06-25 | EJD
| MISAMIS ORIENTAL |  | CAGAYAN DE ORO CITY (Capital) |  | Cugman | 500000 | x |  |  | 500000 | 0 |  |  |  |  | 1 | Completed | turn over COWD | 2019-07-15 | mis.or. LFP Drive
| MISAMIS ORIENTAL | 20 | GITAGUM | 2 | Poblacion | 550000 | For Release | Batch 2 | 550000 | 0 | 550000 |  |  |  |  | 1 | Completed
| MISAMIS ORIENTAL |  | GITAGUM |  |  | 800000 | For Release | Batch 2 | 800000 | 0 | 800000 |  |  |  |  | 1 | Completed
|  |  |  | 8 |  | 6750000 |  |  | 1350000 | 5400000 | 1350000 |  | 0 | 0 | 0 | 8
5 |  | 20 LGU's |  | 45 | TOTAL | 46080000 |  |  | 23275000 | 22805000 | 23275000 | 1 | 0 | 0 | 0 | 44

## 2017 ADM-Others
REGION X - ADM
2017 ADM-OTHERS
as of June 26, 2020
FY | REGION | PROVINCE | CITY / MUNICIPALITY | DISTRICT | BARANGAY | NAME OF PROJECT | ORIGINAL ALLOCATION | CANCELLED | APPROVED DED/POW or DED PREP. | PROCUREMENT | ON-GOING | COMPLETED | STATUS | REMARKS | Date Updated
2017 | REGION X | BUKIDNON | CABANGLASAN | 2ND | PUROK 6, POBLACION | Core Local Access Road | 2000000 |  |  |  |  | 1 | Completed |  | 2019-07-19 | BUK. LFP DRIVE
2017 | REGION X | BUKIDNON | CABANGLASAN | 2ND | PUROK 8 TO PUROK 3, POBLACION | Core Local Access Road | 5531000 |  |  |  |  | 1 | Completed |  | 2019-07-19 | BUK. LFP DRIVE
2017 | REGION X | BUKIDNON | DAMULOG | 3RD | POBLACION (Nat'l Highway to Colago St., Dr. Jose Rizal St. to Carlos Garcia St., Dr. Jose Rizal St. to Gregorio Del Pilar St., Andres Bonifacio to Ramon Magsaysay St., Dr. Jose Rizal St. to Manlabao St.) | Core Local Access Road | 10036000 |  |  |  |  | 1 | Completed | Nat'l Highway to Colago St., Dr. Jose Rizal St. to Carlos Garcia St., Dr. Jose Rizal St. to Gregorio Del Pilar St., Andres Bonifacio to Ramon Magsaysay St. and Dr. Jose Rizal St. to Manlabao St.-Completed | 2017-12-19 | SWA
2017 | REGION X | BUKIDNON | DANGCAGAN | 3RD | UPPER BANBAN, MIARAY | Core Local Access Road | 1213000 |  |  |  |  | 1 | Completed | SWA | 2018-03-14
2017 | REGION X | BUKIDNON | DANGCAGAN | 3RD | BUGWAK | Core Local Access Road | 2000000 |  |  |  |  | 1 | Completed | FOR TURN OVER (SWA) | 2019-08-01
2017 | REGION X | BUKIDNON | DANGCAGAN | 3RD | SAN VICENTE | Core Local Access Road | 5000000 |  |  |  |  | 1 | Completed |  | 2018-05-08 | MJG
2017 | REGION X | BUKIDNON | DANGCAGAN | 3RD | DOLOROSA | Core Local Access Road | 5000000 |  |  |  |  | 1 | Completed | FOR TURN OVER (SWA) | 2019-08-01
2017 | REGION X | BUKIDNON | IMPASUG-ONG | 2ND | BARANGAY GUIHEAN | Core Local Access Road | 2333000 |  |  |  |  | 1 | Completed | SWA | 2018-09-11
2017 | REGION X | BUKIDNON | KADINGILAN | 3RD | BARANGAY PAY AS | Core Local Access Road | 1650000 |  |  |  |  | 1 | Completed | as of 3/21/2019 (SWA) | 2019-04-16
2017 | REGION X | BUKIDNON | KADINGILAN | 3RD | BARANGAY BAGOR | Core Local Access Road | 1650000 |  |  |  |  | 1 | Completed | as of 4/21/2019 (SWA) | 2019-05-10
2017 | REGION X | BUKIDNON | KADINGILAN | 3RD | BARANGAY BALAORA (Macao) | Core Local Access Road | 1100000 |  |  |  |  | 1 | Completed | as of 3/21/2019 (SWA) | 2019-04-16
2017 | REGION X | BUKIDNON | KADINGILAN | 3RD | BARANGAY MATAMPAY | Core Local Access Road | 1100000 |  |  |  |  | 1 | Completed | as of 3/21/2019 (SWA) | 2019-04-16
2017 | REGION X | BUKIDNON | KADINGILAN | 3RD | BARANGAY CABADIANGAN | Core Local Access Road | 1683000 |  |  |  |  | 1 | Completed | SWA | 2019-02-22
2017 | REGION X | BUKIDNON | KADINGILAN | 3RD | BARANGAY POBLACION | Core Local Access Road | 1100000 |  |  |  |  | 1 | Completed | SWA | 2019-02-22
2017 | REGION X | BUKIDNON | KADINGILAN | 3RD | BARANGAY PINAMANGGUAN | Core Local Access Road | 1100000 |  |  |  |  | 1 | Completed | as of 3/21/2019 (SWA) | 2019-04-16
2017 | REGION X | BUKIDNON | KADINGILAN | 3RD | BARANGAY SAN ANDRES | Core Local Access Road | 1100000 |  |  |  |  | 1 | Completed | SWA | 2019-02-22
2017 | REGION X | BUKIDNON | KIBAWE | 3RD | BRGY SINIPON | Core Local Access Road | 6000000 |  |  |  |  | 1 | Completed | SWA | 2018-02-13
2017 | REGION X | BUKIDNON | KITAOTAO | 3RD | BARANGAY PAGAN AND WHITE KULAMAN WITH SITIOS SAGARAN, NABUNTURAN, DADIANGAS, MIDSAYAP AND SITIO DIVISION AS A DIRECT TRAVERSE SITIOS, ALL OF THE MUNICIPALITY OF KITAOTAO | Core Local Access Road | 11758000 | 1 |  |  |  |  | CANCELLED | Incompliant to Documentary Requirements/ No Release to LGU | 2018-02-28
2017 | REGION X | BUKIDNON | LIBONA | 1ST | KIONGKOG, PALABUCAN | Core Local Access Road | 2100000 |  |  |  |  | 1 | Completed | as of 1/9/2019 (SWA) | 2019-05-31 | JKB
2017 | REGION X | BUKIDNON | MANOLO FORTICH | 1ST | SITIO BALAMBAN, BARANGAY AGUSAN CANYON | Core Local Access Road | 10000000 | 1 |  |  |  |  | CANCELLED | Returned to Bureau of Treasury | 2020-02-10
2017 | REGION X | BUKIDNON | MARAMAG | 3RD | PUROK 2A NORTH POBLACION | Core Local Access Road | 10433000 |  |  |  |  | 1 | Completed |  | 2018-10-25 | ME
2017 | REGION X | BUKIDNON | MARAMAG | 3RD | PUROK 2A NORTH POBLACION (SOUTH POBLACION) | Core Local Access Road | 1893000 |  |  |  |  | 1 | Completed | SWA | 2018-04-19
2017 | REGION X | BUKIDNON | MARAMAG | 3RD | PUROK 1 SOUTH POBLACION | Core Local Access Road | 7566907 |  |  |  |  | 1 | Completed | SWA | 2018-08-07
2017 | REGION X | BUKIDNON | PANGANTUCAN | 4TH | BARANGAY GANDINGAN | Core Local Access Road | 5000000 |  |  |  |  | 1 | Completed | as of 4/3/2019 (SWA) | 2019-05-03
2017 | REGION X | BUKIDNON | PANGANTUCAN | 4TH | BARANGAY PIGTAURANAN | Core Local Access Road | 5000000 |  |  |  |  | 1 | Completed |  | 12/21/2018 | JB
2017 | REGION X | BUKIDNON | QUEZON | 3RD | BALANGAY 12 (NEW QUEMERS), POBLACION , TO CENTRO MERANGERAN | Core Local Access Road | 15000000 |  |  |  |  | 1 | Completed | SWA | 2018-05-21
2017 | REGION X | BUKIDNON | SUMILAO | 1ST | PUROK 1 TO PUROK 2, KISOLON | Core Local Access Road | 2000000 |  |  |  |  | 1 | Completed |  | 2018-03-20 | BT
2017 | REGION X | BUKIDNON | SUMILAO | 1ST | PUROK 3 TO PUROK 5, POBLACION | Core Local Access Road | 2000000 |  |  |  |  | 1 | Completed |  | 2018-03-20 | BT
2017 | REGION X | BUKIDNON | SUMILAO | 1ST | PUROK 1 TO PUROK 2, PUNTIAN | Core Local Access Road | 1000000 |  |  |  |  | 1 | Completed |  | 2018-03-20 | BT
2017 | REGION X | BUKIDNON | SUMILAO | 1ST | PUROK 1 TO PUROK 3, KULASI | Core Local Access Road | 1000000 |  |  |  |  | 1 | Completed |  | 2018-03-20 | BT
2017 | REGION X | BUKIDNON | SUMILAO | 1ST | PUROK 1 TO PUROK 3, LUPIAGAN | Core Local Access Road | 1000000 |  |  |  |  | 1 | Completed |  | 2018-03-20 | BT
2017 | REGION X | BUKIDNON | SUMILAO | 1ST | PUROK 1 TO PUROK 4, SAN ROQUE | Core Local Access Road | 1000000 |  |  |  |  | 1 | Completed |  | 2018-03-20 | BT
2017 | REGION X | BUKIDNON | SUMILAO | 1ST | PUROK 1, 2,& 4, SAN VICENTE | Core Local Access Road | 1000000 |  |  |  |  | 1 | Completed |  | 2018-03-20 | BT
2017 | REGION X | BUKIDNON | SUMILAO | 1ST | OCCASION | Core Local Access Road | 1000000 |  |  |  |  | 1 | Completed |  | 2018-03-20 | BT
2017 | REGION X | BUKIDNON | SUMILAO | 1ST | VISTA VILLA | Core Local Access Road | 1000000 |  |  |  |  | 1 | Completed |  | 2018-03-20 | BT
2017 | REGION X | BUKIDNON | SUMILAO | 1ST | PUROK 1 TO PUROK 2, LICOAN | Core Local Access Road | 1000000 |  |  |  |  | 1 | Completed |  | 2018-03-20 | BT
SUB-TOTAL (LAR) BUKIDNON: |  |  | 13 |  |  | 36 | 130346907 | 2 | 0 | 0 | 0 | 34
2017 | REGION X | BUKIDNON | BAUNGON | 1ST | BARANGAY IMBATUG | Evacuation Facility | 4000000 |  |  |  |  | 1 | Completed | as of 7/22/2019 SWA | 2019-08-12
2017 | REGION X | BUKIDNON | CABANGLASAN | 2ND | TOWNSITE, POBLACION | Evacuation Facility | 3000000 |  |  |  |  | 1 | Completed | as of 8/30/2019 (SWA) | 2019-10-28
2017 | REGION X | BUKIDNON | IMPASUG-ONG | 2ND | BARANGAY GUIHEAN | Evacuation Facility | 1000000 |  |  |  |  | 1 | Completed | as of 10/15/2019 SWA; for Final Inspection | 2019-12-11 | JKB
2017 | REGION X | BUKIDNON | IMPASUG-ONG | 2ND | BARANGAY DUMALAGUING | Evacuation Facility | 1000000 |  |  |  |  | 1 | Completed | as of 10/15/2019 SWA; FOR FINAL INSPECTION | 2019-12-11 | JKB
2017 | REGION X | BUKIDNON | SAN FERNANDO | 2ND | POBLACION, HALAPITAN | Evacuation Facility | 1500000 |  |  |  |  | 1 | Completed |  | 2018-05-16 | BT
SUB-TOTAL (OTHERS) BUKIDNON: |  |  | 2 |  |  | 5 | 10500000 | 0 | 0 | 0 | 0 | 5
TOTAL (OTHERS+LAR) (BUKIDNON) |  |  | 15 |  |  | 41 | 140846907 | 2 | 0 | 0 | 0 | 39
2017 | REGION X | CAMIGUIN | CATARMAN | LONE | SITIO TIBACJAO, BRGY. TANGARO | Core Local Access Road | 9378000 |  |  |  |  | 1 | Completed | SWA | 2018-06-05
2017 | REGION X | CAMIGUIN | MAHINOG | LONE | BRHO, BENONI- P 1,000,000.00; TUBOD- P500,000.00; CATOHUGAN- P1,000,000.00; POBLACION- P1,000,000.00 | Core Local Access Road | 3500000 |  |  |  |  | 1 | Completed | NHA BENONI, CATOHUGAN, POBLACION and TUBOD - Completed | 2018-05-21 | CT
2017 | REGION X | CAMIGUIN | MAMBAJAO (CAPITAL) | LONE | SITIO LAKAS BRGY. POBLACION | Core Local Access Road | 5000000 |  |  |  |  | 1 | Completed | as of 2/28/2019 (SWA) | 2019-04-01
2017 | REGION X | CAMIGUIN | SAGAY | LONE | CENTRO, POBLACION, SAGAY | Core Local Access Road | 2500000 |  |  |  |  | 1 | Completed | SWA | 2018-03-27
2017 | REGION X | CAMIGUIN | SAGAY | LONE | SITIO BAGDAL, BONBON, SAGAY | Core Local Access Road | 10000000 |  |  |  |  | 1 | Completed |  | 2018-07-17 | KA
TOTAL (LAR) (CAMIGUIN): |  |  | 4 |  |  | 5 | 30378000 | 0 | 0 | 0 | 0 | 5
2017 | REGION X | LANAO DEL NORTE | BACOLOD | 1ST | PUROK 5, LIANGAN EAST | Core Local Access Road | 2000000 |  |  |  |  | 1 | Completed | SWA | 1/29/2018
2017 | REGION X | LANAO DEL NORTE | BACOLOD | 1ST | ALEGRIA | Core Local Access Road | 2268000 |  |  |  |  | 1 | Completed | SWA | 2017-10-24
2017 | REGION X | LANAO DEL NORTE | BACOLOD | 1ST | POBLACION | Core Local Access Road | 2500000 |  |  |  |  | 1 | Completed | SWA | 2018-02-27
2017 | REGION X | LANAO DEL NORTE | BACOLOD | 1ST | PUROK 3, LIANGAN | Core Local Access Road | 1000000 |  |  |  |  | 1 | Completed | SWA | 2017-10-24
2017 | REGION X | LANAO DEL NORTE | BACOLOD | 1ST | RUPAGAN | Core Local Access Road | 2000000 |  |  |  |  | 1 | Completed | SWA | 1/29/2018
2017 | REGION X | LANAO DEL NORTE | BALOI | 1ST | BARANGAY EAST P-CADAYONAN TO BRGY SANGCAD CORMATAN | Core Local Access Road | 11822000 |  |  |  |  | 1 | Completed | SWA | 2018-05-21
2017 | REGION X | LANAO DEL NORTE | BAROY | 1ST | PENDULONAN | Core Local Access Road | 4706000 |  |  |  |  | 1 | Completed | SWA | 2018-02-27
2017 | REGION X | LANAO DEL NORTE | BAROY | 1ST | STO NINO VILLAGE, BAROY DACU | Core Local Access Road | 2500000 |  |  |  |  | 1 | Completed | SWA | 2018-02-27
2017 | REGION X | LANAO DEL NORTE | BAROY | 1ST | BAROY DACU | Core Local Access Road | 2500000 |  |  |  |  | 1 | Completed | SWA | 2018-03-13
2017 | REGION X | LANAO DEL NORTE | KAPATAGAN | 2ND | BARANGAY POBLACION | Core Local Access Road | 21733907 |  |  |  |  | 1 | Completed | SWA | 2018-07-26
2017 | REGION X | LANAO DEL NORTE | KAUSWAGAN | 1ST | POBLACION AND BAGUMBAYAN | Core Local Access Road | 6000000 |  |  |  |  | 1 | Completed |  | 2018-01-12 | LDNT
2017 | REGION X | LANAO DEL NORTE | KOLAMBUGAN | 1ST | SOCUDAN | Core Local Access Road | 19758907 |  |  |  |  | 1 | Completed | SWA | 2018-06-05
2017 | REGION X | LANAO DEL NORTE | LALA | 2ND | REBE AND PENDEULONAN | Core Local Access Road | 12898000 |  |  |  |  | 1 | Completed | SWA | 2018-03-07
2017 | REGION X | LANAO DEL NORTE | LINAMON | 1ST | POBLACION (GOING TO GP CANOY SCHOOL)/Tilapas, Poblacion | Core Local Access Road | 7000000 |  |  |  |  | 1 | Completed | SWA | 2018-06-12
2017 | REGION X | LANAO DEL NORTE | LINAMON | 1ST | JUNCTION AGWANTA | Core Local Access Road | 2014000 |  |  |  |  | 1 | Completed | SWA | 2018-03-27
2017 | REGION X | LANAO DEL NORTE | LINAMON | 1ST | PURAKAN TO BALAK 2 | Core Local Access Road | 6000000 |  |  |  |  | 1 | Completed | SWA | 2018-03-27
2017 | REGION X | LANAO DEL NORTE | LINAMON | 1ST | BOSQUE - PURAKAN | Core Local Access Road | 2000000 |  |  |  |  | 1 | Completed | SWA | 2017-12-27
2017 | REGION X | LANAO DEL NORTE | LINAMON | 1ST | UPPER MAGO-ONG TO EVACUATION CENTER | Core Local Access Road | 1500907 |  |  |  |  | 1 | Completed | SWA | 2017-12-27
2017 | REGION X | LANAO DEL NORTE | MAGSAYSAY | 2ND | BRGY OLANGO | Core Local Access Road | 2000000 |  |  |  |  | 1 | Completed | SWA | 11/22/2018
2017 | REGION X | LANAO DEL NORTE | MAGSAYSAY | 2ND | BRGY UPPER CANINGAG | Core Local Access Road | 2000000 |  |  |  |  | 1 | Completed |  | 2019-07-19 | CL
2017 | REGION X | LANAO DEL NORTE | MAGSAYSAY | 2ND | BRGY DURIANON | Core Local Access Road | 1382000 |  |  |  |  | 1 | Completed | SWA | 2017-12-12
2017 | REGION X | LANAO DEL NORTE | MAIGO | 1ST | PUROK 2, BALAGTASA | Core Local Access Road | 9647000 |  |  |  |  | 1 | Completed | SWA | 2017-11-20 | CCP
2017 | REGION X | LANAO DEL NORTE | MATUNGAO | 1ST | BARANGAY UPPER BATAL, BARANGAY BANCO | Core Local Access Road | 9078000 |  |  |  |  | 1 | Completed | SWA | 2018-05-21
2017 | REGION X | LANAO DEL NORTE | MUNAI | 2ND | PANGGAO | Core Local Access Road | 10184000 |  |  |  |  | 1 | Completed | SWA | 2018-06-28
2017 | REGION X | LANAO DEL NORTE | PANTAO RAGAT | 2ND | SITIO MARANDAG - BRGY CABASAGAN | Core Local Access Road | 9862000 |  |  |  |  | 1 | Completed | SWA | 2017-10-25
2017 | REGION X | LANAO DEL NORTE | PANTAR | 1ST | BARANGAY BUBONG MADAYA TO BARANGAY CAMPONG (HIGHWAY) | Core Local Access Road | 6925000 |  |  |  |  | 1 | Completed | SWA | 10/17/2018
2017 | REGION X | LANAO DEL NORTE | POONA PIAGAPO | 2ND | BARANGAY MADAYA | Core Local Access Road | 9886000 |  |  |  |  | 1 | Completed | SWA | 2017-12-12
2017 | REGION X | LANAO DEL NORTE | SALVADOR | 2ND | PUROK 5 - CURVA MIAGAO & ADJACENT BRGY | Core Local Access Road | 5000000 |  |  |  |  | 1 | Completed | SWA | 2017-01-12
2017 | REGION X | LANAO DEL NORTE | SALVADOR | 2ND | BARANGAY PADIANAN -BARANGAY KILALA | Core Local Access Road | 5166000 |  |  |  |  | 1 | Completed |  | 2019-02-18 | nd/fcla
2017 | REGION X | LANAO DEL NORTE | SAPAD | 2ND | BRGY PANOLOON TO KATIPUNAN | Core Local Access Road | 2000000 |  |  |  |  | 1 | Completed | SWA | 2018-07-24
2017 | REGION X | LANAO DEL NORTE | SAPAD | 2ND | MAPUROG | Core Local Access Road | 2300000 |  |  |  |  | 1 | Completed | SWA | 2018-07-24
2017 | REGION X | LANAO DEL NORTE | SAPAD | 2ND | P-11, POBLACION | Core Local Access Road | 2300000 |  |  |  |  | 1 | Completed | SWA | 2018-03-07
2017 | REGION X | LANAO DEL NORTE | TAGOLOAN | 1ST | DAMAS PROPER TO SITIO PALO | Core Local Access Road | 6000000 | 1 |  |  |  |  | CANCELLED | Incompliant to Documentary Requirements/ No Release to LGU | 2018-08-03 | CP
2017 | REGION X | LANAO DEL NORTE | TANGCAL | 2ND | BARANGAY LINAO | Core Local Access Road | 9105000 |  |  |  |  | 1 | Completed | SWA | 2018-09-13
2017 | REGION X | LANAO DEL NORTE | TUBOD (CAPITAL) | 1ST | BARANGAY POBLACION | Core Local Access Road | 1500000 |  |  |  |  | 1 | Completed | SWA | 2017-09-25
2017 | REGION X | LANAO DEL NORTE | TUBOD (CAPITAL) | 1ST | BARANGAY KALILANGAN | Core Local Access Road | 6088907 |  |  |  |  | 1 | Completed | SWA | 2018-02-13
SUB-TOTAL (LAR) LANAO DEL NORTE: |  |  | 20 |  |  | 36 | 210625628 | 1 | 0 | 0 | 0 | 35
2017 | REGION X | LANAO DEL NORTE | KAUSWAGAN | 1ST | POBLACION | Evacuation Facility | 3000000 |  |  |  |  | 1 | Completed | SWA | 2018-07-11
2017 | REGION X | LANAO DEL NORTE | LINAMON | 1ST | POBLACION | Evacuation Facility | 1000000 |  |  |  |  | 1 | Completed | SWA | 2018-10-26
2017 | REGION X | LANAO DEL NORTE | LINAMON | 1ST | PUROK 3, ROBOCON | Evacuation Facility | 3000000 |  |  |  |  | 1 | Completed | SWA | 2018-07-26
2017 | REGION X | LANAO DEL NORTE | NUNUNGAN | 2ND | PUROK 1, NRGY. MANSIBAY | Evacuation Facility | 7772000 |  |  |  |  | 1 | Completed | SWA | 2018-05-07
2017 | REGION X | LANAO DEL NORTE | PANTAR | 1ST | BARANGAY POBLACION | Evacuation Facility | 6000000 |  |  |  |  | 1 | Completed | as of 12/20/2019 SWA | 2019-12-23
2017 | REGION X | LANAO DEL NORTE | SAPAD | 2ND | SITIO SAN ROQUE, PANOLOON | Evacuation Facility | 3000000 |  |  |  |  | 1 | Completed | SWA | 2018-07-24
2017 | REGION X | LANAO DEL NORTE | SULTAN NAGA DIMAPORO (KAROMATAN) | 2ND | POBLACION | Evacuation Facility | 3000000 |  |  |  |  | 1 | Completed |  | 2019-07-19 | CL
SUB-TOTAL (OTHERS) LANAO DEL NORTE: |  |  | 2 |  |  | 7 | 26772000 | 0 | 0 | 0 | 0 | 7
TOTAL (OTHERS+LAR) (LANAO DEL NORTE): |  |  | 22 |  |  | 43 | 237397628 | 1 | 0 | 0 | 0 | 42
2017 | REGION X | MISAMIS OCCIDENTAL | ALORAN | 1ST | DALISAY, IBABAO, OSPITAL | Core Local Access Road | 6000000 |  |  |  |  | 1 | Completed | SWA | 2018-07-10
2017 | REGION X | MISAMIS OCCIDENTAL | BALIANGAO | 1ST | BRGY. MABINI | Core Local Access Road | 4000000 |  |  |  |  | 1 | Completed |  | 2019-09-19 | Monthly Meeting
2017 | REGION X | MISAMIS OCCIDENTAL | BALIANGAO | 1ST | BRGY. NORTHERN POBLACION | Core Local Access Road | 3361000 |  |  |  |  | 1 | Completed |  | 2019-09-19 | Monthly Meeting
2017 | REGION X | MISAMIS OCCIDENTAL | BONIFACIO | 2ND | BOLINSONG | Core Local Access Road | 3000000 |  |  |  |  | 1 | Completed |  | 2017-11-01 | MOT
2017 | REGION X | MISAMIS OCCIDENTAL | BONIFACIO | 2ND | POBLACION | Core Local Access Road | 3000000 |  |  |  |  | 1 | Completed | SWA | 2018-05-09
2017 | REGION X | MISAMIS OCCIDENTAL | BONIFACIO | 2ND | DIGSON | Core Local Access Road | 3000000 |  |  |  |  | 1 | Completed |  | 2017-11-01 | MOT
2017 | REGION X | MISAMIS OCCIDENTAL | BONIFACIO | 2ND | D. FERNAN | Core Local Access Road | 1421000 |  |  |  |  | 1 | Completed | SWA | 2017-11-15 | CB
2017 | REGION X | MISAMIS OCCIDENTAL | CALAMBA | 1ST | BRGY. MAGCAMIGUING | Core Local Access Road | 1200000 |  |  |  |  | 1 | Completed | SWA | 2018-03-27
2017 | REGION X | MISAMIS OCCIDENTAL | CALAMBA | 1ST | BRGY. NORTHERN POBLACION | Core Local Access Road | 1500000 |  |  |  |  | 1 | Completed | SWA | 2018-03-27
2017 | REGION X | MISAMIS OCCIDENTAL | CLARIN | 2ND | POBLACION II | Core Local Access Road | 10757000 |  |  |  |  | 1 | Completed | SWA | 2018-08-15
2017 | REGION X | MISAMIS OCCIDENTAL | CONCEPCION | 1ST | BRGY. LINGATONGAN-NEW CASUL- UPPER DAPITAN | Core Local Access Road | 14132000 | 1 |  |  |  |  | CANCELLED |  | 2020-06-05 | ENGR. EMPERIO
2017 | REGION X | MISAMIS OCCIDENTAL | DON VICTORIANO CHIONGBIAN (DON MARIAN | 2ND | PUROK 5, LALUD | Core Local Access Road | 8902000 |  |  |  |  | 1 | Completed |  | 2019-09-16 | Monthly Meeting
2017 | REGION X | MISAMIS OCCIDENTAL | JIMENEZ | 1ST | PUROK 2, BRGY. ADORABLE | Core Local Access Road | 500000 |  |  |  |  | 1 | Completed | SWA | 2018-06-18
2017 | REGION X | MISAMIS OCCIDENTAL | JIMENEZ | 1ST | PUROK 5, BRGY. BUTUAY | Core Local Access Road | 500000 |  |  |  |  | 1 | Completed | SWA | 2018-07-16
2017 | REGION X | MISAMIS OCCIDENTAL | JIMENEZ | 1ST | PUROK 3, 4, & 5 BRGY. CARMEN | Core Local Access Road | 2000000 |  |  |  |  | 1 | Completed | SWA | 2018-06-18
2017 | REGION X | MISAMIS OCCIDENTAL | JIMENEZ | 1ST | LAPU-LAPU ST. PUROK 2, BRY. CORRALES | Core Local Access Road | 500000 |  |  |  |  | 1 | Completed | SWA | 2018-06-18
2017 | REGION X | MISAMIS OCCIDENTAL | JIMENEZ | 1ST | PUROK LAWAAN, DICOLOC | Core Local Access Road | 1000000 |  |  |  |  | 1 | Completed | SWA | 2018-05-07
2017 | REGION X | MISAMIS OCCIDENTAL | JIMENEZ | 1ST | PUROK 2, BRGY. GATA | Core Local Access Road | 671907 |  |  |  |  | 1 | Completed | SWA | 2018-05-07
2017 | REGION X | MISAMIS OCCIDENTAL | JIMENEZ | 1ST | PUROK 7, BRGY. GUINTOMOYAN | Core Local Access Road | 500000 |  |  |  |  | 1 | Completed | SWA | 2018-06-18
2017 | REGION X | MISAMIS OCCIDENTAL | JIMENEZ | 1ST | PUROK 2 & 5, BRGY. MACABAYAO | Core Local Access Road | 500000 |  |  |  |  | 1 | Completed | SWA | 2018-06-18
2017 | REGION X | MISAMIS OCCIDENTAL | JIMENEZ | 1ST | PUROK 2 & 3, BRGY. MALIBACSAN | Core Local Access Road | 1000000 |  |  |  |  | 1 | Completed | SWA | 2018-05-25
2017 | REGION X | MISAMIS OCCIDENTAL | JIMENEZ | 1ST | PUROK 1, MATUGAS ALTO | Core Local Access Road | 500000 |  |  |  |  | 1 | Completed | SWA | 2018-05-25
2017 | REGION X | MISAMIS OCCIDENTAL | JIMENEZ | 1ST | PUROK 3 & 4, BRGY. MATUGAS BAJO | Core Local Access Road | 1000000 |  |  |  |  | 1 | Completed | SWA | 2018-06-18
2017 | REGION X | MISAMIS OCCIDENTAL | JIMENEZ | 1ST | PUROK 4, BRGY. MIALEM | Core Local Access Road | 1000000 |  |  |  |  | 1 | Completed | SWA | 2018-05-25
2017 | REGION X | MISAMIS OCCIDENTAL | JIMENEZ | 1ST | PUROK 2 & 3, BRGY. NACIONAL | Core Local Access Road | 1000000 |  |  |  |  | 1 | Completed | SWA | 2018-05-25
2017 | REGION X | MISAMIS OCCIDENTAL | JIMENEZ | 1ST | JUAN LUNA ST, PUROK 3, BRGY. NAGA | Core Local Access Road | 500000 |  |  |  |  | 1 | Completed | SWA | 2018-05-25
2017 | REGION X | MISAMIS OCCIDENTAL | JIMENEZ | 1ST | PUROK 1, BRGY. SAN ISIDRO | Core Local Access Road | 500000 |  |  |  |  | 1 | Completed | SWA | 2018-06-18
2017 | REGION X | MISAMIS OCCIDENTAL | JIMENEZ | 1ST | PUROK 5, BRGY. STA. CRUZ | Core Local Access Road | 500000 |  |  |  |  | 1 | Completed | SWA | 2018-04-11
2017 | REGION X | MISAMIS OCCIDENTAL | JIMENEZ | 1ST | PUROK 4, BRGY. SETI | Core Local Access Road | 500000 |  |  |  |  | 1 | Completed | SWA | 2018-06-18
2017 | REGION X | MISAMIS OCCIDENTAL | JIMENEZ | 1ST | PUROK 2, BRGY. SIBAROC | Core Local Access Road | 500000 |  |  |  |  | 1 | Completed | SWA | 2018-05-25
2017 | REGION X | MISAMIS OCCIDENTAL | JIMENEZ | 1ST | PUROK 2, BRGY. SINARA ALTO | Core Local Access Road | 500000 |  |  |  |  | 1 | Completed | SWA | 2018-06-18
2017 | REGION X | MISAMIS OCCIDENTAL | JIMENEZ | 1ST | PUROK 3, BRGY. SINARA BAJO | Core Local Access Road | 500000 |  |  |  |  | 1 | Completed | SWA | 2018-06-18
2017 | REGION X | MISAMIS OCCIDENTAL | JIMENEZ | 1ST | PUROK 3 & 4, PUROK 5 & 6, PUROK 6, BRGY. TARAKA | Core Local Access Road | 1500000 |  |  |  |  | 1 | Completed | SWA | 2018-05-07
2017 | REGION X | MISAMIS OCCIDENTAL | LOPEZ JAENA | 1ST | PUROK 1, BRGY. RIZAL | Core Local Access Road | 9908000 |  |  |  |  | 1 | Completed |  | 2019-02-18 | cb/fcla
2017 | REGION X | MISAMIS OCCIDENTAL | PANAON | 1ST | POBLACION & SAN ANDRES | Core Local Access Road | 9000000 |  |  |  |  | 1 | Completed |  | 11/28/2017 | KA
2017 | REGION X | MISAMIS OCCIDENTAL | PANAON | 1ST | BRGY. POBLACION | Core Local Access Road | 2331000 |  |  |  |  | 1 | Completed | SWA | 2018-04-17
2017 | REGION X | MISAMIS OCCIDENTAL | PLARIDEL | 1ST | BRGY. STA. CRUZ- PUNTOD- MANGIDKID | Core Local Access Road | 7000000 |  |  |  |  | 1 | Completed |  | 12/14/2018 | CB
2017 | REGION X | MISAMIS OCCIDENTAL | PLARIDEL | 1ST | BRGY. DIVISORIA-MAMANGA GAMAY | Core Local Access Road | 2000000 |  |  |  |  | 1 | Completed | SWA | 11/28/2017
2017 | REGION X | MISAMIS OCCIDENTAL | PLARIDEL | 1ST | BRGY. USOCAN- DANAO | Core Local Access Road | 3450000 |  |  |  |  | 1 | Completed | SWA | 11/28/2017
2017 | REGION X | MISAMIS OCCIDENTAL | SAPANG DALAGA | 1ST | BRGY. CASUL-SITIO ONGGANAY | Core Local Access Road | 19254907 |  |  |  |  | 1 | Completed | SWA | 2019-04-08
SUB-TOTAL (LAR) MIS.OCC: |  |  | 12 |  |  | 40 | 128888814 | 1 | 0 | 0 | 0 | 39
2017 | REGION X | MISAMIS OCCIDENTAL | ALORAN | 1ST | DALISAY | Evacuation Facility | 1000000 |  |  |  |  | 1 | Completed | SWA | 2018-03-08
2017 | REGION X | MISAMIS OCCIDENTAL | CALAMBA | 1ST | MUNICIPAL COMPOUND- BRGY. SOUTHWESTERN POBLACION | Evacuation Facility | 2000000 |  |  |  |  | 1 | Completed | SWA | 12/20/2018
SUB-TOTAL (OTHERS) MIS.OCC: | [5 empty] | 2 | 3000000 | 0 | 0 | 0 | 0 | 2
TOTAL (OTHERS+LAR) (MISAMIS OCCIDENTAL): |  |  | 12 |  |  | 42 | 131888814 | 1 | 0 | 0 | 0 | 41
2017 | REGION X | MISAMIS ORIENTAL | ALUBIJID | 2ND | SITIO POBLACION, BRGY. SAMPATULOG | Core Local Access Road | 13515000 |  |  |  |  | 1 | Completed |  | 2018-06-20 | npjr
2017 | REGION X | MISAMIS ORIENTAL | BALINGASAG | 1ST | BRGY. KIBALUS, SAN ISIDRO | Core Local Access Road | 2000000 |  |  |  |  | 1 | Completed | SWA | 1/29/2018 | NPJ
2017 | REGION X | MISAMIS ORIENTAL | BALINGASAG | 1ST | BRGY. VENCER, MANDANGOA | Core Local Access Road | 2000000 |  |  |  |  | 1 | Completed | SWA | 1/29/2018 | NPJ
2017 | REGION X | MISAMIS ORIENTAL | BALINGASAG | 1ST | BRGY. KIBANBAN | Core Local Access Road | 3000000 |  |  |  |  | 1 | Completed |  | 2018-06-20 | MOT
2017 | REGION X | MISAMIS ORIENTAL | BALINGASAG | 1ST | BRGY. QUEZON | Core Local Access Road | 2000000 |  |  |  |  | 1 | Completed |  | 2018-03-20 | NPJ
2017 | REGION X | MISAMIS ORIENTAL | BALINGASAG | 1ST | BRGY. CALAWAG | Core Local Access Road | 2000000 |  |  |  |  | 1 | Completed | SWA | 1/29/2018 | NPJ
2017 | REGION X | MISAMIS ORIENTAL | BALINGASAG | 1ST | BRGY. SAN FRANCISCO | Core Local Access Road | 2000000 |  |  |  |  | 1 | Completed | SWA | 2018-02-27
2017 | REGION X | MISAMIS ORIENTAL | BALINGOAN | 1ST | BRGY. BAUK-BAUK | Core Local Access Road | 12331000 | 1 |  |  |  |  | CANCELLED | No funds downloaded/release; for possible cancellation | 2018-06-20 | MOT
2017 | REGION X | MISAMIS ORIENTAL | BINUANGAN | 1ST | BRGY. VALDECONCHA & SITIOS SILAD & KIBUNGTOD | Core Local Access Road | 20000000 |  |  |  |  | 1 | Completed | as of 4/18/2019 (SWA) | 2019-04-22
2017 | REGION X | MISAMIS ORIENTAL | CLAVERIA | 2ND | P6-MENCALOPE STRETCH POBLACION | Core Local Access Road | 6802000 |  |  |  |  | 1 | Completed | as of 7/23/2019 (SWA) | 7/23/2019
2017 | REGION X | MISAMIS ORIENTAL | CLAVERIA | 2ND | PUROK 1 & PUROK 2 MALAGANA | Core Local Access Road | 2000000 |  |  |  |  | 1 | Completed | as of 7/23/2019 (SWA) | 7/23/2019
2017 | REGION X | MISAMIS ORIENTAL | CLAVERIA | 2ND | PUROK 7 BRGY. MADAGUING | Core Local Access Road | 2000000 |  |  |  |  | 1 | Completed | per V.O. 1: 95.54% Phy. Accomp. As of 4/3/2019 (SWA) | 2019-04-08
2017 | REGION X | MISAMIS ORIENTAL | GITAGUM | 2ND | COGON TO TALA-O ROAD | Core Local Access Road | 12757000 |  |  |  |  | 1 | Completed |  | 2018-02-28 | EJD
2017 | REGION X | MISAMIS ORIENTAL | INITAO | 2ND | SINALAC, INITAO | Core Local Access Road | 13708000 |  |  |  |  | 1 | Completed | SWA | 2018-03-27
2017 | REGION X | MISAMIS ORIENTAL | LAGONGLONG | 1ST | KABULAWAN, LAGONGLONG | Core Local Access Road | 3987000 |  |  |  |  | 1 | Completed |  | 2018-07-09 | EJD
2017 | REGION X | MISAMIS ORIENTAL | LAGONGLONG | 1ST | KAUSWAGAN, LAGONGLONG | Core Local Access Road | 4000000 |  |  |  |  | 1 | Completed |  | 2018-08-22 | EJD
2017 | REGION X | MISAMIS ORIENTAL | LAGUINDINGAN | 2ND | GK HEIGHTS, KIBAGHOT, LAGUINDINGAN | Core Local Access Road | 3000000 |  |  |  |  | 1 | Completed | SWA | 2018-09-05
2017 | REGION X | MISAMIS ORIENTAL | LAGUINDINGAN | 2ND | GK DIAMOND, KIBAGHOT, LAGUINDINGAN | Core Local Access Road | 3000000 |  |  |  |  | 1 | Completed | SWA | 2018-06-26
2017 | REGION X | MISAMIS ORIENTAL | LAGUINDINGAN | 2ND | UPPER ZONE 2, POBLACION, LAGUINDINGAN | Core Local Access Road | 2000000 |  |  |  |  | 1 | Completed | SWA | 2018-05-31
2017 | REGION X | MISAMIS ORIENTAL | LIBERTAD | 2ND | BRGY. POBLACION, LIBERTAD | Core Local Access Road | 3432000 |  |  |  |  | 1 | Completed | AS OF 12/17/2019 SWA | 2019-12-26
2017 | REGION X | MISAMIS ORIENTAL | LIBERTAD | 2ND | BRGY. DULONG | Core Local Access Road | 1000000 |  |  |  |  | 1 | Completed | SWA | 2018-09-11
2017 | REGION X | MISAMIS ORIENTAL | LIBERTAD | 2ND | BRGY. POBLACION | Core Local Access Road | 1000000 |  |  |  |  | 1 | Completed | SWA | 2018-09-11
2017 | REGION X | MISAMIS ORIENTAL | LIBERTAD | 2ND | BRGY. RETABLO | Core Local Access Road | 1000000 |  |  |  |  | 1 | Completed | SWA | 11/26/2018
2017 | REGION X | MISAMIS ORIENTAL | LIBERTAD | 2ND | BRGY. TANGKUB | Core Local Access Road | 1000000 |  |  |  |  | 1 | Completed | SWA | 2018-06-11
2017 | REGION X | MISAMIS ORIENTAL | LIBERTAD | 2ND | BRGY. STO. NINO | Core Local Access Road | 1000000 |  |  |  |  | 1 | Completed | as of 7/22/2019 (SWA) | 2019-08-12
2017 | REGION X | MISAMIS ORIENTAL | LIBERTAD | 2ND | BRGY. TAYTAYAN | Core Local Access Road | 1000000 |  |  |  |  | 1 | Completed | SWA | 11/26/2018
2017 | REGION X | MISAMIS ORIENTAL | LIBERTAD | 2ND | BRGY. KIMALOK | Core Local Access Road | 1000000 |  |  |  |  | 1 | Completed | SWA | 2018-06-11
2017 | REGION X | MISAMIS ORIENTAL | LIBERTAD | 2ND | BRGY. GIMAYLAN | Core Local Access Road | 1000000 |  |  |  |  | 1 | Completed | as of 7/22/2019 (SWA) | 2019-08-12
2017 | REGION X | MISAMIS ORIENTAL | LIBERTAD | 2ND | BRGY. LUBLUBAN | Core Local Access Road | 1000000 |  |  |  |  | 1 | Completed | SWA | 12/19/2018
2017 | REGION X | MISAMIS ORIENTAL | LUGAIT | 2ND | POBLACION TO BIGA | Core Local Access Road | 3000000 |  |  |  |  | 1 | Completed |  | 10/25/2018 | ME
2017 | REGION X | MISAMIS ORIENTAL | LUGAIT | 2ND | SITIO LICOAN, BRGY. BIGA | Core Local Access Road | 2400000 |  |  |  |  | 1 | Completed | SWA | 2018-05-07
2017 | REGION X | MISAMIS ORIENTAL | LUGAIT | 2ND | SITIO CABO-CABO, UPPER TALACOGON | Core Local Access Road | 2040000 |  |  |  |  | 1 | Completed | as of 12-19-2019 based on the swa submitted | 2019-02-19
2017 | REGION X | MISAMIS ORIENTAL | OPOL | 2ND | SEGMENT 1 SITIO CAMINGAWAN, BRGY. PATAG | Core Local Access Road | 10000000 |  |  |  |  | 1 | Completed | SWA | 2019-02-18 | npjr/EJD
2017 | REGION X | MISAMIS ORIENTAL | OPOL | 2ND | SEGMENT 2 SITIO GUSA, BRGY. BONBON | Core Local Access Road | 5346000 |  |  |  |  | 1 | Completed | SWA | 2019-02-19 | EJD
2017 | REGION X | MISAMIS ORIENTAL | SALAY | 1ST | BRGY. BUNAL, SALAY | Core Local Access Road | 13583000 |  |  |  |  | 1 | Completed | SWA | 2018-08-22
2017 | REGION X | MISAMIS ORIENTAL | SUGBONGCOGON | 1ST | BRGY. POBLACION & MIMBUAHAN | Core Local Access Road | 4830466.94 |  |  |  |  | 1 | Completed |  | 2018-03-20 | MOT
2017 | REGION X | MISAMIS ORIENTAL | SUGBONGCOGON | 1ST | BRGY. POBLACION | Core Local Access Road | 2496995.79 |  |  |  |  | 1 | Completed | SWA | 2018-02-28
2017 | REGION X | MISAMIS ORIENTAL | SUGBONGCOGON | 1ST | SITIO CAAMULAN, BRGY. POBLACION | Core Local Access Road | 1072537.27 |  |  |  |  | 1 | Completed | SWA | 2018-02-28
SUB-TOTAL (LAR) MIS.OR: |  |  | 14 |  |  | 38 | 169301000 | 1 | 0 | 0 | 0 | 37
2017 | REGION X | MISAMIS ORIENTAL | LAGONGLONG | 1ST | POBLACION, LAGONGLONG | Evacuation Facility | 5000000 |  |  |  |  | 1 | Completed | SWA | 11/14/2018
2017 | REGION X | MISAMIS ORIENTAL | TALISAYAN | 1ST | POBLACION, SAN JOSE, STA. INES | Evacuation Facility | 3274000 |  |  |  | 1 |  | On-going cancellation | Poblacion - 89.48% SWA AS OF MAY 2020 | 2020-02-27
[14 empty] | San Jose - 91.79% (SWA) AS OF MAY 2020 | 2020-02-27
[14 empty] | Sta. Ines - 75.65% (SWA) AS OF MAY 2020 | 2020-02-27
SUB-TOTAL (OTHERS) MIS.OR: |  |  | 1 |  |  | 2 | 8274000 | 0 | 0 | 0 | 1 | 1
TOTAL (OTHERS+LAR) (MISAMIS ORIENTAL): |  |  | 15 |  |  | 40 | 177575000 | 1 | 0 | 0 | 1 | 38
GRAND TOTAL |  |  | 68 |  |  | 171 | 718086349 | 5 | 0 | 0 | 1 | 165

## 2017 ADM-WATER
REGION X - ADM
2017 ADM-WATER
as of June 26, 2020
FY | REGION | PROVINCE | CITY / MUNICIPALITY | DISTRICT | BARANGAY | NAME OF PROJECT | ORIGINAL ALLOCATION | CANCELLED | APPROVED DED/POW or DED PREP. | PROCUREMENT | ON-GOING | COMPLETED | STATUS | REMARKS | DATE UPDATED
2017 | REGION X | BUKIDNON | BAUNGON | 1ST | SITIO KALANGAN, SAN VICENTE (Imbatug) | Provision of Potable Water Supply | 6563000 |  |  |  |  | 1 | Completed |  | 2019-07-15 | FCLA
2017 | REGION X | BUKIDNON | DON CARLOS | 3RD | EMBAYAO, SAN NICOLAS AND MARAYMARAY | Provision of Potable Water Supply | 12825000 | 1 |  |  |  |  | CANCELLED | Returned to BTr | 2019-07-12 | FCLA
2017 | REGION X | BUKIDNON | IMPASUG-ONG | 2ND | SITIO KIBUWA, BARANGAY IMPALUTAO | Provision of Potable Water Supply | 2000000 |  |  |  |  | 1 | Completed | as of 5/29/2019 (SWA) | 2019-05-30
2017 | REGION X | BUKIDNON | IMPASUG-ONG | 2ND | BARANGAY POBLACION AND LA FORTUNA | Provision of Potable Water Supply | 5000000 |  |  |  |  | 1 | Completed | as of 3/28/2019 (SWA) | 2019-05-30
2017 | REGION X | BUKIDNON | KALILANGAN | 4TH | BARANGAY NINOY AQUINO, MACAPAO, LAMPANUSAN AND BARANGAY PUBLIC | Provision of Potable Water Supply | 11064000 | 1 |  |  |  |  | CANCELLED | Incompliant to Documentary Requirements/ No Release to LGU | 2018-01-09 | MCN
2017 | REGION X | BUKIDNON | KIBAWE | 3RD | SITIO RAGOBROB BRGY NEW KIDAPAWAN | Provision of Potable Water Supply | 4771000 |  |  |  |  | 1 | Completed | as of 11/22/2019 SWA | 2019-12-13
2017 | REGION X | BUKIDNON | LANTAPAN | 2ND | SITIO SAN VICENTE, KAATUAN; UPPER ANAIB; BATANGASON, BACLAYON; UPPER BALILA, INSIBAY, POBLACION | Provision of Potable Water Supply | 10000000 |  |  |  |  | 1 | Completed | SWA | 2018-08-07
2017 | REGION X | BUKIDNON | LANTAPAN | 2ND | PUROK 3, BANTUANON TO SITIO KEIGO | Provision of Potable Water Supply | 2221000 |  |  |  |  | 1 | Completed | SWA | 2018-09-11
2017 | REGION X | BUKIDNON | LIBONA | 1ST | SIGMATAN AREA, SIL-IPON, | Provision of Potable Water Supply | 5332000 |  |  |  |  | 1 | Completed | SWA | 2018-10-16
2017 | REGION X | BUKIDNON | LIBONA | 1ST | BARANGAY SIL-IPON TO CAPIHAN | Provision of Potable Water Supply | 5000000 |  |  |  |  | 1 | Completed | SWA | 2018-07-10
2017 | REGION X | BUKIDNON | LIBONA | 1ST | SITIO KINGKOG, PALABUCAN | Provision of Potable Water Supply | 2000000 |  |  |  |  | 1 | Completed | as of 4/2019 (SWA) | 2019-04-16
2017 | REGION X | BUKIDNON | MALITBOG | 1ST | BAGYANGON, SAN LUIS | Provision of Potable Water Supply | 9845000 |  |  |  |  | 1 | Completed | AS OF 3/6/2020 SWA | 2020-05-19 | jb
2017 | REGION X | BUKIDNON | MANOLO FORTICH | 1ST | BARANGAY MAMBATANGAN | Provision of Potable Water Supply | 4744000 |  |  |  |  | 1 | Completed | as of 12/6/2019 SWA | 2019-12-20
2017 | REGION X | BUKIDNON | MARAMAG | 3RD | SOUTH POBLACION | Provision of Potable Water Supply | 4500000 |  |  |  |  | 1 | Completed |  | 2018-10-25 | ME
2017 | REGION X | BUKIDNON | PANGANTUCAN | 4TH | BARANGAY BANGAHAN | Provision of Potable Water Supply | 1706000 |  |  |  |  | 1 | Completed |  | 12/21/2018 | JB
2017 | REGION X | BUKIDNON | SAN FERNANDO | 2ND | MUNICIPAL WIDE, SELECTED 9 SCHOOLS IN SAN FERNANDO DISTRICT 1 AND 9 SCHOOLS IN DISTRICT 2 | Provision of Potable Water Supply | 900000 | 1 |  |  |  |  | CANCELLED | Returned Check to DILG November 2018 | 2019-03-15 | FCLA
2017 | REGION X | BUKIDNON | SAN FERNANDO | 2ND | SUPON, NACABUKLAD (Little Baguio and Mabuhay) | Provision of Potable Water Supply | 9409000 |  |  |  |  | 1 | Completed | SWA | 2018-10-02 | JB
2017 | REGION X | BUKIDNON | SUMILAO | 1ST | OCCASION | Provision of Potable Water Supply | 1445000 |  |  |  |  | 1 | Completed |  | 2018-06-20 | BT
2017 | REGION X | BUKIDNON | TALAKAG | 1ST | BRGYS 1,2,3,4,5, CACAON, DAGUMBAAN, STO NINO, SAN ISIDRO, SAN ANTONIO, LINGION | Provision of Potable Water Supply | 13025000 |  |  |  | 1 |  | 93.32% Physical Accomplishment | Ongoing cancellation | 2020-01-30
SUB-TOTAL |  |  | 14 |  |  | 19 | 112350000 | 3 | 0 | 0 | 1 | 15
2017 | REGION X | CAMIGUIN | GUINSILIBAN | LONE | BRGY. BUTAY & NORTH POBLACION | Provision of Potable Water Supply | 14001000 |  |  |  |  | 1 | Completed |  | 2020-06-26 | ENGR. ALPAS
2017 | REGION X | CAMIGUIN | MAHINOG | LONE | TAOCTAOC, TUPSAN PEQUEÑO- P500,000.00; SAN MIGUEL- P500,000.00; SAN ISIDRO- P500,000.00; OWAKAN- P500,000.00; PONTOD- 500,000.00; HUBANGON/ SAN JOSE- P3,172,000.00 | Provision of Potable Water Supply | 5672000 |  |  |  |  | 1 | Completed | TUPSAN PEQUEÑO (Completed as of 10-15-2018) swa | 2019-02-22
SAN MIGUEL, SAN ISIDRO (Completed as of 10-15-2018) swa
OWAKAN and PONTOD-100% (SWA)
HUBANGON/ SAN JOSE-100% (Completed as of 12-21-2018) (SWA)
2017 | REGION X | CAMIGUIN | MAMBAJAO (CAPITAL) | LONE | BRGY. AGOHO WATERWORKS | Provision of Potable Water Supply | 819000 |  |  |  |  | 1 | Completed | SWA | 2018-07-16
2017 | REGION X | CAMIGUIN | MAMBAJAO (CAPITAL) | LONE | BRGY. TAGDO WATERWORKS | Provision of Potable Water Supply | 1000000 |  |  |  |  | 1 | Completed | SWA | 2018-07-16
2017 | REGION X | CAMIGUIN | MAMBAJAO (CAPITAL) | LONE | BRGY. ANITO WATERWORKS | Provision of Potable Water Supply | 1000000 |  |  |  |  | 1 | Completed | SWA | 2018-08-07
2017 | REGION X | CAMIGUIN | MAMBAJAO (CAPITAL) | LONE | BRGY. SORO-SORO WATERWORKS | Provision of Potable Water Supply | 1000000 |  |  |  |  | 1 | Completed | SWA | 2018-07-16
2017 | REGION X | CAMIGUIN | MAMBAJAO (CAPITAL) | LONE | BRGY. NAASAG WATERWORKS | Provision of Potable Water Supply | 1000000 |  |  |  |  | 1 | Completed | SWA | 2018-07-16
2017 | REGION X | CAMIGUIN | MAMBAJAO (CAPITAL) | LONE | BRGY. BENHAAN WATERWORKS | Provision of Potable Water Supply | 1000000 |  |  |  |  | 1 | Completed | SWA | 2018-08-07 | CT
2017 | REGION X | CAMIGUIN | SAGAY | LONE | MAYANA, SAGAY | Provision of Potable Water Supply | 1953000 |  |  |  |  | 1 | Completed | SWA | 2018-05-23
SUB-TOTAL |  |  | 4 |  |  | 9 | 27445000 | 0 | 0 | 0 | 0 | 9
2017 | REGION X | LANAO DEL NORTE | KAUSWAGAN | 1ST | TACUB, KAUSWAGAN | Provision of Potable Water Supply | 925000 |  |  |  |  | 1 | Completed | SWA | 2018-08-22
2017 | REGION X | LANAO DEL NORTE | MAGSAYSAY | 2ND | BRGY BALAMISU/Talambo | Provision of Potable Water Supply | 4000000 |  |  |  |  | 1 | Completed | SWA | 2018-07-17
2017 | REGION X | LANAO DEL NORTE | NUNUNGAN | 2ND | BARANGAY MASIBAY | Provision of Potable Water Supply | 5000000 |  |  |  |  | 1 | Completed | SWA | 2017-10-19
2017 | REGION X | LANAO DEL NORTE | SULTAN NAGA DIMAPORO (KAROMATAN) | 2ND | BARANGAY PIKNIT, DANGOLAAN AND MAGUINDANAO | Provision of Potable Water Supply | 9369000 |  |  |  |  | 1 | Completed | Pikinit- COMPLETED | 2019-07-19 | CL
[14 empty] | Dangolaan- COMPLETED |  | CL
[14 empty] | Maguindanao- COMPLETED |  | CL
2017 | REGION X | LANAO DEL NORTE | SULTAN NAGA DIMAPORO (KAROMATAN) | 2ND | BARANGAY PAYONG, CALIBAO, BAUYAN AND BANGCO | Small Water Impounding Project (SWIP) | 3000000 |  |  |  |  | 1 | Completed | as of 4/16/2019 (SWA) | 2019-04-17
2017 | REGION X | LANAO DEL NORTE | TAGOLOAN | 1ST | BRGY INAGONGAN | Provision of Potable Water Supply | 6439000 | 1 |  |  |  |  | CANCELLED | Incompliant to Documentary Requirements/ No Release to LGU | 2018-08-03 | CP
2017 | REGION X | LANAO DEL NORTE | TUBOD (CAPITAL) | 1ST | BARANGAY TAGURANAO | Provision of Potable Water Supply | 1000000 |  |  |  |  | 1 | Completed | SWA | 2018-08-23
2017 | REGION X | LANAO DEL NORTE | TUBOD (CAPITAL) | 1ST | BARANGAY BULOD | Provision of Potable Water Supply | 2000000 |  |  |  |  | 1 | Completed | SWA | 2018-02-13
2017 | REGION X | LANAO DEL NORTE | TUBOD (CAPITAL) | 1ST | BARANGAY STO. NINO | Provision of Potable Water Supply | 1000000 |  |  |  |  | 1 | Completed | SWA | 2018-03-27
2017 | REGION X | LANAO DEL NORTE | TUBOD (CAPITAL) | 1ST | BARANGAY PALAO | Provision of Potable Water Supply | 1000000 |  |  |  |  | 1 | Completed | SWA | 2018-08-23
2017 | REGION X | LANAO DEL NORTE | TUBOD (CAPITAL) | 1ST | BARANGAY DALAMA | Provision of Potable Water Supply | 1500000 |  |  |  |  | 1 | Completed | SWA | 2018-08-23
2017 | REGION X | LANAO DEL NORTE | TUBOD (CAPITAL) | 1ST | BARANGAY PUALAS | Provision of Potable Water Supply | 1500000 |  |  |  |  | 1 | Completed | SWA | 1/29/2018
2017 | REGION X | LANAO DEL NORTE | TUBOD (CAPITAL) | 1ST | BARANGAY MALINGAO | Provision of Potable Water Supply | 1500000 |  |  |  |  | 1 | Completed | SWA | 2018-09-12
2017 | REGION X | LANAO DEL NORTE | TUBOD (CAPITAL) | 1ST | BARANGAY PATUDAN | Provision of Potable Water Supply | 2000000 |  |  |  |  | 1 | Completed | SWA | 2018-07-30
2017 | REGION X | LANAO DEL NORTE | TUBOD (CAPITAL) | 1ST | BARANAGAY SAN ANTONIO | Provision of Potable Water Supply | 900000 |  |  |  |  | 1 | Completed | SWA | 1/29/2018
2017 | REGION X | LANAO DEL NORTE | TUBOD (CAPITAL) | 1ST | BARANGAY PINPIN | Provision of Potable Water Supply | 1200000 |  |  |  |  | 1 | Completed | SWA | 2018-03-13
SUB-TOTAL |  |  | 6 |  |  | 16 | 42333000 | 1 | 0 | 0 | 0 | 15
2017 | REGION X | MISAMIS OCCIDENTAL | ALORAN | 1ST | TUBOD | Provision of Potable Water Supply | 10000000 |  |  |  |  | 1 | Completed | as of 6/28/2019 (SWA) | 2019-09-16
2017 | REGION X | MISAMIS OCCIDENTAL | ALORAN | 1ST | MAKAWA | Small Water Impounding Project (SWIP) | 2771907 |  |  |  |  | 1 | Completed | as of 7/31/2019 (SWA) | 2019-10-18
2017 | REGION X | MISAMIS OCCIDENTAL | BALIANGAO | 1ST | BRGY. DEL PILAR | Provision of Potable Water Supply | 500000 |  |  |  |  | 1 | Completed | as of 7/2019 (SWA) | 2019-07-17
2017 | REGION X | MISAMIS OCCIDENTAL | BALIANGAO | 1ST | BRGY. SINIAN | Provision of Potable Water Supply | 500000 |  |  |  |  | 1 | Completed | as of 7/2019 (SWA) | 2019-07-17
2017 | REGION X | MISAMIS OCCIDENTAL | BALIANGAO | 1ST | BRGY. LUMIPAC | Provision of Potable Water Supply | 500000 |  |  |  |  | 1 | Completed | as of 7/2019 (SWA) | 2019-07-17
2017 | REGION X | MISAMIS OCCIDENTAL | BALIANGAO | 1ST | BRGY. PUNTA SULONG | Provision of Potable Water Supply | 500000 |  |  |  |  | 1 | Completed | as of 7/2019 (SWA) | 2019-07-17
2017 | REGION X | MISAMIS OCCIDENTAL | CALAMBA | 1ST | BRGY. SILOY, BONIFACIO, MAUSWAGON, SALVADOR, DAPACAN ALTO & DON BERNARDO A. NERI (Brgy. Singalat) | Provision of Potable Water Supply | 5010000 |  |  |  |  | 1 | Completed | as of 3/8/2019 (SWA) | 2019-03-29
2017 | REGION X | MISAMIS OCCIDENTAL | JIMENEZ | 1ST | PUROK 1 TO 7, MATUGAS ALTO | Provision of Potable Water Supply | 2000000 |  |  |  |  | 1 | Completed |  | 2018-08-06 | MOT
2017 | REGION X | MISAMIS OCCIDENTAL | JIMENEZ | 1ST | PUROK 1 TO 4, MATUGAS BAJO | Provision of Potable Water Supply | 2000000 |  |  |  |  | 1 | Completed |  | 2018-08-06 | MOT
2017 | REGION X | MISAMIS OCCIDENTAL | PANAON | 1ST | BRGY. BAGA | Provision of Potable Water Supply | 500000 |  |  |  |  | 1 | Completed | AS OF 12/12/2019 SWA | 2020-01-02
2017 | REGION X | MISAMIS OCCIDENTAL | PANAON | 1ST | BRGY. CAMANUCAN (P-4) | Provision of Potable Water Supply | 500000 |  |  |  |  | 1 | Completed | as of 11-28-2018 (SWA) | 2019-02-07
2017 | REGION X | MISAMIS OCCIDENTAL | PANAON | 1ST | BRGY. MOHON | Provision of Potable Water Supply | 500000 |  |  |  |  | 1 | Completed | SWA | 2018-12-11
2017 | REGION X | MISAMIS OCCIDENTAL | PANAON | 1ST | BRGY. SAN ANDRES | Provision of Potable Water Supply | 500000 |  |  |  |  | 1 | Completed | as of 1-25-2019 (SWA) | 2019-02-07
2017 | REGION X | MISAMIS OCCIDENTAL | PANAON | 1ST | BRGY. MAGSAYSAY | Provision of Potable Water Supply | 500000 |  |  |  |  | 1 | Completed | as of 1-25-2019 (SWA) | 2019-02-07
2017 | REGION X | MISAMIS OCCIDENTAL | PANAON | 1ST | BRGY. SALIMPONO | Provision of Potable Water Supply | 500000 |  |  |  |  | 1 | Completed | AS OF 12/12/2019 SWA | 2020-01-02
2017 | REGION X | MISAMIS OCCIDENTAL | PLARIDEL | 1ST | BRGY. PANALSALAN- LOOC PROPER | Provision of Potable Water Supply | 6750000 |  |  |  |  | 1 | Completed | SWA | 2018-02-12
2017 | REGION X | MISAMIS OCCIDENTAL | PLARIDEL | 1ST | BRGY. NEW LOOK- BATO | Provision of Potable Water Supply | 1191907 |  |  |  |  | 1 | Completed | SWA | 2018-06-21
2017 | REGION X | MISAMIS OCCIDENTAL | SINACABAN | 2ND | BRGY. KATIPUNAN | Provision of Potable Water Supply | 2200000 |  |  |  |  | 1 | Completed |  | 2018-08-06 | MOT
2017 | REGION X | MISAMIS OCCIDENTAL | SINACABAN | 2ND | PUROK SAN JOSE, BRGY. POBLACION; SITIO BACOC, BRGY. ESTRELLA; PUROK MANGGA, BRGY. LIBERTAD BAJO; BRGY. SAN VICENTE; BRGY. DINAS; SITIO COMMONWEALTH, BRGY. COLUPAN ALTO; PUROK BOMBIL & PUROK GUMAMELA, COLUPAN BAJO; BRGY. SAN LORENZO RUIZ | Provision of Potable Water Supply | 3500000 |  |  |  |  | 1 | Completed | as of 7/15/2019 SWA | 7/23/2019
2017 | REGION X | MISAMIS OCCIDENTAL | SINACABAN | 2ND | PUROK DONYA TRINING, NEAR SINACABAN BIRTHING HOME | Provision of Potable Water Supply | 500000 |  |  |  |  | 1 | Completed | SWA | 2018-06-05
2017 | REGION X | MISAMIS OCCIDENTAL | SINACABAN | 2ND | POBLACION | Provision of Potable Water Supply | 2000000 |  |  |  |  | 1 | Completed | as of 5/30/2019 (SWA) | 2019-06-07
2017 | REGION X | MISAMIS OCCIDENTAL | SINACABAN | 2ND | ESTRELLA, DINAS, TIPAN, SAN LORENZO RUIZ, SAN ISIDRO ALTO, SAN ISIDRO BAJO | Provision of Potable Water Supply | 2500000 |  |  |  |  | 1 | Completed | UPDATE AS OF 3/12/2020 SWA | 2020-03-12
2017 | REGION X | MISAMIS OCCIDENTAL | SINACABAN | 2ND | LIBERTAD ALTO-LIBERTAD BAJO ROAD SECTION; SAN ISIDRO BAJO,-SENIOR- POBLACION ROAD SECTION; TIPAN-CAMANSE-SINONOC ROAD SECTION; DINAS-SAN VICENTE-ROAD SECTION | Provision of Potable Water Supply | 2237000 |  |  |  |  | 1 | Completed | SWA | 2018-07-27
2017 | REGION X | MISAMIS OCCIDENTAL | TUDELA | 2ND |  | Provision of Potable Water Supply | 10167000 |  |  |  |  | 1 | COMPLETED
[5 empty] | LOSOON | [8 empty] | Brgy. LOCSOON - 100% as of 8/13/2019 (SWA) | 2019-08-14
[5 empty] | CENTRO HULPA | [8 empty] | Brgy. CENTRO HULPA- 100% Physical Accomplishment as of 8/22/2019 (SWA) | 2019-09-09
[5 empty] | CANIBUNGAN PROPER | [8 empty] | Brgy. CANIBUNGAN-100% Physical Accomplishment as of 8/22/2019 (SWA) | 2019-09-09
[5 empty] | PAN-AY DIOT | [9 empty] | 2019-12-06 | CB
[5 empty] | TAGUIMA | [8 empty] | Brgy. Taguima- COMPLETED | 2020-01-31 | KCE
[5 empty] | UPPER CENTRO | [8 empty] | Brgy. Upper Centro- COMPLETED | 2020-01-31 | KCE
SUB-TOTAL |  |  | 8 |  |  | 24 | 57827814 | 0 | 0 | 0 | 0 | 24
2017 | REGION X | MISAMIS ORIENTAL | BALINGASAG | 1ST | BRGY. LINABU | Provision of Potable Water Supply | 3336000 |  |  |  |  | 1 | Completed | as of 5/15/2019 (SWA) | 2019-06-18
2017 | REGION X | MISAMIS ORIENTAL | BINUANGAN | 1ST | SOURCE IS AT SITIO KUMGAYKAY OF BRGY. KITAMBAN & SERVED TO BRGY. POBLACION | Provision of Potable Water Supply | 3743907 |  |  |  |  | 1 | Completed | as of 6/18/2019 (SWA) | 2019-06-28
2017 | REGION X | MISAMIS ORIENTAL | CLAVERIA | 2ND | BRGY. MALAGANA, MINALWANG & PUNONG | Provision of Potable Water Supply | 2000000 |  |  |  |  | 1 | Completed | SWA | 12/19/2018 | NP
2017 | REGION X | MISAMIS ORIENTAL | CLAVERIA | 2ND | BRGY. PATROCINIO | Provision of Potable Water Supply | 2000000 |  |  |  |  | 1 | Completed |  | 12/19/2018 | NP
2017 | REGION X | MISAMIS ORIENTAL | JASAAN | 2ND | BRGY. CORRALES & BRGY. APLAYA | Provision of Potable Water Supply | 15203000 |  |  |  |  | 1 | Completed |  | 2019-10-29 | NPJR
2017 | REGION X | MISAMIS ORIENTAL | KINOGUITAN | 1ST | MUNICIPAL WIDE | Provision of Potable Water Supply | 22174907 |  |  |  |  | 1 | Completed | AS OF JULY 4, 2019 SWA | 2020-02-28
2017 | REGION X | MISAMIS ORIENTAL | LAGUINDINGAN | 2ND | GK HEIGHTS RELOCATION SITE, BRGY. KIBAGHOT | Provision of Potable Water Supply | 2000000 |  |  |  |  | 1 | Completed | SWA | 2018-05-31
2017 | REGION X | MISAMIS ORIENTAL | LAGUINDINGAN | 2ND | GK DIAMOND RELOCATION SITE, BRGY. KIBAGHOT | Provision of Potable Water Supply | 2000000 |  |  |  |  | 1 | Completed |  | 10/25/2018 | ME
2017 | REGION X | MISAMIS ORIENTAL | LAGUINDINGAN | 2ND | SITIO MAGSAYSAY-SALCEDO, POBLACION | Provision of Potable Water Supply | 1168000 |  |  |  |  | 1 | Completed | SWA | 2018-05-31
2017 | REGION X | MISAMIS ORIENTAL | LUGAIT | 2ND | POBLACION, BIGA & CALANGAHAN | Provision of Potable Water Supply | 5500000 |  |  |  |  | 1 | Completed | SWA | 2018-04-12
2017 | REGION X | MISAMIS ORIENTAL | MAGSAYSAY (LINUGOS) | 1ST | BRGY. CABANTIAN-KIBUNGSOD | Provision of Potable Water Supply | 10075000 |  |  |  |  | 1 | Completed |  | 12/19/2018 | NP
2017 | REGION X | MISAMIS ORIENTAL | MAGSAYSAY (LINUGOS) | 1ST | BRGY. SAN VICENTE | Provision of Potable Water Supply | 3900000 |  |  |  |  | 1 | Completed |  | 10/25/2018 | ME
2017 | REGION X | MISAMIS ORIENTAL | MANTICAO | 2ND | BRGYS. CABALANTIAN, PANLANGAN & POBLACION | Provision of Potable Water Supply | 13525000 |  |  |  |  | 1 | Completed | as of 5/17/2019 (SWA) | 2019-05-22
2017 | REGION X | MISAMIS ORIENTAL | MEDINA | 1ST | BRGY. BULWA | Provision of Potable Water Supply | 7000000 |  |  |  |  | 1 | Completed | as of 5/23/2019 (SWA) | 2019-05-28
2017 | REGION X | MISAMIS ORIENTAL | MEDINA | 1ST | BRGY. TUP-ON | Provision of Potable Water Supply | 6839000 |  |  |  |  | 1 | Completed | as of 5/23/2019 (SWA) | 2019-05-28
2017 | REGION X | MISAMIS ORIENTAL | NAAWAN | 2ND | BRGYS. MAPULOG & LINANGKAYAN; BRGYS. TAGBALOGO, MAT-I, TUBORAN, PATAG, MAPULOG, & DON PEDRO; BRGY PATAG & MAPUTI | Provision of Potable Water Supply | 22615907 |  |  |  |  | 1 | Completed | AS OF FEB. 20, 2020 SWA | 2020-03-06
2017 | REGION X | MISAMIS ORIENTAL | SUGBONGCOGON | 1ST | BRGY. KAULAYANAN, KIDAMPAS, AMPIANGA & MIMBUAHAN | Provision of Potable Water Supply | 3828000 |  |  |  |  | 1 | COMPLETED | SWA | 2019-02-04
2017 | REGION X | MISAMIS ORIENTAL | SUGBONGCOGON | 1ST | BRGY. POBLACION, MANGGA, SILAD, KIRAGING, ALICOMOHAN AND STA. CRUZ | Provision of Potable Water Supply | 2000000 |  |  |  |  | 1 | COMPLETED | SWA | 2019-02-04
2017 | REGION X | MISAMIS ORIENTAL | TAGOLOAN | 2ND | BRGY. CASINGLOT | Provision of Potable Water Supply | 8190000 |  |  |  | 1 |  | 90% Physical Accomplishment | on going implementation | 2019-12-06 | NP
2017 | REGION X | MISAMIS ORIENTAL | TAGOLOAN | 2ND | BRGY. MOHON | Provision of Potable Water Supply | 8000000 | 1 |  |  |  |  | CANCELLED | Reverted and remitted the unutilized fund to the Bureau of the Treasury | 2019-12-03
2017 | REGION X | MISAMIS ORIENTAL | TALISAYAN | 1ST | CABALAWAN, MINTABON, GUIWANON, POBLACION | Provision of Potable Water Supply | 10000000 |  |  |  |  | 1 | COMPLETED | AS OF NOVEMBER 2019 SWA | 2019-12-27
2017 | REGION X | MISAMIS ORIENTAL | VILLANUEVA | 2ND | SOURCE- NAPAPONG SPRING, BENEFICIARIES- BRGY. KATIPUNAN, DAYAWAN, TAMBOBONG, BALACANAS & BRGY. SAN MARTIN | Provision of Potable Water Supply | 13898000 |  |  |  |  | 1 | COMPLETED | PER ENGR. PUIG | 2020-06-23 | NP
SUB-TOTAL |  |  | 15 |  |  | 22 | 168996721 | 1 | 0 | 0 | 1 | 20
GRAND TOTAL |  |  | 47 |  |  | 90 | 408952535 | 5 | 0 | 0 | 2 | 83

## 2018 AM-Others
REGION X - AM
2018 AM-OTHERS
as of June 26, 2020
FY | REGION | PROVINCE | CITY / MUNICIPALITY | NAME OF PROJECT | PHYSICAL TARGETS/OUTPUTS | BARANGAY | ORIGINAL ALLOCATION | CANCELLED | APPROVED DED/POW or DED PREP. | PROCUREMENT | ON-GOING | COMPLETED | STATUS | REMARKS | DATE UPDATED |  | SUBMITTED ON-TIME (SWA)
2018 | REGION X | BUKIDNON | CABANGLASAN | LOCAL ACCESS ROAD | LOCAL ROAD UPGRADING | MANDAING | 6659107.4 |  |  |  |  | 1 | COMPLETED | SWA WITH 100% PHYSICAL ACCOMPLISHMENT AS OF SEPT. 30, 2019 | 2019-10-30 |  | -
2018 | REGION X | BUKIDNON | DAMULOG | LOCAL ACCESS ROAD | LOCAL ROAD UPGRADING | AGUINALDO STREET JCT. BONIFACIO STREET TO JCT. MANLABAO STREET, POBLACION | 3000000 |  |  |  |  | 1 | COMPLETED | SWA | 2019-03-04 |  | -
2018 | REGION X | BUKIDNON | DAMULOG | LOCAL ACCESS ROAD | LOCAL ROAD UPGRADING | C.M. RECTO STREET JCT. MANLABAO STREET TO SAN ISIDRO STREET | 2500381.09 |  |  |  |  | 1 | COMPLETED | SWA | 2019-03-04 |  | -
2018 | REGION X | BUKIDNON | DANGCAGAN | LOCAL ACCESS ROAD | LOCAL ROAD UPGRADING | MIARAY-TAGONGTONG | 3600000 |  |  |  |  | 1 | COMPLETED | as of 3/8/2019 (SWA) | 2019-03-13 |  | -
2018 | REGION X | BUKIDNON | DANGCAGAN | LOCAL ACCESS ROAD | LOCAL ROAD UPGRADING | KIANGGAT-SAN VICENTE | 3641583.83 |  |  |  |  | 1 | COMPLETED | as of January 24, 2019 (SWA) | 2019-03-14 |  | -
2018 | REGION X | BUKIDNON | DON CARLOS | LOCAL ACCESS ROAD | LOCAL ROAD UPGRADING | DON CARLOS SUR | 7916368.68 |  |  |  |  | 1 | COMPLETED | as of 7/24/2019 (SWA) | 7/25/2019 |  | -
2018 | REGION X | BUKIDNON | IMPASUG-ONG | LOCAL ACCESS ROAD | LOCAL ROAD UPGRADING | SITIO QUISUMBING, IMPALUTAO, IMPASUG-ONG, BUKDINON | 6211221.49 |  |  |  |  | 1 | COMPLETED | Turn over last January 29, 2019 | 2019-02-18 | fcla | -
2018 | REGION X | BUKIDNON | KADINGILAN | LOCAL ACCESS ROAD | LOCAL ROAD UPGRADING | BARANGAY PAY-AS | 5745366.18 |  |  |  |  | 1 | COMPLETED | AS OF 8/20/2019 SWA | 2020-01-31 |  | -
2018 | REGION X | BUKIDNON | KIBAWE | LOCAL ACCESS ROAD | LOCAL ROAD UPGRADING | JUNCTION BARANGAY OLD KIBAWE NATIONAL HIGHWAY - SITIO GRECAN, BARANGAY OLD KIBAWE | 5903208.92 |  |  |  |  | 1 | COMPLETED | as of 6/3/2019 (SWA) | 2019-06-18 |  | -
2018 | REGION X | BUKIDNON | LIBONA | LOCAL ACCESS ROAD | LOCAL ROAD REHABILITATION/IMPROVEMENT | PUROK 1, PUROK 4, POBLACION | 8797109.25 |  |  |  |  | 1 | COMPLETED | SWA | 2019-03-19 |  | -
2018 | REGION X | BUKIDNON | MALITBOG | LOCAL ACCESS ROAD | LOCAL ROAD UPGRADING | POBLACION-MINDAGAT | 5395700.66 |  |  |  |  | 1 | COMPLETED | as of 10/2/2019 SWA; 11/22/2019 PROJECT INSPECTION REPORT | 2020-01-09 |  | -
2018 | REGION X | BUKIDNON | MARAMAG | LOCAL ACCESS ROAD | LOCAL ROAD UPGRADING | NORTH POBLACION | 5575122.66 |  |  |  |  | 1 | COMPLETED | AS OF 04/27/2020 SWA | 2020-04-30 |  | 0
2018 | REGION X | BUKIDNON | PANGANTUCAN | LOCAL ACCESS ROAD | LOCAL ROAD REHABILITATION/IMPROVEMENT | CONCEPCION | 3207824.89 |  |  |  |  | 1 | COMPLETED | AS OF 9/27/2019 SWA | 2019-09-16 |  | -
2018 | REGION X | BUKIDNON | PANGANTUCAN | LOCAL ACCESS ROAD | LOCAL ROAD REHABILITATION/IMPROVEMENT | NEW EDEN | 3207824.88 |  |  |  |  | 1 | COMPLETED | AS OF 9/27/2019 SWA | 2020-01-27 |  | -
2018 | REGION X | BUKIDNON | QUEZON | LOCAL ACCESS ROAD | LOCAL ROAD UPGRADING | POBLACION | 9108410.22 |  |  |  |  | 1 | COMPLETED | Turn over last February 13, 2019 | 2019-02-18 | fcla | -
2018 | REGION X | BUKIDNON | SUMILAO | LOCAL ACCESS ROAD | LOCAL ROAD UPGRADING | BARANGAY LUPIAGAN | 7368734.93 |  |  |  |  | 1 | COMPLETED | AS OF DECEMBER19, 2019 SWA | 2019-12-06 | JKB | 0
2018 | REGION X | BUKIDNON | TALAKAG | LOCAL ACCESS ROAD | LOCAL ROAD UPGRADING | SITIO BABALAYAN-SITIO BATANG ROAD BRGY COSINA | 7138547.6 |  |  |  |  | 1 | COMPLETED | AS OF DECEMBER 2019 SWA | 2020-01-10 |  | -
SUB-TOTAL (LAR) BUKIDNON: |  |  | 14 | 17 |  |  | 94976512.68 | 0 | 0 | 0 | 0 | 17
2018 | REGION X | BUKIDNON | MANOLO FORTICH | PROVISION OF SANITARY TOILET AND HYGIENE FACILITIES | CONSTRUCTION OF SANITARY TOILET WITH HYGIENE FACILITIES FOR PUBLIC PLACES | TANKULAN | 1500000 |  |  |  |  | 1 | COMPLETED | as of 5/30/2019 (SWA) | 2019-06-10 |  | -
2018 | REGION X | BUKIDNON | MARAMAG | LOCAL BRIDGES | LOCAL BRIDGE CONSTRUCTION | NORTH POBLACION | 10000000 |  |  |  |  | 1 | COMPLETED | AS OF 1/20/2020 SWA | 2020-01-27 |  | -
SUB-TOTAL (OTHERS) BUKIDNON: |  |  | 1 | 2 |  |  | 11500000 | 0 | 0 | 0 | 0 | 2
TOTAL (OTHERS+LAR) BUKIDNON |  |  | 15 | 19 |  |  | 106476512.68 | 0 | 0 | 0 | 0 | 19
2018 | REGION X | CAMIGUIN | CATARMAN | LOCAL ACCESS ROAD | LOCAL ROAD UPGRADING | MANDUAO | 5139754.27 |  |  |  |  | 1 | COMPLETED | as of 4/15/2019 (SWA) | 2019-04-25 |  | -
2018 | REGION X | CAMIGUIN | GUINSILIBAN | LOCAL ACCESS ROAD | LOCAL ROAD OPENING | NATIONAL HIGHWAY, SOUTH POBLACION TO KIWAKAT | 7673459.11 |  |  |  |  | 1 | COMPLETED |  | 2020-06-26 | engr.alpas | 1
2018 | REGION X | CAMIGUIN | MAHINOG | LOCAL ACCESS ROAD | LOCAL ROAD UPGRADING | TACANGON, POBLACION | 750000 |  |  |  |  | 1 | COMPLETED | as of 3/25/2019 (SWA) | 2019-04-15 |  | -
2018 | REGION X | CAMIGUIN | MAHINOG | LOCAL ACCESS ROAD | LOCAL ROAD UPGRADING | BRHP, BENONI | 750000 |  |  |  |  | 1 | COMPLETED | SWA | 2019-02-22 |  | -
2018 | REGION X | CAMIGUIN | MAHINOG | LOCAL ACCESS ROAD | LOCAL ROAD UPGRADING | HUBANGON | 1000000 |  |  |  |  | 1 | COMPLETED | as of 1/11/2019 (SWA) | 2019-04-15 |  | -
2018 | REGION X | CAMIGUIN | MAHINOG | LOCAL ACCESS ROAD | LOCAL ROAD UPGRADING | BENONI | 1026852.87 |  |  |  |  | 1 | COMPLETED | SWA | 2019-02-22 |  | -
2018 | REGION X | CAMIGUIN | MAHINOG | LOCAL ACCESS ROAD | LOCAL ROAD OPENING | POBLACION | 1500000 |  |  |  |  | 1 | COMPLETED | as of 3/22/2019 (SWA) | 2019-04-15 |  | -
2018 | REGION X | CAMIGUIN | MAMBAJAO (Capital) | LOCAL ACCESS ROAD | LOCAL ROAD UPGRADING | GOVERNMENT CENTER, LACAS, POBLACION | 5378737.14 |  |  |  |  | 1 | COMPLETED | as of 11/25/2019 SWA | 2019-12-17 |  | -
2018 | REGION X | CAMIGUIN | SAGAY | LOCAL ACCESS ROAD | LOCAL ROAD UPGRADING | BRGY. MAYANA | 4000000 |  |  |  |  | 1 | COMPLETED | as of 2/15/2019 (SWA) | 2019-02-27 |  | -
SUB-TOTAL (LAR) CAM.: |  |  | 5 | 9 |  |  | 27218803.39 | 0 | 0 | 0 | 0 | 9
2018 | REGION X | CAMIGUIN | MAMBAJAO (Capital) | DRR RESCUE EQUIPMENT | DRR EQUIPMENT | MAMBAJAO, CAMIGUIN | 1438213 |  |  |  |  | 1 | COMPLETED | PURCHASE ORDER, ACCEPTANCE AND INSPECTION REPORT | 2019-10-09 |  | -
SUB-TOTAL (OTHERS) CAM.: |  |  |  | 1 |  |  | 1438213 | 0 | 0 | 0 | 0 | 1
TOTAL (OTHERS+LAR) CAMIGUIN: |  |  | 5 | 10 |  |  | 28657016.39 | 0 | 0 | 0 | 0 | 10
2018 | REGION X | LANAO DEL NORTE | BACOLOD | LOCAL ACCESS ROAD | LOCAL ROAD UPGRADING | BABALAYA | 5353499.65 |  |  |  |  | 1 | COMPLETED | as of February 2019 (SWA) | 2019-04-24 |  | -
2018 | REGION X | LANAO DEL NORTE | BALOI | LOCAL ACCESS ROAD | LOCAL ROAD UPGRADING | BARANGAY ABAGA | 3239612.66 |  |  |  |  | 1 | COMPLETED |  | 2019-04-01 | ND | -
2018 | REGION X | LANAO DEL NORTE | BALOI | LOCAL ACCESS ROAD | LOCAL ROAD UPGRADING | BRGY. CORMATAN TO SIGAYAN | 3239612.65 |  |  |  |  | 1 | COMPLETED |  | 2019-04-01 | ND | -
2018 | REGION X | LANAO DEL NORTE | BAROY | LOCAL ACCESS ROAD | LOCAL ROAD UPGRADING | PUROK 2 & 3, MALIWANAG | 6638307.23 |  |  |  |  | 1 | COMPLETED | as of 7/21/2019 (SWA) | 2019-03-07 |  | -
2018 | REGION X | LANAO DEL NORTE | KAPATAGAN | LOCAL ACCESS ROAD | LOCAL ROAD OPENING | POBLACION | 14117817.62 |  |  |  |  | 1 | COMPLETED | SWA | 2019-04-22 |  | -
2018 | REGION X | LANAO DEL NORTE | KAUSWAGAN | LOCAL ACCESS ROAD | LOCAL ROAD UPGRADING | KAWIT ORIENTAL | 1000000 |  |  |  |  | 1 | COMPLETED | SWA | 2019-02-22 |  | -
2018 | REGION X | LANAO DEL NORTE | KAUSWAGAN | LOCAL ACCESS ROAD | LOCAL ROAD UPGRADING | KAWIT OCCIDENTAL | 1000000 |  |  |  |  | 1 | COMPLETED | Monthly Meeting | 2019-03-08 |  | -
2018 | REGION X | LANAO DEL NORTE | KAUSWAGAN | LOCAL ACCESS ROAD | LOCAL ROAD UPGRADING | POBLACION | 1000000 |  |  |  |  | 1 | COMPLETED | SWA | 2019-02-22 |  | -
2018 | REGION X | LANAO DEL NORTE | KOLAMBUGAN | LOCAL ACCESS ROAD | LOCAL ROAD UPGRADING | INUDARAN | 12147954.46 |  |  |  |  | 1 | COMPLETED | as of 4/9/2019 (SWA) | 2019-04-23 |  | -
2018 | REGION X | LANAO DEL NORTE | LALA | LOCAL ACCESS ROAD | LOCAL ROAD UPGRADING | REBE | 9275165.59 |  |  |  |  | 1 | COMPLETED |  | 2019-03-04 | nd | -
2018 | REGION X | LANAO DEL NORTE | LINAMON | LOCAL ACCESS ROAD | LOCAL ROAD UPGRADING | BARANGAY MAG-ONG | 4500000 |  |  |  |  | 1 | COMPLETED | SWA | 2019-06-20 |  | -
2018 | REGION X | LANAO DEL NORTE | LINAMON | LOCAL ACCESS ROAD | LOCAL ROAD UPGRADING | BARANGAY BOSQUE | 4500000 |  |  |  |  | 1 | COMPLETED | SWA | 2019-02-04 |  | -
2018 | REGION X | LANAO DEL NORTE | LINAMON | LOCAL ACCESS ROAD | LOCAL ROAD UPGRADING | BARANGAY ROBOCON | 3158421.8 |  |  |  |  | 1 | COMPLETED | Monthly Meeting | 2019-03-08 |  | -
2018 | REGION X | LANAO DEL NORTE | MAGSAYSAY | LOCAL ACCESS ROAD | LOCAL ROAD UPGRADING | POBLACION TO LEMONCRET | 5141946.53 |  |  |  |  | 1 | COMPLETED | as of 3/12/2019 (SWA) | 2019-03-25 |  | -
2018 | REGION X | LANAO DEL NORTE | MAIGO | LOCAL ACCESS ROAD | LOCAL ROAD UPGRADING | BALAGATASA | 5287183.78 |  |  |  |  | 1 | COMPLETED | as of 4/22/2019 (SWA) | 2019-04-26 |  | -
2018 | REGION X | LANAO DEL NORTE | MATUNGAO | LOCAL ACCESS ROAD | LOCAL ROAD UPGRADING | BRGY. BATANGAN | 4975334.75 |  |  |  |  | 1 | COMPLETED | Monthly Meeting | 2019-03-08 |  | -
2018 | REGION X | LANAO DEL NORTE | MUNAI | LOCAL ACCESS ROAD | LOCAL ROAD UPGRADING | PANGGAO-TAMPARAN | 5581494.72 |  |  |  | 1 |  | 23.91% Physical Accomplishment | AS OF 04/15/2020 SWA ongoing implementation | 2020-05-05 |  | 0
2018 | REGION X | LANAO DEL NORTE | PANTAO RAGAT | LOCAL ACCESS ROAD | LOCAL ROAD UPGRADING | BARANGAY CABASAGAN | 5405017.77 |  |  |  |  | 1 | COMPLETED | as of 3/12/2019 (SWA) | 2019-03-26 |  | -
2018 | REGION X | LANAO DEL NORTE | PANTAR | LOCAL ACCESS ROAD | LOCAL ROAD REHABILITATION/IMPROVEMENT | LUMBA PUNOD TO SUNDIGA PUNOD | 4402528.71 |  |  |  |  | 1 | COMPLETED | SWA | 2018-09-11 |  | -
2018 | REGION X | LANAO DEL NORTE | POONA PIAGAPO | LOCAL ACCESS ROAD | LOCAL ROAD UPGRADING | BRGY. NUNANG TO BRGY. POBLACION | 5418171.33 |  |  |  | 1 |  | 37.76% Physical Accomplishment | AS OF 1/15/2020 SWA ongoing cancellation | 2020-06-26 |  | 0
2018 | REGION X | LANAO DEL NORTE | SALVADOR | LOCAL ACCESS ROAD | LOCAL ROAD UPGRADING | BARANGAY PADIANAN | 6890417.17 |  |  |  |  | 1 | COMPLETED | 2019-03-25 | 2019-04-24 | CL | -
2018 | REGION X | LANAO DEL NORTE | SAPAD | LOCAL ACCESS ROAD | LOCAL ROAD REHABILITATION/IMPROVEMENT | BARANGAY PANOLOON TO BARANGAY KATIPUNAN | 6580212.33 |  |  |  |  | 1 | COMPLETED | SWA | 12/21/2018 |  | -
2018 | REGION X | LANAO DEL NORTE | TAGOLOAN | LOCAL ACCESS ROAD | LOCAL ROAD UPGRADING | BRGY. KIAZAR | 6817381.47 | 1 |  |  |  |  | CANCELLED | No download/no GFH Passer | 2019-03-04 | nd | -
2018 | REGION X | LANAO DEL NORTE | TANGCAL | LOCAL ACCESS ROAD | LOCAL ROAD UPGRADING | BARANGAY BUBONG TO LINAO | 4990132.51 |  |  |  |  | 1 | COMPLETED | as of 6/20/2019 (SWA) | 2019-07-03 |  | -
2018 | REGION X | LANAO DEL NORTE | TUBOD | LOCAL ACCESS ROAD | LOCAL ROAD OPENING | POBLACION (Legaspi - Gom-os) | 12931687.52 |  |  |  |  | 1 | COMPLETED | as of 4/22/2019 (SWA) | 2019-04-23 |  | -
SUB-TOTAL (LAR) LDN: |  |  | 20 | 24 |  |  | 143591900.25 | 1 | 0 | 0 | 2 | 22
2018 | REGION X | LANAO DEL NORTE | KAUSWAGAN | MUNICIPAL DRUG REHABILITATION FACILITY | REHABILITATION/IMPROVEMENT OF EXISTING BUILDING TO A MUNICIPAL DRUG REHABILITATION FACILITY | UPPER BAGUMBAYAN | 2000000 |  |  |  |  | 1 | COMPLETED | as of 3/5/2019 (SWA) | 2019-04-02 |  | -
2018 | REGION X | LANAO DEL NORTE | LINAMON | DRR RESCUE EQUIPMENT | DRR EQUIPMENT | DRRMO/POBLACION | 500000 |  |  |  |  | 1 | COMPLETED |  | 2019-07-19 | CL | -
2018 | REGION X | LANAO DEL NORTE | LINAMON | EVACUATION CENTER | IMPROVEMENT/REHABILITATION OF EVACUATION CENTER | POBLACION | 1000000 |  |  |  |  | 1 | COMPLETED | Monthly Meeting | 2019-03-08 |  | -
2018 | REGION X | LANAO DEL NORTE | NUNUNGAN | LOCAL BRIDGES | LOCAL BRIDGE CONSTRUCTION | BARANGAY RABARAN | 3000000 |  |  |  |  | 1 | COMPLETED | Monthly Meeting | 2019-03-08 |  | -
2018 | REGION X | LANAO DEL NORTE | SULTAN NAGA DIMAPORO | DRR RESCUE EQUIPMENT | DRR EQUIPMENT | SND, LDN | 600000 |  |  |  |  | 1 | COMPLETED |  | 2019-09-09 | nd | -
SUB-TOTAL (OTHERS) LDN: |  |  | 2 | 5 |  |  | 7100000 | 0 | 0 | 0 | 0 | 5
TOTAL (OTHERS+LAR) LANAO DEL NORTE: |  |  | 22 | 29 |  |  | 150691900.25 | 1 | 0 | 0 | 2 | 27
2018 | REGION X | MISAMIS OCCIDENTAL | ALORAN | LOCAL ACCESS ROAD | LOCAL ROAD UPGRADING | BRGY. TUBURAN | 12155079.3 |  |  |  |  | 1 | COMPLETED | UPDATE AS OF 1/30/2020 MONTHLY MEETING | 2020-01-31 |  | 0
2018 | REGION X | MISAMIS OCCIDENTAL | BALIANGAO | LOCAL ACCESS ROAD | LOCAL ROAD UPGRADING | BRGY. MISOM - BPLS ROAD | 5130437.17 |  |  |  |  | 1 | COMPLETED | as of 2/2019 (SWA) | 2019-05-03 |  | -
2018 | REGION X | MISAMIS OCCIDENTAL | BONIFACIO | LOCAL ACCESS ROAD | LOCAL ROAD UPGRADING | BOLINSONG | 7030173.76 |  |  |  |  | 1 | COMPLETED | SWA | 12/20/2018 |  | -
2018 | REGION X | MISAMIS OCCIDENTAL | CALAMBA | LOCAL ACCESS ROAD | LOCAL ROAD REHABILITATION/IMPROVEMENT | BARANGAY LIBERTAD | 6209145.97 |  |  |  |  | 1 | COMPLETED | as of 3/28/2019 (SWA) | 2019-03-29 |  | -
2018 | REGION X | MISAMIS OCCIDENTAL | CLARIN | LOCAL ACCESS ROAD | LOCAL ROAD UPGRADING | SEGATIC DAKU AND CABUNGA-AN | 6782970.1 |  |  |  |  | 1 | COMPLETED | as of 2/7/2019 (SWA) | 2/18/019 | cb | -
2018 | REGION X | MISAMIS OCCIDENTAL | CONCEPCION | LOCAL ACCESS ROAD | LOCAL ROAD REHABILITATION/IMPROVEMENT | BRGY. NEW CASUL | 7745255.64 | 1 |  |  |  |  | CANCELLED |  | 2020-01-10 | cb | -
2018 | REGION X | MISAMIS OCCIDENTAL | DON VICTORIANO CHIONGBIAN (DON MARIANO MARCOS) | LOCAL ACCESS ROAD | LOCAL ROAD UPGRADING | PUROK 5, LALUD | 4878875.3 |  |  |  |  | 1 | COMPLETED | as of 6/27/2019 (SWA) | 2019-09-09 |  | -
2018 | REGION X | MISAMIS OCCIDENTAL | LOPEZ JAENA | LOCAL ACCESS ROAD | LOCAL ROAD UPGRADING | BRGY. RIZAL | 5430228.76 |  |  |  |  | 1 | COMPLETED | as of 5/22/2019 (SWA) | 2019-06-24 |  | -
2018 | REGION X | MISAMIS OCCIDENTAL | PANAON | LOCAL ACCESS ROAD | LOCAL ROAD UPGRADING | BRGY. SAN ROQUE | 4400000 |  |  |  |  | 1 | COMPLETED | 4/29/2019 SWA | 2019-08-01 |  | -
2018 | REGION X | MISAMIS OCCIDENTAL | PANAON | LOCAL ACCESS ROAD | LOCAL ROAD REHABILITATION/IMPROVEMENT | BRGY. PUNTA | 4341754.68 |  |  |  |  | 1 | COMPLETED | 4/25/2019 SWA | 2019-08-01 |  | -
2018 | REGION X | MISAMIS OCCIDENTAL | PLARIDEL | LOCAL ACCESS ROAD | LOCAL ROAD REHABILITATION/IMPROVEMENT | SITIO TAGAYTAY - BRGY. DIVISORIA | 5494879.65 |  |  |  |  | 1 | COMPLETED |  | 2019-02-18 | CB | -
2018 | REGION X | MISAMIS OCCIDENTAL | PLARIDEL | LOCAL ACCESS ROAD | LOCAL ROAD REHABILITATION/IMPROVEMENT | PUROK PARPAGAYO - BRGY. LAO PROPER | 7000000 |  |  |  |  | 1 | COMPLETED |  | 2019-02-18 | CB | -
2018 | REGION X | MISAMIS OCCIDENTAL | SAPANG DALAGA | LOCAL ACCESS ROAD | LOCAL ROAD UPGRADING | SALIMPUNO TO CAPUNDAG ROAD SECTION | 11871729.66 |  |  |  |  | 1 | COMPLETED | as of 6/20/2019 (SWA) | 2019-06-27 |  | -
2018 | REGION X | MISAMIS OCCIDENTAL | SINACABAN | LOCAL ACCESS ROAD | LOCAL ROAD REHABILITATION/IMPROVEMENT | LIBERTAD ALTO | 7977751.97 |  |  |  |  | 1 | COMPLETED | SWA | 2019-02-22 |  | -
2018 | REGION X | MISAMIS OCCIDENTAL | TUDELA | LOCAL ACCESS ROAD | LOCAL ROAD UPGRADING | YAHONG | 6890965.23 |  |  |  |  | 1 | COMPLETED | as of 12/5/2018 (SWA) | 2019-06-24 |  | -
TOTAL (LAR) MISAMIS OCCIDENTAL: |  |  | 13 | 14 |  |  | 103339247.19 | 1 | 0 | 0 | 0 | 14
2018 | REGION X | MISAMIS ORIENTAL | ALUBIJID | LOCAL ACCESS ROAD | LOCAL ROAD UPGRADING | BARANGAY LOGUILO | 7407099.49 |  |  |  |  | 1 | COMPLETED | AS OF 12/13/2019 SWA;FOR FINAL INSPECTION | 2019-12-24 |  | -
2018 | REGION X | MISAMIS ORIENTAL | BALINGASAG | LOCAL ACCESS ROAD | LOCAL ROAD UPGRADING | SITIO VENCER, BARANGAY COGON | 8953191.06 |  |  |  |  | 1 | COMPLETED | SWA | 2019-03-20 |  | -
2018 | REGION X | MISAMIS ORIENTAL | CLAVERIA | LOCAL ACCESS ROAD | LOCAL ROAD UPGRADING | SITIO IMPAKIBIL, APOSKAHOY | 8112459.24 |  |  |  |  | 1 | COMPLETED | as of 7/9/2019 SWA | 7/24/2019 |  | -
2018 | REGION X | MISAMIS ORIENTAL | GITAGUM | LOCAL ACCESS ROAD | LOCAL ROAD UPGRADING | PUROK 6, G.PELAEZ | 6991666.16 |  |  |  |  | 1 | COMPLETED | SWA | 2019-02-06 |  | -
2018 | REGION X | MISAMIS ORIENTAL | KINOGUITAN | LOCAL ACCESS ROAD | LOCAL ROAD UPGRADING | BRGY. CALUBO TO BRGY. KITOTOK ROAD | 4000000 |  |  |  |  | 1 | COMPLETED | PER ENGR. PUIG | 2020-06-23 | npj | 0
2018 | REGION X | MISAMIS ORIENTAL | LAGONGLONG | LOCAL ACCESS ROAD | LOCAL ROAD UPGRADING | SAPONG-AGONG GAMAY TABOK | 3558860.57 |  |  |  |  | 1 | COMPLETED | as of 12/31/2018 (SWA) | 2019-04-03 |  | -
2018 | REGION X | MISAMIS ORIENTAL | LAGONGLONG | LOCAL ACCESS ROAD | LOCAL ROAD UPGRADING | SAPONG, TABOK | 3558860.56 |  |  |  |  | 1 | COMPLETED | as of 12/27/2018 (SWA) | 2019-04-03 |  | -
2018 | REGION X | MISAMIS ORIENTAL | LIBERTAD | LOCAL ACCESS ROAD | LOCAL ROAD UPGRADING | PUROK 10 (TAMBO), BRGY. POBLACION | 8132332.62 |  |  |  |  | 1 | COMPLETED | as of 7/22/2019 (SWA) | 2019-08-12 |  | -
2018 | REGION X | MISAMIS ORIENTAL | MAGSAYSAY (LINUGOS) | LOCAL ACCESS ROAD | LOCAL ROAD UPGRADING | CABUBUHAN-KAUSWAGAN | 7659209.42 |  |  |  |  | 1 | COMPLETED | as of 6/26/2019 (SWA) | 2016-07-10 |  | -
2018 | REGION X | MISAMIS ORIENTAL | MEDINA | LOCAL ACCESS ROAD | LOCAL ROAD UPGRADING | P-2 TO P-3, BRGY. ROAD, SAN JOSE | 3984672.57 |  |  |  |  | 1 | COMPLETED | as of 5/23/2019 (SWA) | 2019-05-28 |  | -
2018 | REGION X | MISAMIS ORIENTAL | MEDINA | LOCAL ACCESS ROAD | LOCAL ROAD UPGRADING | P-6, PAHINDONG | 3600000 |  |  |  |  | 1 | COMPLETED | as of 5/23/2019 (SWA) | 2019-05-28 |  | -
2018 | REGION X | MISAMIS ORIENTAL | NAAWAN | LOCAL ACCESS ROAD | LOCAL ROAD UPGRADING | BARANGAY MAPULOG | 13713776.38 |  |  |  |  | 1 | COMPLETED | SWA | 2019-05-24 |  | -
2018 | REGION X | MISAMIS ORIENTAL | OPOL | LOCAL ACCESS ROAD | LOCAL ROAD UPGRADING | BARANGAY AWANG | 9298040.73 |  |  |  |  | 1 | COMPLETED | SWA | 2019-05-28 |  | -
2018 | REGION X | MISAMIS ORIENTAL | SALAY | LOCAL ACCESS ROAD | LOCAL ROAD REHABILITATION/IMPROVEMENT | SITIO SALAHON, BRGY. ALIPUATON | 7444367.91 |  |  |  |  | 1 | COMPLETED | as of 3/29/2019 SWA | 2019-04-15 |  | -
2018 | REGION X | MISAMIS ORIENTAL | SUGBONGCOGON | LOCAL ACCESS ROAD | LOCAL ROAD UPGRADING | BARANGAY MANGGA | 7797869.88 |  |  |  |  | 1 | COMPLETED | 370 meters: 100% as of 3/28/2019 (SWA) | 2019-04-08 |  | -
350 meters: 100% as of 3/28/2019 (SWA)
2018 | REGION X | MISAMIS ORIENTAL | TAGOLOAN | LOCAL ACCESS ROAD | LOCAL ROAD UPGRADING | POBLACION | 3951394.66 | 1 |  |  |  |  | CANCELLED | RETURNED TO BTr | 2020-01-10 | npj | -
2018 | REGION X | MISAMIS ORIENTAL | TALISAYAN | LOCAL ACCESS ROAD | LOCAL ROAD UPGRADING | BARANGAY BUGDANG | 4200000 |  |  |  |  | 1 | COMPLETED | AS OF MAY 2020 SWA | 2020-06-05 |  | 0
2018 | REGION X | MISAMIS ORIENTAL | TALISAYAN | LOCAL ACCESS ROAD | LOCAL ROAD UPGRADING | BARANGAY MAGKARILA | 4393803.42 |  |  |  |  | 1 | COMPLETED | AS OF MAY 2020 SWA | 2020-06-05 |  | 0
2018 | REGION X | MISAMIS ORIENTAL | VILLANUEVA | LOCAL ACCESS ROAD | LOCAL ROAD UPGRADING | SITIO BANBAN TO SITIO MADRID, BRGY. LOOC | 8504442.5 |  |  |  |  | 1 | COMPLETED | PER ENGR. PUIG BUT HAS DEFFECTS | 2020-06-23 | npj | 0
SUB-TOTAL (LAR) MIS.OR: |  |  | 16 | 18 |  |  | 125262047.17 | 1 | 0 | 0 | 0 | 18
2018 | REGION X | MISAMIS ORIENTAL | BALINGOAN | PROVISION OF SANITARY TOILET AND HYGIENE FACILITIES | REHABILITATION/IMPROVEMENT/UPGRADING OF EXISTING SANITARY TOILET AND HYGIENE FACILITIES FOR PUBLIC PLACES | MUNICIPAL WIDE | 5345624.53 |  |  |  | 1 |  | 90.00% Physical Accompishment | ongoing implementation | 2020-06-23 | engr. puig | 0
2018 | REGION X | MISAMIS ORIENTAL | BALINGOAN | DRR RESCUE EQUIPMENT | DRR EQUIPMENT | MUNICIPAL WIDE | 2300000 |  |  |  |  | 1 | COMPLETED |  | 2019-09-16 | npjr | 0
2018 | REGION X | MISAMIS ORIENTAL | INITAO | LOCAL BRIDGES | LOCAL BRIDGE REHABILITATION | APAS, INITAO | 7512876.05 |  |  |  |  | 1 | COMPLETED | UPDATE PER ENGR.PUIG | 2020-06-23 |  | 0
2018 | REGION X | MISAMIS ORIENTAL | LAGUINDINGAN | EVACUATION CENTER | CONSTRUCTION OF NEW EVACUATION CENTER | BARANGAY TUBAJON | 7216920.91 |  |  |  |  | 1 | COMPLETED | as of 10/15/2019 SWA | 2019-10-28 |  | -
SUB-TOTAL (OTHERS) MIS.OR: |  |  | 3 | 4 |  |  | 22375421.49 | 0 | 0 | 0 | 1 | 3 |  |  |  |  | 1
TOTAL (OTHERS+LAR) MISAMIS ORIENTAL: |  |  | 19 | 22 |  |  | 147637468.66 | 1 | 0 | 0 | 1 | 21
GRAND TOTAL |  |  | 74 | 94 |  |  | 536802145.17 | 3 | 0 | 0 | 3 | 91

## 2018 AM-WATER
REGION X - AM
2018 AM-WATER
as of June 26, 2020
FY | REGION | PROVINCE | CITY / MUNICIPALITY | NAME OF PROJECT | PHYSICAL TARGETS/OUTPUTS | BARANGAY | ORIGINAL ALLOCATION | CANCELLED PROJECTS | APPROVED DED/POW or DED PREP. | PROCUREMENT | ON-GOING | COMPLETED | STATUS | REMARKS | DATE UPDATED |  | SUBMITTED ON-TIME (SWA)
2018 | REGION X | BUKIDNON | BAUNGON | PROVISION OF POTABLE WATER SUPPLY | REHABILITATION/IMPROVEMENT OF LEVEL II/LEVEL III WATER SYSTEM | BRGY. SAN VICENTE - BRGY SALIMBALAN | 5789211.39 |  |  |  |  | 1 | COMPLETED | as of 11/8/2019 SWA | 2019-12-09 |  | -
2018 | REGION X | BUKIDNON | KALILANGAN | PROVISION OF POTABLE WATER SUPPLY | EXPANSION OF LEVEL II/LEVEL III WATER SYSTEM | BARANGAY LAMPANUSAN | 6063791.99 |  |  |  | 1 |  | 80.33% Physical Accomplishment | AS OF 05/20/2020 SWA ongoing cancellation | 2020-06-03 |  | 0
2018 | REGION X | BUKIDNON | KITAOTAO | PROVISION OF POTABLE WATER SUPPLY | NEW CONSTRUCTION OF LEVEL II POTABLE WATER SUPPLY SYSTEM | SINUDA | 7762936.76 | 1 |  |  |  |  | CANCELLED |  |  |  | -
2018 | REGION X | BUKIDNON | LANTAPAN | PROVISION OF POTABLE WATER SUPPLY | REHABILITATION/IMPROVEMENT OF LEVEL II/LEVEL III WATER SYSTEM | BARANGAY KAATUAN, LANTAPAN | 6697903.28 |  |  |  | 1 |  | 98.29% Physical Accomplishment | AS OF 5/20/2020 (under suspension due to COVID-19) | 2020-06-25 |  | 0
2018 | REGION X | BUKIDNON | MANOLO FORTICH | PROVISION OF POTABLE WATER SUPPLY | UPGRADING OF WATER SYSTEM | SANTIAGO | 1104892.56 |  |  |  |  | 1 | COMPLETED | as of 8/15/2019 (SWA) | 2019-09-23 |  | -
2018 | REGION X | BUKIDNON | MANOLO FORTICH | PROVISION OF POTABLE WATER SUPPLY | UPGRADING OF WATER SYSTEM | KALUGMANAN | 2000000 |  |  |  |  | 1 | COMPLETED | AS OF 9/30/2019 SWA | 2020-01-09 |  | -
2018 | REGION X | BUKIDNON | MANOLO FORTICH | PROVISION OF POTABLE WATER SUPPLY | EXPANSION OF LEVEL II/LEVEL III WATER SYSTEM | TICALA | 1500000 |  |  |  |  | 1 | COMPLETED | as of 8/1/2019 (SWA) | 2019-08-19 |  | -
2018 | REGION X | BUKIDNON | MANOLO FORTICH | PROVISION OF POTABLE WATER SUPPLY | EXPANSION OF LEVEL II/LEVEL III WATER SYSTEM | MAMPAYAG | 2863213 |  |  |  |  | 1 | COMPLETED | as of 8/8/2019 (SWA) | 2019-08-20 |  | -
2018 | REGION X | BUKIDNON | SAN FERNANDO | PROVISION OF POTABLE WATER SUPPLY | NEW CONSTRUCTION OF LEVEL II POTABLE WATER SUPPLY SYSTEM | NACABUKLAD, TUGOP, HALAPITAN AND LITTLE BAGUIO | 6472100.47 |  |  |  |  | 1 | COMPLETED | as of 11/5/2019 SWA | 11/25/2019 |  | -
TOTAL |  |  | 6 | 8 |  |  | 40254049.45 | 1 | 0 | 0 | 2 | 6
2018 | REGION X | CAMIGUIN | SAGAY | PROVISION OF POTABLE WATER SUPPLY | EXPANSION OF LEVEL II/LEVEL III WATER SYSTEM | BRGY. BUGANG TO BRGY. MAYANA | 2921184.53 |  |  |  |  | 1 | COMPLETED | as of 3/15/2019 (SWA) | 2019-04-25 |  | -
2018 | REGION X | CAMIGUIN | SAGAY | PROVISION OF POTABLE WATER SUPPLY | EXPANSION OF LEVEL II/LEVEL III WATER SYSTEM | SITIO KILOMOY, BRGY. BACNIT | 1000000 |  |  |  |  | 1 | COMPLETED | as of 2/15/2019 (SWA | 2019-02-27 |  | -
TOTAL |  |  | 1 | 2 |  |  | 3921184.53 | 0 | 0 | 0 | 0 | 2
2018 | REGION X | LANAO DEL NORTE | KAUSWAGAN | PROVISION OF POTABLE WATER SUPPLY | REHABILITATION/IMPROVEMENT OF LEVEL II/LEVEL III WATER SYSTEM | TUGAR | 219772.94 |  |  |  |  | 1 | COMPLETED | as of 3/18/2019 (SWA) | 2019-03-25 |  | -
2018 | REGION X | LANAO DEL NORTE | KAUSWAGAN | PROVISION OF POTABLE WATER SUPPLY | REHABILITATION/IMPROVEMENT OF LEVEL II/LEVEL III WATER SYSTEM | BARAASON | 219772.93 |  |  |  |  | 1 | COMPLETED | as of 3/18/2019 (SWA) | 2019-03-25 |  | -
2018 | REGION X | LANAO DEL NORTE | NUNUNGAN | PROVISION OF POTABLE WATER SUPPLY | NEW CONSTRUCTION OF LEVEL II POTABLE WATER SUPPLY SYSTEM | BARANGAY LUPITAN | 3999887.14 |  |  |  |  | 1 | COMPLETED | Monthly Meeting | 2019-03-08 |  | -
2018 | REGION X | LANAO DEL NORTE | PANTAR | PROVISION OF POTABLE WATER SUPPLY | NEW CONSTRUCTION OF LEVEL II POTABLE WATER SUPPLY SYSTEM | BRGYS. CAMPONG, POBLACION & PANTAR WEST (BANGCAL) | 2000000 |  |  |  |  | 1 | COMPLETED | as of 12/20/2019 SWA | 2019-12-23 |  | -
2018 | REGION X | LANAO DEL NORTE | PANTAR | PROVISION OF POTABLE WATER SUPPLY | NEW CONSTRUCTION OF LEVEL II POTABLE WATER SUPPLY SYSTEM | BRGYS. KALANGANAN EAST TO LOWER KALANGANAN (TANCAL) | 2000000 |  |  |  |  | 1 | COMPLETED | as of 12/20/2019 SWA | 2019-12-23 |  | -
2018 | REGION X | LANAO DEL NORTE | SULTAN NAGA DIMAPORO | PROVISION OF POTABLE WATER SUPPLY | NEW CONSTRUCTION OF LEVEL II POTABLE WATER SUPPLY SYSTEM | BARANGAYS MAMAGUM, BANGAAN, SIGAYAN | 7823212.13 |  |  |  |  | 1 | COMPLETED | Mamagum - 100% SWA | 2019-06-20 |  | -
[14 empty] | Sigayan - 100% as of 7/22/2019 SWA | 7/23/2019
[14 empty] | Bangaan-100% SWA | 2019-06-20
TOTAL |  |  | 4 | 6 |  |  | 16262645.14 | 0 | 0 | 0 | 0 | 6
2018 | REGION X | MISAMIS OCCIDENTAL | JIMENEZ | PROVISION OF POTABLE WATER SUPPLY | REHABILITATION/IMPROVEMENT OF LEVEL II/LEVEL III WATER SYSTEM | BRGY. CORRALES, TARAKA, NAGA, NACIONAL, STA. CRUZ, PALILAN, AND TABO-O | 12987707.44 |  |  |  |  | 1 | COMPLETED |  | 2020-01-10 |  | 0
TOTAL |  |  | 1 | 1 |  |  | 12987707.44 | 0 | 0 | 0 | 0 | 1
2018 | REGION X | MISAMIS ORIENTAL | BINUANGAN | PROVISION OF POTABLE WATER SUPPLY | UPGRADING OF WATER SYSTEM | BARANGAY DAMPIAS, MOSANGOT, POBLACION AND MABINI | 15219428.42 |  |  |  |  | 1 | COMPLETED |  | 2020-06-23 | NPJ | 0
2018 | REGION X | MISAMIS ORIENTAL | JASAAN | PROVISION OF POTABLE WATER SUPPLY | EXPANSION OF LEVEL II/LEVEL III WATER SYSTEM | BARANGAY APLAYA | 9219667.43 |  |  |  |  | 1 | COMPLETED | AS OF 2/19/2020 SWA | 2020-03-30 |  | 0
2018 | REGION X | MISAMIS ORIENTAL | KINOGUITAN | PROVISION OF POTABLE WATER SUPPLY | EXPANSION OF LEVEL II/LEVEL III WATER SYSTEM | MUNICIPAL WIDE, BARANGAY KAGUMAHAN | 9472079.68 |  |  |  |  | 1 | COMPLETED |  | 2020-06-23 | NPJ | 0
2018 | REGION X | MISAMIS ORIENTAL | LUGAIT | PROVISION OF POTABLE WATER SUPPLY | EXPANSION OF LEVEL II/LEVEL III WATER SYSTEM | POBLACION | 7979396.16 |  |  |  | 1 |  | 78.00% Physical Accomplishment | AS OF 2/15/2020 SWA ongoing implementation | 2020-03-03 |  | 0
2018 | REGION X | MISAMIS ORIENTAL | MANTICAO | PROVISION OF POTABLE WATER SUPPLY | EXPANSION OF LEVEL II/LEVEL III WATER SYSTEM | PANIANGAN, POBLACION, PUNTA SILUM | 7412580.14 |  |  |  |  | 1 | COMPLETED | FOR FINAL INSPECTION | 2020-01-10 | NPJ | 0
2018 | REGION X | MISAMIS ORIENTAL | TAGOLOAN | PROVISION OF POTABLE WATER SUPPLY | NEW CONSTRUCTION OF LEVEL II POTABLE WATER SUPPLY SYSTEM | NATUMOLAN | 5809213 | 1 |  |  |  |  | CANCELLED | Reverted and remitted the unutilized fund to the Bureau of the Treasury | 2019-12-03 |  | -
TOTAL |  |  | 6 | 5 |  |  | 55112364.83 | 1 | 0 | 0 | 1 | 4 |  |  |  |  | 0
GRAND TOTAL |  |  | 18 | 22 |  |  | 128537951.39 | 2 | 0 | 0 | 3 | 19

## 2019 LGSF-AM
REGION X - AM
2019 AM-OTHERS
as of June 26, 2020
FY | REGION | PROVINCE | CITY/MUNICIPALITY | NAME OF PROJECT | PHYSICAL TARGETS/OUTPUTS | BARANGAY | ORIGINAL ALLOCATION | CANCELLED | DED/POW PREPARATION | FINALIZATION | PROCUREMENT | ON-GOING | COMPLETED | STATUS | REMARKS | DATE UPDATED
2019 | REGION X | BUKIDNON | CABANGLASAN | LOCAL ACCCESS ROAD IN CAPINONAN | LOCAL ACCESS ROAD | CAPINONAN | 5302000 | [5 empty] | 1 | COMPLETED | AS OF 06/11/2020 SWA | 2020-06-26
2019 | REGION X | BUKIDNON | DAMULOG | LOCAL ACCESS ROAD IN BRGY. POBLACION (JCT. NATIONAL ROAD TO SAN ROQUE ST.) | LOCAL ACCESS ROAD | BRGY. POBLACION (JCT. NATIONAL ROAD TO SAN ROQUE ST.) | 6180000 |  |  |  |  | 1 |  | 73.90% PHYSICAL ACCOMPLISHMENT | UPDATE AS OF 5/23//2020 SWA | 2020-05-27
2019 | REGION X | BUKIDNON | DAMULOG | LOCAL ACCESS ROAD IN BRGY. POBLACION (JOSE RIZAL ST. TO JCT. ANTONIO LUNA ST.) | LOCAL ACCESS ROAD | POBLACION (JOSE RIZAL ST. TO JCT. ANTONIO LUNA ST.) | 3736000 |  |  |  |  | 1 |  | 23.35% PHYSICAL ACCOMPLISHMENT | UPDATE AS OF 5/23//2020 SWA | 2020-05-27
2019 | REGION X | BUKIDNON | DANGCAGAN | LOCAL ACCESS ROAD IN SAN VICENTE | LOCAL ACCESS ROAD | SAN VICENTE | 4889500 |  |  |  |  | 1 |  | 84.52% PHYSICAL ACCOMPLISHMENT | AS OF 05/20/2020 SWA | 2020-05-22
2019 | REGION X | BUKIDNON | DANGCAGAN | LOCAL ACCESS ROAD IN DOLOROSA | LOCAL ACCESS ROAD | DOLOROSA | 4889500 |  |  |  |  | 1 |  | 90.80% PHYSICAL ACCOMPLISHMENT | AS OF 05/20/2020 SWA | 2020-05-22
2019 | REGION X | BUKIDNON | DON CARLOS | LOCAL ACCESS ROAD IN BRGY. DON CARLOS NORTE | LOCAL ACCESS ROAD | DON CARLOS NORTE | ₱5,985,000.00 |  |  |  | 1 |  |  | PROCUREMENT PROCESS | AS OF 4/21/2020 SWA | 2020-04-28
2019 | REGION X | BUKIDNON | KADINGILAN | LOCAL ACCESS ROAD IN PAY-AS | LOCAL ACCESS ROAD | PAY-AS | 6466000 |  |  |  |  | 1 |  | 73.44% PHYSICAL ACCOMPLISHMENT | AS OF 6/24/2020 SWA | 2020-06-26
2019 | REGION X | BUKIDNON | KIBAWE | LOCAL ACCESS ROAD IN BRGY. WEST KIBAWE | LOCAL ACCESS ROAD | WEST KIBAWE | 6587000 | [5 empty] | 1 | COMPLETED |  | 2020-06-23 | per engr.alamban
2019 | REGION X | BUKIDNON | LIBONA | LOCAL ACCESS ROAD IN BRGY. POBLACION | LOCAL ACCESS ROAD | POBLACION | 5927000 |  |  |  |  | 1 |  | 3.12% PHYSICAL ACCOMPLISHMENT | AS OF 3/11/2020 SWA | 2020-05-14
2019 | REGION X | BUKIDNON | MALITBOG | LOCAL ACCESS ROAD IN SAN LUIS | LOCAL ACCESS ROAD | SAN LUIS | 5105000 |  |  |  |  | 1 |  | 4.90% PHYSICAL ACCOMPLISHMENT | AS OF 5/26/2020 SWA | 2020-06-03
2019 | REGION X | BUKIDNON | PANGANTUCAN | LOCAL ACCESS ROAD IN BRGY. MENDIS | LOCAL ACCESS ROAD | MENDIS | 5698000 |  |  |  |  | 1 |  | 39.46% PHYSICAL ACCOMPLISHMENT | AS OF 05/25/2020 SWA | 2020-06-11
2019 | REGION X | BUKIDNON | QUEZON | LOCAL ACCESS ROAD IN BRGY. POBLACION | LOCAL ACCESS ROAD | POBLACION | 11445000 |  |  |  |  | 1 |  | 70.00% PHYSICAL ACCOMPLISHMENT | AS OF 4/15/2020 SWA | 2020-04-28
2019 | REGION X | BUKIDNON | SUMILAO | LOCAL ACCESS ROAD IN KULASI | LOCAL ACCESS ROAD | KULASI | 2894000 | [5 empty] | 1 | COMPLETED | AS OF 2/14/2020 SWA | 2020-04-08
2019 | REGION X | BUKIDNON | SUMILAO | LOCAL ACCESS ROAD IN OCCASION | LOCAL ACCESS ROAD | OCCASION | 2894000 | [5 empty] | 1 | COMPLETED | AS OF 2/6/2020 SWA | 2020-04-08
2019 | REGION X | BUKIDNON | SUMILAO | LOCAL ACCESS ROAD IN PUNTIAN | LOCAL ACCESS ROAD | PUNTIAN | 2895000 | [5 empty] | 1 | COMPLETED | AS OF 2/6/2020 SWA | 2020-04-08
2019 | REGION X | BUKIDNON | TALAKAG | LOCAL ACCESS ROAD IN BRGY. COSINA | LOCAL ACCESS ROAD | COSINA | 6082000 |  |  |  |  | 1 |  | 43.30% PHYSICAL ACCOMPLISHMENT | AS OF 4/24/2020 SWA | 2020-04-28
SUB-TOTAL (BUKIDNON LAR) |  |  | 12 | 16 |  |  | 80990000 | 0 | 0 | 0 | 1 | 10 | 5
2019 | REGION X | BUKIDNON | BAUNGON | PROCUREMENT OF DRR EQUIPMENT | DRR RELATED EQUIPMENT |  | 6477000 |  |  |  | 1 |  |  | PROCUREMENT PROCESS | UPDATE AS OF 1/30/2020 MONTHLY MEETING | 2020-01-31
2019 | REGION X | BUKIDNON | BAUNGON | PROCUREMENT OF RESCUE VEHICLE | DRR RELATED EQUIPMENT | SELECTED BARANGAYS | 770000 |  |  | 1 |  |  |  | DED AND POW FINALIZATION |  | 2020-05-22
2019 | REGION X | BUKIDNON | BAUNGON | PROCUREMENT OF RESCUE VEHICLE | DRR RELATED EQUIPMENT | LGU | 4800000 |  |  | 1 |  |  |  | DED AND POW FINALIZATION |  | 2020-05-22
2019 | REGION X | BUKIDNON | MARAMAG | LOCAL BRIDGE IN NORTH POBLACION | LOCAL BRIDGES | NORTH POBLACION | 7881000 |  |  |  |  | 1 |  | 9.87% PHYSICAL ACCOMPLISHMENT | AS OF 04/27/2020 SWA | 2020-04-30
2019 | REGION X | BUKIDNON | SAN FERNANDO | PROCUREMENT OF DRR EQUIPMENT | DRR RELATED EQUIPMENT |  | 5761000 | [5 empty] | 1 | COMPLETED |  | 2020-06-23 | engr. alamban
SUB-TOTAL (BUKIDNON OT) |  |  | 3 | 5 |  |  | 25689000 | 0 | 0 | 2 | 1 | 1 | 1
TOTAL |  |  | 15 | 21 |  |  | 106679000 | 0 | 0 | 2 | 2 | 11 | 6
2019 | REGION X | CAMIGUIN | CATARMAN | LOCAL ACCESS ROAD IN BARANGAY ALGA | LOCAL ACCESS ROAD | ALGA | 5000000 |  |  |  |  | 1 |  | 77.25% PHYSICAL ACCOMPLISHMENT | AS OF 04/27/2020 SWA | 2020-05-05
2019 | REGION X | CAMIGUIN | CATARMAN | LOCAL ACCESS ROAD IN BRGY. POBLACION | LOCAL ACCESS ROAD | POBLACION | 5804000 |  |  |  | 1 |  |  | ONGOING PROCUREMENT PROCESS | AS OF 04/27/2020 SWA | 2020-05-05
2019 | REGION X | CAMIGUIN | GUINSILIBAN | LOCAL ACCESS ROAD IN SOUTH POBLACION TO KIWAKAT | LOCAL ACCESS ROAD | SOUTH POBLACION TO KIWAKAT | 5146000 | 1 | [5 empty] | CANCELLED | NON-GFH PASSER | 2020-02-24 | KA
2019 | REGION X | CAMIGUIN | MAHINOG | LOCAL ACCESS ROAD IN BENONI | LOCAL ACCESS ROAD | BENONI | 3730000 | [5 empty] | 1 | COMPLETED | AS OF 03/10/2020 SWA | 2020-05-04
2019 | REGION X | CAMIGUIN | MAHINOG | LOCAL ACCESS ROAD IN POBLACION | LOCAL ACCESS ROAD | POBLACION | 3501000 | [5 empty] | 1 | COMPLETED | AS OF 03/10/2020 SWA | 2020-05-04
SUB-TOTAL |  |  | 3 | 4 |  |  | 23181000 | 1 | 0 | 0 | 1 | 1 | 2
2019 | REGION X | CAMIGUIN | MAMBAJAO | IMPROVEMENT/ REHABILITATION OF EVACUATION CENTER | EVACUATION CENTER |  | 2500000 |  |  |  | 1 |  |  | DED/POW APPROVED |  | 2020-06-11 | KA
2019 | REGION X | CAMIGUIN | MAMBAJAO | CONSTRUCTION OF SANITARY TOILET AND HYGIENE FACILITY | HEALTH AND SANITATION |  | 2068000 |  |  |  | 1 |  |  | DED/POW APPROVED |  | 2020-06-11 | KA
SUB-TOTAL |  |  | 1 | 2 |  |  | 4568000 | 0 | 0 | 0 | 2 | 0 | 0 |  |  | .
TOTAL |  |  | 4 | 6 |  |  | 27749000 | 1 | 0 | 0 | 3 | 1 | 2
2019 | REGION X | LANAO DEL NORTE | BACOLOD | LOCAL ACCESS ROAD IN BRGY. KAHAYAG | LOCAL ACCESS ROAD | KAHAYAG | 9765000 |  |  |  | 1 |  |  | PROCUREMENT PROCESS |  | 2020-01-10 | ND
2019 | REGION X | LANAO DEL NORTE | BALO-I | LOCAL ACCESS ROAD IN BRGY. MAMAANUN | LOCAL ACCESS ROAD | MAMAANUN | 5500000 |  |  |  | 1 |  |  | DED/POW APPROVED | NO FUND DOWNLOAD | 2020-01-10 | ND
2019 | REGION X | LANAO DEL NORTE | BALO-I | LOCAL ACCESS ROAD IN BRGY. ANGAYEN | LOCAL ACCESS ROAD | ANGAYEN | 4997000 |  |  |  | 1 |  |  | DED/POW APPROVED | NO FUND DOWNLOAD | 2020-01-10 | ND
2019 | REGION X | LANAO DEL NORTE | BAROY | LOCAL ACCESS ROAD IN LINDONGAN AND BATO | LOCAL ACCESS ROAD | LINDONGAN AND BATO | 9756000 |  |  |  |  | 1 |  | 50.34% PHYSICAL ACCOMPLISHMENT | AS OF 4/24/2020 SWA | 2020-05-12
2019 | REGION X | LANAO DEL NORTE | KAPATAGAN | LOCAL ACCESS ROAD IN POBLACION | LOCAL ACCESS ROAD | POBLACION | 10590000 |  |  |  |  | 1 |  | 86.86% PHYSICAL ACCOMPLISHMENT | 06/15/2020 SWA | 2020-06-19
2019 | REGION X | LANAO DEL NORTE | KAUSWAGAN | LOCAL ACCESS ROAD IN BRGY. KAWIT OCCIDENTAL | LOCAL ACCESS ROAD | KAWIT OCCIDENTAL | 2000000 | [5 empty] | 1 | COMPLETED | AS OF 2/20/2020 SWA | 2020-03-03
2019 | REGION X | LANAO DEL NORTE | KAUSWAGAN | LOCAL ACCESS ROAD IN POBLACION | LOCAL ACCESS ROAD | POBLACION | 3000000 |  |  |  |  | 1 |  | 90.55% PHYSICAL ACCOMPLISHMENT | AS OF 2/17/2020 SWA | 2020-02-27
2019 | REGION X | LANAO DEL NORTE | KAUSWAGAN | LOCAL ACCESS ROAD IN KAWIT ORIENTAL | LOCAL ACCESS ROAD | KAWIT ORIENTAL | 2484000 | [5 empty] | 1 | COMPLETED | AS OF 1/14/2020 SWA | 2020-01-20
2019 | REGION X | LANAO DEL NORTE | LALA | LOCAL ACCESS ROAD IN BRGY. LANIPAO, STARTS FROM NATIONAL HIGHWAY | LOCAL ACCESS ROAD | BRGY. LANIPAO, STARTS FROM NATIONAL HIGHWAY | 10691000 | [5 empty] | 1 | COMPLETED | AS OF 3/19//2020 SWA | 2020-03-19
2019 | REGION X | LANAO DEL NORTE | MAGSAYSAY | LOCAL ACCESS ROAD IN BAGUIGUICON | LOCAL ACCESS ROAD | BAGUIGUICON | 4992000 | [5 empty] | 1 | COMPLETED | AS OF JANUARY 20, 2020 SWA | 2020-02-27 | ND
2019 | REGION X | LANAO DEL NORTE | MAIGO | LOCAL ACCESS ROAD IN BALAGATASA AND SEGAPOD | LOCAL ACCESS ROAD | BALAGATASA AND SEGAPOD | 10905000 |  |  |  |  | 1 |  | 89.87% PHYSICAL ACCOMPLISHMENT | AS OF 05/20/2020 SWA | 2020-04-28
2019 | REGION X | LANAO DEL NORTE | MATUNGAO | LOCAL ACCESS ROAD IN BRGY. PASAYANON | LOCAL ACCESS ROAD | PASAYANON | 9577000 |  |  |  |  | 1 |  | 25.99% PHYSICAL ACCOMPLISHMENT | AS OF 03/30/2020 SWA | 2020-04-07
2019 | REGION X | LANAO DEL NORTE | MUNAI | LOCAL ACCESS ROAD IN BARANGAY TAMPARAN | LOCAL ACCESS ROAD | BARANGAY TAMPARAN | 9971000 |  |  |  |  | 1 |  | 94.40% PHYSICAL ACCOMPLISHMENT | AS OF 05/15/2020 SWA | 2020-05-05
2019 | REGION X | LANAO DEL NORTE | NUNUNGAN | LOCAL ACCESS ROAD IN NUNUNGAN | LOCAL ACCESS ROAD | NUNUNGAN | 10086000 | [5 empty] | 1 | COMPLETED | AS OF 2/2/2020 SWA | 2020-03-19
2019 | REGION X | LANAO DEL NORTE | PANTAO RAGAT | LOCAL ACCESS ROAD IN BRGY. BANDAY | LOCAL ACCESS ROAD | BANDAY | 4815000 | 1 | [5 empty] | CANCELLED | NON-GFH PASSER | 2020-02-24 | ND
2019 | REGION X | LANAO DEL NORTE | PANTAO RAGAT | LOCAL ACCESS ROAD IN BRGY. MADAYA | LOCAL ACCESS ROAD | MADAYA | 5050000 | 1 | [5 empty] | CANCELLED | NON-GFH PASSER | 2020-02-24 | ND
2019 | REGION X | LANAO DEL NORTE | PANTAR | LOCAL ACCESS ROAD IN BOWI TO SUNDIGA PUNOD | LOCAL ACCESS ROAD | BOWI TO SUNDIGA PUNOD | 5739000 |  |  |  |  | 1 |  | 60.76% PHYSICAL ACCOMPLISHMENT | AS OF 05/20/2020 SWA | 2020-05-27
2019 | REGION X | LANAO DEL NORTE | PANTAR | LOCAL ACCESS ROAD IN TAWANAN AND CADAYONAN (BOX CULVERT) | LOCAL ACCESS ROAD | TAWANAN AND CADAYONAN (BOX CULVERT) | 2000000 |  |  |  |  | 1 |  | 0.87% PHYSICAL ACCOMPLISHMENT | AS OF 05/20/2020 SWA | 2020-05-27 | ND
2019 | REGION X | LANAO DEL NORTE | POONA PIAGAPO | LOCAL ACCESS ROAD IN BRGY. CADAYONAN | LOCAL ACCESS ROAD | CADAYONAN | 10266000 |  |  |  |  | 1 |  | 40.00% PHYSICAL ACCOMPLISHMENT | AS OF 04/22/2020 SWA | 2020-04-28
2019 | REGION X | LANAO DEL NORTE | SAPAD | LOCAL ACCESS ROAD IN BARANGAY POBLACION (PROJECT 1) | LOCAL ACCESS ROAD | PUROK 8 POBLACION (PROJECT 1) | 2763689 |  |  |  |  | 1 |  | 95% PHYSICAL ACCOMPLISHMENT | AS OF 5/25/2020 SWA | 2020-06-11 | ND
2019 | REGION X | LANAO DEL NORTE | SAPAD | LOCAL ACCESS ROAD IN BARANGAY POBLACION (PROJECT 2) | LOCAL ACCESS ROAD | PUROK 13 POBLACION (PROJECT 2) | 3816523 |  |  |  |  | 1 |  | 90% PHYSICAL ACCOMPLISHMENT | AS OF 5/25/2020 SWA | 2020-06-11 | ND
2019 | REGION X | LANAO DEL NORTE | TAGOLOAN | LOCAL ACCESS ROAD IN BRGY. KIAZAR | LOCAL ACCESS ROAD | KIAZAR | 4873000 | 1 | [5 empty] | CANCELLED | NON-GFH PASSER | 2020-02-24 | ND
2019 | REGION X | LANAO DEL NORTE | TUBOD | LOCAL ACCESS ROAD IN BARANGAY POBLACION AND SAN ANTONIO | LOCAL ACCESS ROAD | BARANGAY POBLACION AND SAN ANTONIO | 11433000 |  |  |  |  | 1 |  | 73.13% PHYSICAL ACCOMPLISHMENT | AS OF 05/20/2020 SWA | 2020-06-03
SUB-TOTAL |  |  | 17 | 20 |  |  | 155070212 | 3 | 0 | 0 | 3 | 12 | 5
2019 | REGION X | LANAO DEL NORTE | KOLAMBUGAN | CONSTRUCTION / REPAIR OF HEALTH/SANITATION FACILITIES | HEALTH AND SANITATION |  | 5000000 |  |  |  |  | 1 |  | 55.05% PHYSCIAL ACCOMPLISHMENT (Brgy. Titunod) 88.81% PHYSCIAL ACCOMPLISHMENT (Brgy. Sto. Niño) | AS OF 05/20/2020 SWA | 2020-06-05
2019 | REGION X | LANAO DEL NORTE | KOLAMBUGAN | CONSTRUCTION OF SANITARY TOILET WITH HYGIENE FACILITIES FOR PUBLIC PLACES | HEALTH AND SANITATION |  | 1847000 |  |  |  | 1 |  |  | PROCUREMENT PROCESS |  | 2020-01-10 | ND
2019 | REGION X | LANAO DEL NORTE | SALVADOR | LOCAL BRIDGES IN BRGY. PANALIWAD | LOCAL BRIDGES | LOCAL BRIDGES IN BRGY. PANALIWAD | 8648000 |  |  |  | 1 |  |  | DED/POW APPROVED | NO FUND DOWNLOAD | 2020-01-10 | ND
2019 | REGION X | LANAO DEL NORTE | SALVADOR | PROCUREMENT OF DRR RESCUE VEHICLE | DRR RELATED EQUIPMENT | PROCUREMENT OF DRR RESCUE VEHICLE | 1300000 |  |  |  |  | 1 |  | ON-GOING IMPLEMENTATION | REQUEST TO PURCHASE | 2020-01-10 | ND
2019 | REGION X | LANAO DEL NORTE | SAPAD | CONSTRUCTION OF EVACUATION CENTER | EVACUATION CENTER | CONSTRUCTION OF EVACUATION CENTER | 3148788 |  |  |  |  | 1 |  | 60% PHYSICAL ACCOMPLISHMENT | AS OF 5/25/2020 SWA | 2020-06-11
2019 | REGION X | LANAO DEL NORTE | TANGCAL | LOCAL ACCESS ROAD IN BRGY. PAPAN | LOCAL ACCESS ROAD | BRGY. PAPAN | 4000000 |  |  |  |  | 1 |  | 70.11% PHYSCIAL ACCOMPLISHMENT | AS OF 2/20/2020 SWA | 2020-03-03
2019 | REGION X | LANAO DEL NORTE | TANGCAL | LOCAL ACCESS ROAD IN BERWAR TO TANGCAL PROPER | LOCAL ACCESS ROAD | BERWAR TO TANGCAL PROPER | 5602000 |  |  |  |  | 1
SUB-TOTAL |  |  | 4 | 7 |  |  | 29545788 | 0 | 0 | 0 | 2 | 5 | 0
TOTAL |  |  | 21 | 27 |  |  | 184616000 | 3 | 0 | 0 | 5 | 17 | 5
2019 | REGION X | MISAMIS OCCIDENTAL | ALORAN | LOCAL ACCESS ROAD IN BARANGAY MAKAWA | LOCAL ACCESS ROAD | MAKAWA | 6338000 |  |  |  |  | 1 |  | ON-GOING IMPLEMENTATION | (MOBILIZATION) UPDATE AS OF 1/30/2020 MONTHLY MEETING | 2020-01-31
2019 | REGION X | MISAMIS OCCIDENTAL | BALIANGAO | LOCAL ACCESS ROAD IN BRGY. MISOM | LOCAL ACCESS ROAD | MISOM | 4952000 | 1 | [5 empty] | CANCELLED | NON-GFH PASSER | 2020-02-24 | CEB
2019 | REGION X | MISAMIS OCCIDENTAL | BONIFACIO | LOCAL ACCESS ROAD IN BRGY. TANGAB | LOCAL ACCESS ROAD | TANGAB | 9958000 | [5 empty] | 1 | COMPLETED | as of 12/26/2019 SWA | 2020-04-03
2019 | REGION X | MISAMIS OCCIDENTAL | CALAMBA | LOCAL ACCESS ROAD IN BRGY. BUNAWAN | LOCAL ACCESS ROAD | BUNAWAN | 7889000 |  |  |  |  | 1 |  | 46.67 PHYSICAL ACCOMPLISHMENT | AS OF 03/26/2020 SWA | 2020-05-05
2019 | REGION X | MISAMIS OCCIDENTAL | CLARIN | LOCAL ACCESS ROAD IN KINANGAY NORTE AND KINANGAY SUR | LOCAL ACCESS ROAD | KINANGAY NORTE AND KINANGAY SUR | 11734000 |  |  |  |  | 1 |  | 30.03% PHYSICAL ACCOMPLISHMENT | AS OF 01/29/2020 SWA | 2020-04-03 | CEB
2019 | REGION X | MISAMIS OCCIDENTAL | CONCEPCION | LOCAL ACCESS ROAD IN NEW CASUL - UPPER DAPITAN | LOCAL ACCESS ROAD | NEW CASUL - UPPER DAPITAN | 4825000 | 1 | [5 empty] | CANCELLED | RETURNING OF FUNDS | 2020-05-18 | CEB
2019 | REGION X | MISAMIS OCCIDENTAL | DON VICTORIANO CHIONGBAN | LOCAL ACCESS ROAD IN LALUD, NAPANGAN, AND NUEVA VISTA | LOCAL ACCESS ROAD | LALUD, NAPANGAN, AND NUEVA VISTA | 4809000 |  |  |  | 1 |  |  | PROCUREMENT PROCESS |  | 2020-01-10 | CEB
2019 | REGION X | MISAMIS OCCIDENTAL | LOPEZ JAENA | LOCAL ACCESS ROAD IN BARANGAY RIZAL | LOCAL ACCESS ROAD | BARANGAY RIZAL | 5117000 |  |  |  | 1 |  |  | POW/DED APPROVED |  | 2020-05-18 | CEB
2019 | REGION X | MISAMIS OCCIDENTAL | PANAON | LOCAL ACCESS ROAD IN POBLACION | LOCAL ACCESS ROAD | POBLACION | 3277000 |  |  |  |  | 1 |  | 90.00% PHYSICAL ACCOMPLISHMENT | AS OF 2/12/2020 | 2020-04-03
2019 | REGION X | MISAMIS OCCIDENTAL | PANAON | LOCAL ACCESS ROAD IN PUNTA | LOCAL ACCESS ROAD | PUNTA | 3200000 |  |  |  |  | 1 |  | 48.50% PHYSICAL ACCOMPLISHMENT | AS OF 3/2/2020 | 2020-04-03
2019 | REGION X | MISAMIS OCCIDENTAL | PLARIDEL | LOCAL ACCESS ROAD IN EASTERN LOOC | LOCAL ACCESS ROAD | EASTERN LOOC | 11262000 | [5 empty] | 1 | COMPLETED | AS OF 2/27/2020 SWA | 2020-04-06
2019 | REGION X | MISAMIS OCCIDENTAL | SAPANG DALAGA | LOCAL ACCESS ROAD IN SINAAD | LOCAL ACCESS ROAD | SINAAD | 6180000 |  |  |  | 1 |  |  | PROCUREMENT PROCESS |  | 2020-01-10 | CEB
2019 | REGION X | MISAMIS OCCIDENTAL | SINACABAN | LOCAL ACCESS ROAD IN BRGY. LIBERTAD ALTO | LOCAL ACCESS ROAD | BRGY. LIBERTAD ALTO | 6147000 | [5 empty] | 1 | COMPLETED | AS OF 2/7/2020 SWA | 2020-03-12
2019 | REGION X | MISAMIS OCCIDENTAL | TUDELA | LOCAL ACCESS ROAD IN BARANGAY YAHONG | LOCAL ACCESS ROAD | BARANGAY YAHONG | 6365000 |  |  |  | 1 |  |  | PROCUREMENT PROCESS |  | 2020-01-10 | CEB
TOTAL |  |  | 13 | 12 |  |  | 92053000 | 2 | 0 | 0 | 4 | 5 | 3
2019 | REGION X | MISAMIS ORIENTAL | ALUBIJID | LOCAL ACCESS ROAD IN BRGY. POBLACION | LOCAL ACCESS ROAD | BRGY. POBLACION | 11072000 |  |  |  |  | 1 |  | 94.02% PHYSICAL ACCOMPLISHMENT | AS OF 6/5//2020 SWA | 2020-06-19
2019 | REGION X | MISAMIS ORIENTAL | BALINGASAG | LOCAL ACCESS ROAD IN BARANGAY MANDANGOA | LOCAL ACCESS ROAD | BARANGAY MANDANGOA | 4000000 |  |  |  | 1 |  |  | DED and POW Approved |  | 2020-01-10
2019 | REGION X | MISAMIS ORIENTAL | BALINGASAG | LOCAL ACCESS ROAD IN BARANGAY LINGGANGAO | LOCAL ACCESS ROAD | BARANGAY LINGGANGAO | 4000000 |  |  |  | 1 |  |  | DED and POW Approved |  | 2020-01-10
2019 | REGION X | MISAMIS ORIENTAL | BALINGASAG | LOCAL ACCESS ROAD IN LOWER BARANGAY SAN FRANCISCO | LOCAL ACCESS ROAD | LOWER BARANGAY SAN FRANCISCO | 3845000 |  |  |  | 1 |  |  | DED and POW Approved |  | 2020-01-10
2019 | REGION X | MISAMIS ORIENTAL | BALINGOAN | LOCAL ACCESS ROAD IN BRGY. BAUK-BAUK | LOCAL ACCESS ROAD | BRGY. BAUK-BAUK | 5995000 |  |  | 1 |  |  |  | DED and POW Finalization |  | 2020-01-24 | NPJR
2019 | REGION X | MISAMIS ORIENTAL | BINUANGAN | LOCAL ACCESS ROAD IN POBLACION TO BRGY. KITAMBAN | LOCAL ACCESS ROAD | POBLACION TO BRGY. KITAMBAN | 3500000 |  |  |  | 1 |  |  | DED and POW Approved |  | 2020-01-10 | NPJR
2019 | REGION X | MISAMIS ORIENTAL | BINUANGAN | LOCAL ACCESS ROAD IN MABINI | LOCAL ACCESS ROAD | MABINI | 4000000 |  |  |  | 1 |  |  | DED and POW Approved |  | 2020-01-10 | NPJR
2019 | REGION X | MISAMIS ORIENTAL | CLAVERIA | LOCAL ACCESS ROAD IN BRGY. POBLACION | LOCAL ACCESS ROAD | BRGY. POBLACION | 5611000 |  |  |  |  | 1 |  | 54.56% PHYSICAL ACCOMPLISHMENT | AS OF 03/11/2020 | 2020-04-27
2019 | REGION X | MISAMIS ORIENTAL | GITAGUM | LOCAL ACCESS ROAD IN BRGY. MATANGAD | LOCAL ACCESS ROAD | BRGY. MATANGAD | 4645000 | [5 empty] | 1 | COMPLETED | AS OF 4/15/2020 SWA | 2020-06-17
2019 | REGION X | MISAMIS ORIENTAL | GITAGUM | LOCAL ACCESS ROAD IN BRGY. QUEZON | LOCAL ACCESS ROAD | BRGY. QUEZON | 6150000 | [5 empty] | 1 | COMPLETED | AS OF 4/25/2020 SWA | 2020-06-17
2019 | REGION X | MISAMIS ORIENTAL | KINOGUITAN | LOCAL ACCESS ROAD IN BRGY. CALUBO | LOCAL ACCESS ROAD | BRGY. CALUBO | 4896000 |  |  |  | 1 |  |  | DED and POW Approved |  | 2020-01-10
2019 | REGION X | MISAMIS ORIENTAL | LAGUINDINGAN | LOCAL ACCESS ROAD IN BARANGAY GASI | LOCAL ACCESS ROAD | BARANGAY GASI | 3136000 | [5 empty] | 1 | COMPLETED | AS OF DEC.23, 2019-FEB. 27, 2020 SWA | 2020-03-06
2019 | REGION X | MISAMIS ORIENTAL | LAGUINDINGAN | LOCAL ACCESS ROAD IN BARANGAY MAUSWAGON | LOCAL ACCESS ROAD | BARANGAY MAUSWAGON | 3136000 | [5 empty] | 1 | COMPLETED | AS OF DEC.23, 2019-FEB. 27, 2020 SWA | 2020-03-06
2019 | REGION X | MISAMIS ORIENTAL | LIBERTAD | LOCAL ACCESS ROAD IN TABOO-POBLACION | LOCAL ACCESS ROAD | TABOO-POBLACION | 6022000 |  |  |  |  | 1 |  | 67.28% PHYSICAL ACCOMPLISHMENT | AS OF 5/28/2020 SWA | 2020-06-05
2019 | REGION X | MISAMIS ORIENTAL | LUGAIT | LOCAL ACCESS ROAD IN BARANGAY AYA-AYA | LOCAL ACCESS ROAD | BARANGAY AYA-AYA | 6675000 |  |  |  |  | 1 |  | 42.72% PHYSICAL ACCOMPLISHMENT | AS OF 2/15/2020 SWA | 2020-03-03
2019 | REGION X | MISAMIS ORIENTAL | MAGSAYSAY | LOCAL ACCESS ROAD IN BARANGAY KAUSWAGAN | LOCAL ACCESS ROAD | BARANGAY KAUSWAGAN | 10005000 |  |  |  | 1 |  |  | DED and POW Approved |  | 2020-01-10
2019 | REGION X | MISAMIS ORIENTAL | MEDINA | LOCAL ACCESS ROAD IN BARANGAY SOUTH POBLACION | LOCAL ACCESS ROAD | BARANGAY SOUTH POBLACION | 6448000 |  |  |  |  | 1 |  | 90.35% PHYSICAL ACCOMPLISHMENT | AS OF 03/09/2020 SWA | 2020-06-23
2019 | REGION X | MISAMIS ORIENTAL | NAAWAN | LOCAL ACCESS ROAD IN BRGY. DON PEDRO | LOCAL ACCESS ROAD | BRGY. DON PEDRO | 6205000 |  |  |  | 1 |  |  | DED and POW Approved |  | 2020-01-10
2019 | REGION X | MISAMIS ORIENTAL | OPOL | LOCAL ACCESS ROAD IN PATAG | LOCAL ACCESS ROAD | PATAG | 11730000 |  |  |  | 1 |  |  | DED and POW Approved |  | 2020-01-10
2019 | REGION X | MISAMIS ORIENTAL | SALAY | LOCAL ACCESS ROAD IN BRGY. SARAY | LOCAL ACCESS ROAD | BRGY. SARAY | 11051000 |  |  |  |  | 1 |  | 94.58% PHYSICAL ACCOMPLISHMENT | AS OF 06/15/2020 SWA | 2020-06-26
2019 | REGION X | MISAMIS ORIENTAL | TAGOLOAN | LOCAL ACCESS ROAD IN POBLACION | LOCAL ACCESS ROAD | POBLACION | 7781000 |  |  |  | 1 |  |  | DED and POW Approved |  | 2020-01-10
2019 | REGION X | MISAMIS ORIENTAL | TALISAYAN | LOCAL ACCESS ROAD IN BRGY. SIBANTANG | LOCAL ACCESS ROAD | BRGY. SIBANTANG | 5106000 |  |  |  |  | 1 |  | 98.70% PHYSICAL ACCOMPLISHMENT | AS OF MAY2020 | 2020-06-05
2019 | REGION X | MISAMIS ORIENTAL | VILLANUEVA | LOCAL ACCESS ROAD IN BARANGAY LOOC | LOCAL ACCESS ROAD | BARANGAY LOOC | 5832000 |  |  |  | 1 |  |  | DED and POW Approved |  | 2020-01-10
SUB-TOTAL |  |  | 16 | 23 |  |  | 140841000 | 0 | 0 | 1 | 11 | 7 | 4
2019 | REGION X | MISAMIS ORIENTAL | INITAO | LOCAL BRIDGE IN BRGY. APAS | LOCAL BRIDGES | BRGY. APAS | 11127000 |  |  |  | 1 |  |  | DED and POW Approved |  | 2020-01-10 | NPJR
SUB-TOTAL |  |  | 1 | 1 |  |  | 11127000 | 0 | 0 | 0 | 1 | 0 | 0
TOTAL |  |  | 17 | 24 |  |  | 151968000 | 0 | 0 | 1 | 12 | 7 | 4
GRAND TOTAL |  |  | 70 | 90 |  |  | 563065000 | 6 | 0 | 3 | 26 | 41 | 20

## 2019 AM-WATER
REGION X - AM
2019 AM-WATER
as of June 26, 2020
FY | REGION | PROVINCE | CITY / MUNICIPALITY | NAME OF PROJECT | PHYSICAL TARGETS/OUTPUTS | BARANGAY | ORIGINAL ALLOCATION | CANCELLED | DED/POW PREPARATION | FINALIZATION | PROCUREMENT | ON-GOING | COMPLETED | STATUS | REMARKS | DATE UPDATED
2019 | REGION X | BUKIDNON | IMPASUG-ONG | CONSTRUCTION OF WATER SYSTEM | POTABLE WATER SUPPLY SYSTEM |  | 6007000 |  |  |  |  | 1 |  | ONGOING IMPLEMENTATION | AS OF 3/25/2020 | 2020-04-27
2019 | REGION X | BUKIDNON | KALILANGAN | REHABILITATION OF LEVEL III POTABLE WATER SYSTEM | POTABLE WATER SUPPLY SYSTEM | Cogo, Maca-opao | 6628000 |  |  |  | 1 |  |  | Procurement Process | AS OF MAY 20, 2020 SWA | 2020-06-05
2019 | REGION X | BUKIDNON | KITAOTAO | CONSTRUCTION OF WATER SYSTEM | POTABLE WATER SUPPLY SYSTEM |  | 5639000 | 1 | [5 empty] | CANCELLED | CANCELLED (NO FUND DOWNLOAD) | 2020-02-24 | FCLA
2019 | REGION X | BUKIDNON | LANTAPAN | CONSTRUCTION OF LEVEL II WATER SYSTEM | POTABLE WATER SUPPLY SYSTEM |  | 7052000 |  |  |  |  | 1 |  | 26.71% PHYSICAL ACCOMPLISHED | AS OF 05/20/2020 | 2020-06-03
2019 | REGION X | BUKIDNON | MANOLO FORTICH | REHABILITATION/IMPROVEMENT OF WATER SYSTEM IN BRGY. MINSURO | POTABLE WATER SUPPLY SYSTEM | MINSURO | 3000000 |  |  |  |  | 1 |  | 50.59% PHYSICAL ACCOMPLISHED | AS OF 05/22/2020 SWA | 2020-06-05
2019 | REGION X | BUKIDNON | MANOLO FORTICH | EXPANSION OF WATER SYSTEM IN BRGY. DICKLUM | POTABLE WATER SUPPLY SYSTEM | DICKLUM | 4842000 |  |  |  |  | 1 |  | 0.26% PHYSICAL ACCOMPLISHED | AS OF 05/22/2020 SWA | 2020-06-05
TOTAL |  |  | 5 | 6 |  |  | 33168000 | 1 | 0 | 0 | 1 | 4 | 0
2019 | REGION X | CAMIGUIN | MAMBAJAO | REHAB/ IMPROVEMENT OF LEVEL II WATER SYSTEM | POTABLE WATER SUPPLY SYSTEM |  | 2500000 |  |  | 1 |  |  |  | DED/POW FINALIZATION |  | 2020-02-24 | KA
2019 | REGION X | CAMIGUIN | SAGAY | CONSTRUCTION OF LEVEL II WATER SYSTEM IN SUDLON, BACNIT | POTABLE WATER SUPPLY SYSTEM | SUDLON, BACNIT | 8000000 |  |  |  | 1 |  |  | Procurement Process | FOR ISSUANCE OF NTP | 2020-01-24 | FLOR
2019 | REGION X | CAMIGUIN | SAGAY | REHABILITATION/IMPROVEMENT OF WATER SYSTEM IN POBLACION | POTABLE WATER SUPPLY SYSTEM | POBLACION | 1550000 |  |  |  | 1 |  |  | Procurement Process | FOR ISSUANCE OF NTP | 2020-01-24 | FLOR
TOTAL |  |  | 2 | 3 |  |  | 12050000 | 0 | 0 | 1 | 2 | 0 | 0
2019 | REGION X | LANAO DEL NORTE | KOLAMBUGAN | CONSTRUCTION OF WATER SUPPLY SYSTEM | POTABLE WATER SUPPLY SYSTEM |  | 3000000 |  |  |  | 1 |  |  | DED/POW APPROVED |  | 2020-02-24 | ND
2019 | REGION X | LANAO DEL NORTE | LINAMON | REHAB/ IMPROVEMENT OF LEVEL II WATER SYSTEM | POTABLE WATER SUPPLY SYSTEM |  | 6187000 |  |  |  | 1 |  |  | DED/POW APPROVED | AS OF 05/22/2020 BID OPENING | 2020-01-24 | ND
2019 | REGION X | LANAO DEL NORTE | PANTAR | CONSTRUCTION OF WATER SUPPLY SYSTEM | POTABLE WATER SUPPLY SYSTEM |  | 2000000 |  |  |  |  | 1 |  | 63.52% PHYSICAL ACCOMPLISHMENT | AS OF 05/20/2020 | 2020-05-27
2019 | REGION X | LANAO DEL NORTE | SULTAN NAGA DIMAPORO | NEW CONSTRUCTION OF LEVEL II POTABLE WATER SUPPLY SYSTEM IN BRGY. KAUSWAGAN | POTABLE WATER SUPPLY SYSTEM | BRGY. KAUSWAGAN | 2774000 | [5 empty] | 1 | COMPLETED | AS OF 003/19/2020 SWA | 2020-03-19
2019 | REGION X | LANAO DEL NORTE | SULTAN NAGA DIMAPORO | NEW CONSTRUCTION OF LEVEL II POTABLE WATER SUPPLY SYSTEM IN BRGY. TAGULO | POTABLE WATER SUPPLY SYSTEM | BRGY. TAGULO | 3000000 | [5 empty] | 1 | COMPLETED | AS OF 03/19/2020 SWA | 2020-03-19
TOTAL |  |  | 4 | 5 |  |  | 16961000 | 0 | 0 | 0 | 2 | 1 | 2
2019 | REGION X | MISAMIS OCCIDENTAL | JIMENEZ | REHABILITATION/IMPROVEMENT OF LEVEL III WATERWORKS SYSTEM | POTABLE WATER SUPPLY SYSTEM |  | 11529000 |  |  |  |  | 1 |  | 24.76% PHYSICAL ACCOMPLISHMENT | AS OF 04/15/2020 SWA | 2020-04-15
TOTAL |  |  | 1 | 1 |  |  | 11529000 | 0 | 0 | 0 | 0 | 1 | 0
2019 | REGION X | MISAMIS ORIENTAL | BINUANGAN | REHABILITATION OF LEVEL III POTABLE WATER SYSTEM | POTABLE WATER SUPPLY SYSTEM |  | 2362000 |  |  |  | 1 |  |  | DED and POW APPROVED |  | 2020-02-24 | NPJR
2019 | REGION X | MISAMIS ORIENTAL | JASAAN | EXPANSION OF WATER SYSTEM | POTABLE WATER SUPPLY SYSTEM |  | 11584000 |  |  |  |  | 1 |  | 59.91% PHYSICAL ACCOMPLISHMENT | AS OF 03/19/2020 SWA | 2020-04-28
2019 | REGION X | MISAMIS ORIENTAL | LAGONGLONG | CONSTRUCTION OF WATER SUPPLY SYSTEM | POTABLE WATER SUPPLY SYSTEM |  | 5047000 |  |  |  | 1 |  |  | DED and POW Approved |  | 2019-08-19
2019 | REGION X | MISAMIS ORIENTAL | MANTICAO | EXPANSION OF WATER SYSTEM | POTABLE WATER SUPPLY SYSTEM |  | 9877000 |  |  |  | 1 |  |  | DED and POW Approved |  | 2019-08-19
2019 | REGION X | MISAMIS ORIENTAL | SUGBONGCOGON | EXPANSION OF WATER SYSTEM | POTABLE WATER SUPPLY SYSTEM |  | 7631000 |  |  |  | 1 |  |  | DED and POW Approved |  | 2019-08-19
TOTAL |  |  | 5 | 5 |  |  | 36501000 | 0 | 0 | 0 | 4 | 1 | 0
GRAND TOTAL |  |  | 17 | 20 |  |  | 110209000 | 1 | 0 | 1 | 9 | 7 | 2

## 2020 LGSF-AM
REGION X - AM
2020 AM - OTHERS
as of June 26, 2020
| FY | REGION | PROVINCE | CITY / MUNICIPALITY | PROJECT TYPE | PROJECT TITLE | PHYSICAL TARGET/ OUTPUT | BARANGAY | NG ALLOCATION | CANCELLED | DED/POW PREPARATION | FINALIZATION | PROCUREMENT | ON-GOING | COMPLETED | STATUS | REMARKS | DATE UPDATED
002 | 2020 | REGION X | BUKIDNON | CABANGLASAN | Local Access Road | Upgrading and improvement of Proper Anlugan to Compound Road | Concreting of Municipal Gravel Road (500meters x 6.1m x 0.20m PCCP) with Concrete Canal | Proper Anlugan | 7632000 |  |  |  | 1 |  |  | DED & POW APPROVED |  | 2020-03-19
003 | 2020 | REGION X | BUKIDNON | DAMULOG | Local Access Road | Concreting of Municipal Streets with Cross Drains | 0.600Km Concreted Municipal streets with installation of Cross Drains | Poblacion: Jct. Andress Bonifacio st. to Manuel Roxas st. to jct. San Isidro st. | 7200000 |  |  |  | 1 |  |  | DED & POW APPROVED
004 | 2020 | REGION X | BUKIDNON | DAMULOG | Local Access Road | Concreting of Municipal Streets with Cross Drains | 0.446Km Concreted Municipal streets with installation of Cross Drains | Poblacion: Jct. National Road to Manuel L. Quezon st. via. F. Quirino st. to jct. Aglipay st. | 5352000 |  |  |  | 1 |  |  | DED & POW APPROVED
005 | 2020 | REGION X | BUKIDNON | DANGCAGAN | Local Access Road | Concreting of Brgy. Road @ Brgy. Kianggat - Brgy. San Vicente, Dangcagan, Bukidnon | Concreting of 500meter road (500m x 5.0m x 0.20m PCCP) | Brgy. Kianggat, Dangcagan, Bukidnon | 6000000 |  |  |  | 1 |  |  | DED & POW APPROVED |  | 2020-02-07
006 | 2020 | REGION X | BUKIDNON | DANGCAGAN | Local Access Road | Concreting of Brgy. Road @ Brgy. Dolorosa, Dangcagan, Bukidnon | Concreting of 500meter road (500m x 5.0m x 0.20m PCCP) | Brgy. Dolorosa, Dangcagan, Bukidnon | 6014000 |  |  |  | 1 |  |  | DED & POW APPROVED |  | 2020-02-07
007 | 2020 | REGION X | BUKIDNON | DON CARLOS | Local Access Road | Upgrading of Local Access Road | 0.220 Km of Municipal Road Rehabilitated | Brgy. Don Carlos Norte | 4334000 |  |  |  | 1 |  |  | DED & POW APPROVED
008 | 2020 | REGION X | BUKIDNON | IMPASUG-ONG | Local Access Road | Concreting of 700 meters Ilignan to Guihean Farm to Market Road | Concreting of Farm to Market Road, 700 meters x 5.0 meters width x 0.20 meter thick Portland Cement Concrete Concrete Pavement (PCCP), installation of 3 station 7.0m x 910mm diameter RCPC cross drainage with stone masonry head wall and catch basin and 600 meters stone masonry line canal | Sitio Ilignan to Brgy. Guihean | 7442000 |  |  |  | 1 |  |  | DED & POW APPROVED |  | 2020-02-07
009 | 2020 | REGION X | BUKIDNON | KADINGILAN | Local Access Road | Concreting of FMR at Sitio Maituba, Bagongbayan | Concreting of Brgy. Road (400m x 5.0m x 0.2m PCCP) | Sitio Maituba, Bagongbayan | 4989000 |  |  | 1 |  |  |  | DED & POW FINALIZATION
010 | 2020 | REGION X | BUKIDNON | KALILANGAN | Local Access Road | Rehabilitation of Manggahan Road | 400m x 5.0m x 0.20m PCCP | Brgy. Ninoy Aquino, Kalilangan, Bukidnon | 4989000 |  |  | 1 |  |  |  | DED & POW FINALIZATION |  | 2020-02-26
011 | 2020 | REGION X | BUKIDNON | KIBAWE | Local Access Road | Concreting of Municipal Street | 860 meters of Municipal Road Concreted | Brgy. Palma 1. Portion of Gen. Antonio st. - Gregorio del Pilar st. 2. MH Del Pilar st. - Gen. Santos st. | 11207000 |  |  |  | 1 |  |  | DED & POW APPROVED |  | 2020-01-27 | FCLA
016 | 2020 | REGION X | BUKIDNON | MALITBOG | Local Access Road | Concreting/rehabilitation of San Luis - Lapu lapu FMR | Concreting/rehabilitation of 0.350Km length pavement | Sitio Lapu lapu, Brgy. Omaging & San Luis | 4630000 |  |  | 1 |  |  |  | DED & POW FINALIZATION |  | 2020-06-17
019 | 2020 | REGION X | BUKIDNON | PANGANTUCAN | Local Access Road | Concreting of Municipal Street along Eboney St (from Jct. Rizal St. to Jct. Lawin St.) @ Barangay Poblacion | Concreting 300 meter road (300m x 6mx .20m PCCP) | Barangay Poblacion (along Eboney St. from Jct. Rizal to Jct Lawin St.) | 4641000 |  |  |  | 1 |  |  | DED & POW APPROVED | WAITING FO FUND RELEASE/ SWA | 2020-06-11
020 | 2020 | REGION X | BUKIDNON | QUEZON | Local Access Roads | Concreting of FMR from Balangay 2 to Balangay 1B, Poblacion | 800 LM | Poblacion | 8052000 |  |  |  | 1 |  |  | DED & POW APPROVED |  | 02/26/0202
021 | 2020 | REGION X | BUKIDNON | QUEZON | Local Access Roads | Construction of Box Culvert | 1 unit 4mx4m Double Barrel Box Culvert | Sta. Felomina | 4500000 |  |  |  | 1 |  |  | DED & POW APPROVED |  | 2020-02-26
023 | 2020 | REGION X | BUKIDNON | SUMILAO | Local Access Road | Upgrading & improvement of Brgy. Road | Concreting of Brgy. Road (345m x 5.0m x 0.20m PCCP) w/ 2 stations of RCPC Cross Drains. | Brgy. Kisolon | 3204000 |  |  |  | 1 |  |  | DED & POW APPROVED |  | 2020-02-27
024 | 2020 | REGION X | BUKIDNON | SUMILAO | Local Access Road | Upgrading & improvement of Brgy. Road | Concreting of Brgy. Road (325m x 5.0m x 0.20m PCCP) w/ 2 stations of 0.90m RCPC Cross Drains. | Brgy. Vista Villa | 3000000 |  |  |  | 1 |  |  | DED & POW APPROVED |  | 2020-02-27
025 | 2020 | REGION X | BUKIDNON | SUMILAO | Local Access Road | Upgrading & improvement of Brgy. Road | Concreting of Brgy. Road (319m x 5.0m x 0.20m PCCP) w/ 1 stations of RCPC Cross Drains. | Brgy. San Roque | 3000000 |  |  |  | 1 |  |  | DED & POW APPROVED |  | 2020-02-27
026 | 2020 | REGION X | BUKIDNON | SUMILAO | Local Access Road | Upgrading & improvement of Brgy. Road | Concreting of Brgy. Road (320m x 5.0m x 0.20m PCCP) w/ 2 stations of RCPC Cross Drains. | Brgy. Licoan | 3000000 |  |  |  | 1 |  |  | DED & POW APPROVED |  | 2020-02-27
027 | 2020 | REGION X | BUKIDNON | TALAKAG | Local Access Road | Upgrading of Babalayan - Batang FMR | 330 meters Length W = 5.0m T = 0.20m shoulder bothsides = 1.50m | Sitio Camaman-an, Cosina | 4989000 |  |  |  | 1 |  |  | DED & POW FOR APPROVED |  | 2020-04-21
|  |  |  | 13 | 19 |  |  |  | 104175000 | 0 | 0 | 3 | 16 | 0 | 0
018 | 2020 | REGION X | BUKIDNON | MARAMAG | Municipal Building | Construction of 2-storey Municipal Building | Construction of 460 sq.m. 2-storey Municipal Building | Anahawon | 9254000 |  |  |  | 1 |  |  | DED & POW APPROVED |  | 2020-06-19
|  |  |  | 1 | 1 |  |  |  | 9254000 | 0 | 0 | 0 | 1 | 0 | 0
|  |  |  | 14 | 20 |  |  |  | 113429000 | 0 | 0 | 3 | 17 | 0 | 0
029 | 2020 | REGION X | CAMIGUIN | CATARMAN | Local Access Road | Poblacion-Madling-Quidag-um Access Road Project | 600 linear meters PCCP x 6.1 meters width X 0.20 meter thickness; drainage canal on both sides | Purok 7, Poblacion; | 12204000 |  |  | 1 |  |  |  | DED & POW FINALIZATION
030 | 2020 | REGION X | CAMIGUIN | GUINSILIBAN | Local Access Road | Continuation of Local Access Road | 300 meters Local Access Road Opening in Barangay South Poblacion to Sitio Kiwakat | Barangay from South Poblacion to Sitio Kiwakat South Poblacion, Guinsiliban | 4630000 |  | 1 |  |  |  |  | NO SUBMISSION
031 | 2020 | REGION X | CAMIGUIN | MAHINOG | Local Access Road | Concreting of Alternate Road in Poblacion | 323.3 meters of alternate road rehabilitated | Poblacion | 4067000 |  |  | 1 |  |  |  | DED & POW FOR FINALIZATION | 2020-06-09 | 2020-05-21
036 | 2020 | REGION X | CAMIGUIN | SAGAY | Roads and Bridges | Local Access Road - Concreting of Vasquez St., to Mayana Cemetery Road | 500 linear meter Road opening & concreting of Vasquez St., to Mayana Cemetery Road | Brgy. Poblacion and Brgy. Mayana | 7000000 |  |  | 1 |  |  |  | DED & POW FOR FINALIZATION |  | 2020-05-11
|  |  |  | 4 | 4 |  |  |  | 27901000 | 0 | 1 | 3 | 0 | 0 | 0
032 | 2020 | REGION X | CAMIGUIN | MAHINOG | Drainage System | Construction of drainage system in Poblacion | 300 meters drainge canalrehabitated along Burgos St., with dimension of 1.8 m x 1.2 m 290 meters drainge canal rehabitated along Quezon St., with dimension of 0.5 m x 0.6 m 180 meters drainge canalrehabitated along Luna St., with dimension of 0.5 m x 0.6 m 30 meters drainge canalrehabitated along Road 1 with dimension of 1.8 m x 1.2 m |  | 4000000 |  |  | 1 |  |  |  | DED & POW FOR FINALIZATION |  | 2020-06-05
033 | 2020 | REGION X | CAMIGUIN | MAMBAJAO | Evacuation Center Facility Improvement | Improvement/Rehab. of Camiguin Evacuation Center | Perimeter fence constructed & evacuation ground improved | Poblacion, Mambajao, Camiguin | 3000000 |  |  | 1 |  |  |  | DED & POW FOR FINALIZATION |  | 2020-05-11
034 | 2020 | REGION X | CAMIGUIN | MAMBAJAO | Improvement of Institional Facilities | Improvement of Municipal Ground at Government Center | Municipal Ground Improved | Lakas, Poblacion, Mambajao | 2727000 |  |  | 1 |  |  |  | DED & POW FOR FINALIZATION |  | 2020-05-11
|  |  |  | 2 | 3 |  |  |  | 9727000 | 0 | 0 | 3 | 0 | 0 | 0
|  |  |  | 6 | 7 |  |  |  | 37628000 | 0 | 1 | 6 | 0 | 0 | 0
038 | 2020 | REGION X | LANAO DEL NORTE | BACOLOD | Local Access Road | Road Concreting | Concreting of Municipal Road (Earth to Concrete) 850MLM x 5M x 0.20m upgraded from Binuni to Poblacion | Binuni to Poblacion | 11897000 |  |  | 1 |  |  |  | DED & POW FINALIZATION |  | 2020-02-24
039 | 2020 | REGION X | LANAO DEL NORTE | BALOI | Local Access Road | Concreting of Local Access Road | concreting of 450 linear meter farm to market road with improvement of submarine bridge | Brgy. Sigayan | 12204000 |  |  |  | 1 |  |  | DED & POW APPROVED
040 | 2020 | REGION X | LANAO DEL NORTE | BAROY | Local Access Road | Upgrading and Improvement of Barangay Tinubdan Road | Concreting barangay gravel road (6.0m x 0.20m x 1km PCCP) | Brgy. Tinubdan | 12204000 |  |  | 1 |  |  |  | DED & POW FOR FINALIZATION |  | 2020-03-02
041 | 2020 | REGION X | LANAO DEL NORTE | KAPATAGAN | Local Access Road | Rehabilitataion/Concreting of Sitio Putol - Tulay Buhangin Access Road Phase IV | Concreting of 1 km cincumferential road ( 5.00m width, 0.20m thickness, 1.5m should both sides) with 1-unit double barrel box cuilvert, 8 lines 36" dia RCPC with head wall and grouted riprap slope protection | Poblacion | 12204000 |  |  |  | 1 |  |  | DED & POW APPROVED |  | 2020-04-17
043 | 2020 | REGION X | LANAO DEL NORTE | KAUSWAGAN | Infrastructure | Local Access Road | Concreting of 300 linear meter access road | Brgy. Tugar, Kauswagan, Lanao del Norte | 3000000 |  |  |  | 1 |  |  | DED & POW APPROVED |  | 2020-02-26
046 | 2020 | REGION X | LANAO DEL NORTE | LALA | FMR | Concreting of (1.18km) Lanipao to Cabasagan Spring FMR | 1.18 kilometers of barangay to be concreted to benefit the commuters, travelers and farmers in the community | Barangay Cabasagan | 12204000 |  |  |  | 1 |  |  | DED & POW APPROVED |  | 2020-02-26
049 | 2020 | REGION X | LANAO DEL NORTE | MAGSAYSAY | LAR | Concreting of Access Road to Magsaysay National High School | 500 meters | Poblacion | 5000000 |  |  |  | 1 |  |  | DED & POW APPROVED |  | 2020-06-26
050 | 2020 | REGION X | LANAO DEL NORTE | MAGSAYSAY | LAR | Concreting of Access Road to Farm Tourism Site | 500 meters | Poblacion | 5055000 |  |  |  | 1 |  |  | DED & POW APPROVED |  | 2020-06-26
051 | 2020 | REGION X | LANAO DEL NORTE | MAIGO | LAR | Concreting of Access Road | 350 meters | Purok 6, Labuay, Maigo, Lanao del Norte | 4000000 |  |  | 1 |  |  |  | DED & POW FINALIZATION
052 | 2020 | REGION X | LANAO DEL NORTE |  |  |  | 850 meters | Purok 6, Balagatasa, Maigo, Lanao del Norte | 7897000
053 | 2020 | REGION X | LANAO DEL NORTE | MATUNGAO | LAR | Concreting of Brgy. Poblacion to Puntod Local Access Road | 740 meters | Brgy. Poblacion and Brgy. Puntod, Matungao, Lanao del Norte | 12552000 |  |  |  | 1 |  |  | DED & POW APPROVED |  | 2020-04-22
054 | 2020 | REGION X | LANAO DEL NORTE | MUNAI | LAR | Concreting of Matampay to Ramain Access Road | 1.1 KM | Brgy. Ramain | 14243000 |  |  |  | 1 |  |  | DED & POW APPROVED
056 | 2020 | REGION X | LANAO DEL NORTE | PANTAO RAGAT | LAR | Rehabilitation/Concreting of Madaya Local Access Road | Concreting municipal gravel road (1 km(l) x 6m(w) x 0.20m PCCP) | Brgy. Madaya | 14243000 |  |  |  | 1 |  |  | DED & POW APPROVED
062 | 2020 | REGION X | LANAO DEL NORTE | POONA PIAGAPO | LAR | Concreting of Nunungan - Tangclao Local Access Road | 1km | Nunungan - Tangclao | 10000000 |  |  |  | 1 |  |  | DED & POW APPROVED |  | 2020-04-17
063 | 2020 | REGION X | LANAO DEL NORTE | POONA PIAGAPO | LAR | Concreting of Poblacion Access Road | 300 meter | Poblacion Proper | 2552000 |  |  |  | 1 |  |  | DED & POW APPROVED |  | 2020-03-02
064 | 2020 | REGION X | LANAO DEL NORTE | SALVADOR | LAR | Concreting of Loacal Access Road of Sudion - Camp 3 Road | 280 meters | Brgy. Camp 3 | 3555000 |  |  | 1 |  |  |  | DED & POW FINALIZATION
068 | 2020 | REGION X | LANAO DEL NORTE | SAPAD | LAR | Concreting of Barangay Road | 300 meters | Barangay Poblacion | 3290100 |  |  | 1 |  |  |  | DED & POW FINALIZATION |  | 2020-03-06
069 | 2020 | REGION X | LANAO DEL NORTE | SAPAD | LAR | Concreting of Barangay Road | 657 meters | Barangay Poblacion | 5761900 |  |  | 1 |  |  |  | DED & POW FINALIZATION |  | 2020-03-06
071 | 2020 | REGION X | LANAO DEL NORTE | SULTAN NAGA DIMAPORO | LAR | Concreting of 310 ln.m barangay road from junction Mamagum-Calipapa to junction Mahayahay-Cabongbongan road aliignment | 310 ln.m | Brgy. Mamagum, Sultan Naga Dimaporo | 5277000 |  |  |  | 1 |  |  | DED & POW APPROVED |  | 2020-03-02
072 | 2020 | REGION X | LANAO DEL NORTE | TAGOLOAN | LAR | Concreting of Dimayo to Kiazar Road | Road concreted | Dimayon | 4799000 |  |  |  | 1 |  |  | DED & POW APPROVED |  | 2020-03-02
073 | 2020 | REGION X | LANAO DEL NORTE | TANGCAL | Local Access Road | Rehabilitation of Road from Poblacion to Bubong | 0.500 Km | Poblacion, Bubong | 6000000 |  |  |  | 1 |  |  | DED & POW APPROVED |  | 2020-06-03
076 | 2020 | REGION X | LANAO DEL NORTE | TUBOD | LAR | Concreting of Legaspino-GK National Highway Alternate Road | 875m road constructed/concreted | Poblacion | 11897000 |  |  |  | 1 |  |  | DED & POW APPROVED |  | 2020-02-26
|  |  |  | 18 | 21 |  |  |  | 179835000 | 0 | 0 | 6 | 15 | 0 | 0
042 | 2020 | REGION X | LANAO DEL NORTE | KAUSWAGAN | Infrastructure | Construction of Youth Home Care/ Reformatory Center | Two storey youth care/ reformatory center to cater street children, with estimated area of 180 sq.m with kitchen, dining room, living room and bed rooms separate from male and female with rainwater collector and medical care room | Bargy. Poblacion, Kauswagan, Lanao del Norte | 3500000 |  |  |  | 1 |  |  | DED & POW APPROVED
044 | 2020 | REGION X | LANAO DEL NORTE | KAUSWAGAN | Infrastructure | Improvement of Existing Drug Rehabilititation Center | Constructed a drug rehabilitation center that will support the CBRP and Balay Silangan Program with the following facilities: bedrooms, comfort rooms, living room, conference hall, prayer room and health care room and sport facilities | Bagumbayan, Kauswagan,Lano del Norte | 2754000 |  |  |  | 1 |  |  | DED & POW APPROVED |  | 2020-02-26
045 | 2020 | REGION X | LANAO DEL NORTE | KOLAMBUGAN | Local Access Road | Concreting of 650 lm FMR Barangay Kulasihan-Lumao Road | Concreting of 2-lane 650 lm FMR leading towards Mangrove Eco-Tourism Park | Brgy. Kulasihan, Kolambugan, Lanao del Norte | 9254000 |  |  |  | 1 |  |  | DED & POW APPROVED |  | 2020-06-24
048 | 2020 | REGION X | LANAO DEL NORTE | MAGSAYSAY | Other Infra | Construction of Concrete line canal Poblacion, Magsaysay,Lanao del Norte | 150 meters | Poblacioon | 1500000 |  |  |  | 1 |  |  | DED & POW APPROVED |  | 2020-06-26
055 | 2020 | REGION X | LANAO DEL NORTE | NUNUNGAN | Other Infra | Construction of Cultural Center | 500 Sq.m | Brgy. Poblacion | 9550000 |  |  |  | 1 |  |  | DED & POW APPROVED |  | 2020-04-22
058 | 2020 | REGION X | LANAO DEL NORTE | PANTAR | FLOOD CONTROL | Construction of Slope Protection | Construction of Slope protection | Brgy. Bubong Madaya | 500000 |  |  | 1 |  |  |  | DED & POW FOR FINALIZATION |  | 2020-02-26
059 | 2020 | REGION X | LANAO DEL NORTE | PANTAR | LAR | Rehabilitation of Cabasaran Box Culvert | Rehabilitation of Box Culvert with approx. of 9m length. | Brgy. Cabasaran | 1500000 |  |  |  | 1 |  |  | DED & POW FOR APPROVED |  | 2020-02-26
060 | 2020 | REGION X | LANAO DEL NORTE | PANTAR | Other Infra | Construction of DRRM Building | Construction of one storey Disaster Risk and Reduction Management Building with basic facilities | Brgy. Poblacion | 3000000 |  |  |  | 1 |  |  | DED & POW FOR APPROVED |  | 2020-02-26
061 | 2020 | REGION X | LANAO DEL NORTE | PANTAR | Other Infra | Construction of Covered Court | Construction of 16m x 30m Covered Court with 6-7m height | Brgy. Punod | 4000000 |  |  | 1 |  |  |  | DED & POW FOR FINALIZATION |  | 2020-02-26
065 | 2020 | REGION X | LANAO DEL NORTE | SALVADOR | Evacuation Center | Improvement of Evacuation Center | water system, installation of temporary partition of the facility | Brgy Inasagan | 1000000 |  |  | 1 |  |  |  | DED & POW FINALIZATION
066 | 2020 | REGION X | LANAO DEL NORTE | SALVADOR | Footbridge | Construction of Footbridge | 75 meters of cable suspended bridge | Brgy Poblacion | 5500000 |  |  | 1 |  |  |  | DED & POW FINALIZATION
067 | 2020 | REGION X | LANAO DEL NORTE | SALVADOR | Drug Rehab Center | Improvement of Drug Rehabilitation Center | Existing (9.0m x 15m) Drug Rehabilitation Center/Bahay Silangan | Brgy Poblacion | 1500000 |  |  | 1 |  |  |  | DED & POW FINALIZATION
070 | 2020 | REGION X | LANAO DEL NORTE | SAPAD | Evacuation Center and Risk Reduction-Related Equipment | Construction of Evacuation Center | Elevated evacuation Center with area of 225 sq.m and following facilities: comfort rooms, kitchen, clinic, storage area, and DRRM Office | Barangay Lower Sapad | 3500000 |  | 1 |  |  |  |  | NO SUBMISSION
074 | 2020 | REGION X | LANAO DEL NORTE | TANGCAL | Local Access Bridge | Construction of Banisilon Box Culvert | 20 Lm | Poblacion, Big Banisilon | 1719000 |  |  |  | 1 |  |  | DED & POW APPROVED |  | 2020-06-03
075 | 2020 | REGION X | LANAO DEL NORTE | TANGCAL | Multi-Purpose Building | Construction of Poblacion Multi-Purpose Building | Area = 15m x 30m | Poblacion | 2000000 |  |  |  | 1 |  |  | DED & POW APPROVED |  | 2020-06-03
|  |  |  | 8 | 15 |  |  |  | 50777000 | 0 | 1 | 5 | 9 | 0 | 0
|  |  |  | 26 | 36 |  |  |  | 230612000 | 0 | 1 | 11 | 24 | 0 | 0
078 | 2020 | REGION X | MISAMIS OCCIDENTAL | ALORAN | Local Access Raod | Concreting of Pelong-Culpan Road and Parking area (Sanitary Landfill area) | 540lm of Pelong-Culpan Road and Parking Area in the Sanitary Landfill area concreted | Brgy.Culpan Road: | 6257000 |  |  | 1 |  |  |  | DED & POW FINALIZATION |  | 2020-05-27
079 | 2020 | REGION X | MISAMIS OCCIDENTAL | BALIANGAO | Local Access Road | Rehabilitation/ Improvement of Local Access Road at Brgy. Lusot | 0.49KM of Barangay Road Rehabilitated | Brgy. Lusot (BP:8°36'19.3"N, 123°37'14.69"E EP:8°36'20"N, 123°37'11.2"E | 4641000 |  |  | 1 |  |  |  | DED & POW FINALIZATION
083 | 2020 | REGION X | MISAMIS OCCIDENTAL | CALAMBA | Local Access Road | Upgrading and Improvement of Brgy. Road of Libertad Phase II | Concreting of 2-lane Municipal Road - 341 meters x 6 meters x 0.20 meters PCCP with 0.6 meter concrete shoulder | Concreting of Barangay Libertad Phase II starts at Lat 8 ͦ 33'53.02" N , long. 123 ͦ 36'43.8" E and End at lat 8 ͦ 33'31.77" N and long. 123 ͦ 36'26.59" E | 3067000 |  |  |  | 1 |  |  | DED & POW APPROVED |  | 2020-06-17
084 | 2020 | REGION X | MISAMIS OCCIDENTAL | CLARIN | Local Access Road | Road Concreting | 0.661 km PCCP Constructed | Segatic Diot | 9254000 |  |  | 1 |  |  |  | DED & POW FINALIZATION |  | 2020-03-02
085 | 2020 | REGION X | MISAMIS OCCIDENTAL | CONCEPCION | Local Access Road | Concreting of Brgy Upper Potongan to small potongan | 0.55km PCCP | Brgy Upper Potongan to small potongan | 4799000 |  |  |  | 1 |  |  | DED & POW APPROVED |  | 2020-06-26
086 | 2020 | REGION X | MISAMIS OCCIDENTAL | DON VICTORIANO CHIONGBIAN | Local Access Road | Concreting of Road at Sitio Ninang - Brgy. Tuno | Concreting of 2-lane L=428m, 0.20 thk, W=5m road | Sitio Ninang - Brgy. Tuno Lat: 8°13'36.64"N Long: 123°33'42.38"E | 4630000 |  |  |  | 1 |  |  | DED & POW APPROVED |  | 2020-06-19
090 | 2020 | REGION X | MISAMIS OCCIDENTAL | LOPEZ JAENA | Local Access Road | Concreting of Rizal-Ilihan Road | Local Road Upgrading | Barangay Rizal | 4641000 |  |  | 1 |  |  |  | DED & POW FINALIZATION
091 | 2020 | REGION X | MISAMIS OCCIDENTAL | PANAON | Local Access Road | Concreting of Brgy. Baga (Phase I) | 9m formation width 2-lane 300lm, 5m wide & 20cm thick PCCP . 1m wide Graveled shoulder on both sides w/ 1m wide earth Canal on both sides | Baga / Start 8°21'51" N, 123°49'17" E and End 8°21'41" N, 123°48'25" E | 4000000 |  | 1 |  |  |  |  | NO SUBMISSION
092 | 2020 | REGION X | MISAMIS OCCIDENTAL | PANAON | Local Access Road | Concreting of Poblacion Access Road F.T. Paylaga Sr. Circumferential Road (Phase II) | 9m formation width 2-lane 500 lm, 5m wide & 20cm thick PCCP. 1m wide Graveled shoulder on both sides w/ 1m wide Earth Canal on both sides | Poblacion / Start 8°22'02" N, 123°49'52" E and End 8°22'10" N, 123°49'46" E | 6541000 |  | 1 |  |  |  |  | NO SUBMISSION
094 | 2020 | REGION X | MISAMIS OCCIDENTAL | PLARIDEL | Local access | Construction of Southern Poblacion-Eastern Looc-Plaridel Port Road | Concreting of 370m x 6m x 0.20m with 1.5m on one side shoulder, embankment and grouted riprap/stone masonry | Southern Poblacion, Eastern Looc | 9254000 |  |  |  | 1 |  |  | DED & POW APPROVED |  | 2020-02-26
095 | 2020 | REGION X | MISAMIS OCCIDENTAL | SAPANG DALAGA | Local Access Road | Concreting of Barangay Lucos Road | Concreting of Brgy Lucos Road ( 300lm x 5m x 0.20m) PCCP | Brgy. Lucos | 4641000 |  |  | 1 |  |  |  | DED & POW FOR FINALIZATION |  | 2020-02-27
096 | 2020 | REGION X | MISAMIS OCCIDENTAL | SINACABAN | Local Access Road | Concreting of 1.9km | 1.9km concrete road | Libertad Alto - Libertad Bajo | 10900000 |  |  |  | 1 |  |  | DED & POW APPROVED |  | 2020-03-30
|  |  |  | 11 | 12 |  |  |  | 72625000 | 0 | 2 | 5 | 5 | 0 | 0
077 | 2020 | REGION X | MISAMIS OCCIDENTAL | ALORAN | Solid Waste Disposal Facility | Development and Establishment of Sanitary Landfill (Residual Containment area) | 1 Residual Containtment area (RCA) w/ estimated floor area of 96 sq.m, with comfort room, septic vault & health care waste treatment facility development and established | Brgy. Culpan | 2000000 |  |  | 1 |  |  |  | DED & POW FOR FINALIZATION |  | 2020-05-27
081 | 2020 | REGION X | MISAMIS OCCIDENTAL | BONIFACIO | Provision of Potable Water Supply | Expansion of Municipal Waterworks System | Transmission and distribution pipelines, concrete reservoir, air release valves, water meter clusters, blow off valves and fire hydrant | Brgy. Lumapas (Start of Project,) -8°5'9.59" N , 123°36'42.06"E Brgy. Tiaman and Brgy. Lower Usogan (End of Project, 8°3'38.27" N 123°39' 38.27"E Brgy. Linconan | 12880000 |  | 1 |  |  |  |  | DED & POW FOR REVIEW |  | 2020-06-17
082 | 2020 | REGION X | MISAMIS OCCIDENTAL | CALAMBA | Sanitary Landfill | Construction of Sanitary Landfill (Phase I) in Barangay Magcamiguing | 1 Unit Sanitary Land Fill constructed for 19 Barangays of the Municipality | Barangay Magcamiguing | 5000000 |  |  | 1 |  |  |  | DED & POW FOR FINALIZATION |  | 2020-06-09
|  |  |  | 3 | 3 |  |  |  | 19880000 | 0 | 1 | 2 | 0 | 0 | 0
|  |  |  | 14 | 15 |  |  |  | 92505000 | 0 | 3 | 7 | 5 | 0 | 0
098 | 2020 | REGION X | MISAMIS ORIENTAL | ALUBIJID | Local Access Road | Concreting of Tambacan FMR |  | Loguilo | 9254000 |  |  |  | 1 |  |  | DED & POW APPROVED |  | 2020-05-18
099 | 2020 | REGION X | MISAMIS ORIENTAL | BALINGASAG | Local Access Road | Upgrading of Linggangao-Tulay Grande Road | Concreting of 930 meters barangay road with shouldering and Construction of 40 meters spillway | Sitio Tulay Grande, Barangay Linggangao & Sitio Dal-as, Barangay Talusan | 11370000 |  |  |  | 1 |  |  | DED & POW APPROVED |  | 2020-05-18
100 | 2020 | REGION X | MISAMIS ORIENTAL | BALINGOAN | Local Access Road | Concreting of Local Access Road |  | Barangay Lapinig | 4144000 |  | 1 |  |  |  |  | NO SUBMISSION |  | 2020-04-21
102 | 2020 | REGION X | MISAMIS ORIENTAL | CLAVERIA | Local Access Road | Rehabilitation of Junction Provincial Road to Sitio Impakibil (Phase II) | Concreting of 470 l.m road with 1.0 m shoulder and line canal both sides | Sitio Impakibil, Brgy. Aposkahoy | 8564000 |  |  |  | 1 |  |  | DED & POW APPROVED |  | 2020-03-06
103 | 2020 | REGION X | MISAMIS ORIENTAL | GITAGUM | Local Access Road | Upgrading/ Concreting of Local Access Road |  | P6, Matangad | 7204000 |  |  |  | 1 |  |  | DED & POW APPROVED |  | 2020-06-17
104 | 2020 | REGION X | MISAMIS ORIENTAL | GITAGUM | Local Access Road | Upgrading/ Concreting of Local Access Road |  | P7 to P8, Cogon | 5000000 |  |  |  | 1 |  |  | DED & POW APPROVED |  | 2020-06-17
105 | 2020 | REGION X | MISAMIS ORIENTAL | INITAO | Road Upgrading | Upgrading of Calacapan-Bansilang-Sinalac Road |  | Calacapan, Bansilang, Sinalac | 9254000 |  |  |  | 1 |  |  | DED & POW APPROVED |  | 2020-03-30 | npjr
107 | 2020 | REGION X | MISAMIS ORIENTAL | KINOGUITAN | Local Acces Road | Concreting of Buko Bypass Road |  | Buko, Kinoguitan | 4334000 |  |  |  | 1 |  |  | DED & POW APPROVED |  | 2020-06-03
108 | 2020 | REGION X | MISAMIS ORIENTAL | LAGONGLONG | Local Access Road | Concreting of Banglay FMR | 500 l.m with grouted riprap | Banglay, Lagonglong, Misamis Oriental | 6300000 |  |  |  | 1 |  |  | DED & POW APPROVED |  | 2020-02-27
109 | 2020 | REGION X | MISAMIS ORIENTAL | LAGONGLONG | Local Access Road | Concreting of Roa-Roa-Umagos FMR Phase II | 440 l.m with grouted riprap | Umagos, Lagonglong, Misamis Oriental | 5597000 |  |  |  | 1 |  |  | DED & POW APPROVED |  | 2020-03-06
111 | 2020 | REGION X | MISAMIS ORIENTAL | LAGUINDINGAN | Road Concreting | Concreting of Road at Phase 2 Relocation Site Purok 5, Tubajon |  | Barangay Tubajon | 3000000 |  | 1 |  |  |  |  | NO SUBMISSION |  | 2020-03-06
114 | 2020 | REGION X | MISAMIS ORIENTAL | LIBERTAD | Local Access Road | Upgrading and Improvement of Road Street (Poblacion to Kimalok Road) |  | Brgy. Kimalok | 8374000 |  |  |  | 1 |  |  | DED & POW APPROVED |  | 2020-03-06
115 | 2020 | REGION X | MISAMIS ORIENTAL | LUGAIT | Local Access Road | Concreting of Farm to Market Road | Concreted/Constructed 318.16 LM FMR | Sitio Linabo, Barangay Aya-Aya | 3924000 |  |  |  | 1 |  |  | DED & POW APPROVED |  | 2020-03-02
116 | 2020 | REGION X | MISAMIS ORIENTAL | LUGAIT | Local Access Road | Concreting of Farm to Market Road | Concreted/Constructed 300 LM FMR | Purok 2, Kuluknayan Proper, Barangay Kuluknayan | 3700000 |  |  |  | 1 |  |  | DED & POW APPROVED |  | 2020-04-21
117 | 2020 | REGION X | MISAMIS ORIENTAL | MAGSAYSAY | Local Acces Road | Cabubuhan(Lilo) - Kibungsod Circumferential Road |  | Brgy. Cabubuhan | 9909000 |  |  |  | 1 |  |  | DED & POW APPROVED |  | 2020-02-26
120 | 2020 | REGION X | MISAMIS ORIENTAL | NAAWAN | Local Access Road | Concreting of Don Pedro to Simanoc Farm to Market Road | Concreting of at least 600 meters road | Brgy. Don Pedro | 6977000 |  |  |  | 1 |  |  | DED & POW APPROVED |  | 2020-02-26
121 | 2020 | REGION X | MISAMIS ORIENTAL | OPOL | LOCAL ACCESS ROAD | UPGRADING/ ROAD CONCRETING | CONCRETING OF 680 METERS LAR/ FMR | BRGY. PATAG | 8257000 |  |  |  | 1 |  |  | DED & POW APPROVED |  | 2020-02-26
122 | 2020 | REGION X | MISAMIS ORIENTAL | SALAY | Local Access Road | Concreting of 1 Kilometer Barangay Alipuaton to Sitio Salahon Farm-to-Market Road | 1 KM of FMR concreted with Lined Canal at both sides of road | Barangay Alipuaton, Salay, Misamis Oriental | 11897000 |  |  |  | 1 |  |  | DED & POW APPROVED
126 | 2020 | REGION X | MISAMIS ORIENTAL | VILLANUEVA | Local Access Road | Concreting of Sitio Macusi - Kimaya Road |  | Kimaya - Villanueva, Misamis Oriental | 6787000 |  |  |  | 1 |  |  | DED & POW APPROVED |  | 2020-03-16
|  |  |  | 16 | 19 |  |  |  | 93310000 | 0 | 2 | 0 | 17 | 0 | 0
110 | 2020 | REGION X | MISAMIS ORIENTAL | LAGUINDINGAN | Sanitary Landfill | Improvement of Sanitary Landfill-Lapad |  | Brgy. Lapad | 3470250 |  |  | 1 |  |  |  | DED & POW FINALIZATION |  | 2020-03-16
112 | 2020 | REGION X | MISAMIS ORIENTAL | LAGUINDINGAN | Evacuation Center | Improvement of Evacuation Center - San Juan Moog |  | Brgy. Moog | 1627000 |  |  | 1 |  |  |  | DED & POW FINALIZATION |  | 2020-01-31
113 | 2020 | REGION X | MISAMIS ORIENTAL | LAGUINDINGAN | Municipal Gymnasium | Improvement of Municipal Gymnasium |  | Brgy. Poblacion | 1156750 |  |  |  | 1 |  |  | DED & POW APPROVED |  | 7348835
119 | 2020 | REGION X | MISAMIS ORIENTAL | MEDINA | Evacuation Center | Completion of Evacuation Center | Completion of multi-purpose buildings that would serve as venue for social/public events and at the same time as an evacuation center for displaced families during disaster. | South Poblacion | 6703000 |  |  |  | 1 |  |  | DED & POW APPROVED |  | 2020-02-26
125 | 2020 | REGION X | MISAMIS ORIENTAL | TALISAYAN | Ecological Solid Waste | Construction of Sanitary Landfill (Phase 2) |  | Casibole, Talisayan, Misamis Oriental | 4334000 |  | 1 |  |  |  |  | NO SUBMISSION |  | 2020-04-21
|  |  |  | 3 | 5 |  |  |  | 17291000 | 0 | 1 | 2 | 2 | 0 | 0
|  |  |  | 19 | 24 |  |  |  | 110601000 | 0 | 3 | 2 | 19 | 0 | 0
|  |  |  | 79 | 102 |  |  |  | 584775000 | 0 | 8 | 29 | 65 | 0 | 0

## 2020 AM-WATER
REGION X - AM
2020 AM-WATER
as of June 26, 2020
| FY | REGION | PROVINCE | CITY / MUNICIPALITY | PROJECT TYPE | PROJECT TITLE | PHYSICAL TARGET/ OUTPUT | BARANGAY | NG ALLOCATION | CANCELLED | DED/POW PREPARATION | FINALIZATION | PROCUREMENT | ON-GOING | COMPLETED | STATUS | REMARKS | DATE UPDATED
001 | 2020 | REGION X | BUKIDNON | BAUNGON | Potable Water System | Rehabilitation / Improvement of level 3 Distribution pipeline | Rehabilitation of New Distribution Pipeline from 150mm diam. to 200mm diam. HDPE SDR 11 | Brgy. Liburan | 7284000 |  |  |  | 1 |  |  | DED & POW APPROVED |  | 2020-01-28
012 | 2020 | REGION X | BUKIDNON | KITAOTAO | Potable Water System | Construction of Level II Potable Water System | Development of spring Water Source that will impound 100cu.m. with treatment facilities, installation of new 1,000 L.m. new distribution line and additional 25 tap stands. | Brgy. Sinuda | 4989000 |  | 1 |  |  |  |  | NO SUBMISSION |  | 2020-01-28
013 | 2020 | REGION X | BUKIDNON | LANTAPAN | Potable Water System | Construction of Potable Water System (phase II) | 6,000 meters | Brgy. Basak & Kibanggay | 12204000 |  |  |  | 1 |  |  | DED & POW APPROVED |  | 2020-04-21
014 | 2020 | REGION X | BUKIDNON | LIBONA | Potable Water System | Improvement/rehab. of sigmatan water system (phase vIII) | Upgrading of Transmission & Lateral lines (Pipes to be used 4",3",2") | Sitio Salvacion, Maambong | 7000000 |  |  | 1 |  |  |  | DED & POW FINALIZATION |  | 2020-01-28
015 | 2020 | REGION X | BUKIDNON | LIBONA | Potable Water System | Development/Const. of Tigbao Water System | Laying of Transmission Pipe line to Tigbao, San Jose, Crossing 8 (crossing 171 Hs), pipes to be used 4" with accessories, and Water Treatment (chlorinator) | purok 2 Crossing, Tigbao, San Jose, Tigbao spring | 3900000 |  |  | 1 |  |  |  | DED & POW FINALIZATION |  | 2020-01-28
017 | 2020 | REGION X | BUKIDNON | MANOLO FORTICH | Water System | Improvement of Lindaban Water System | Rehabilitation of existing pioeline, provision of intake box, provision of cluster meters | Lindaban, Manolo Fortich, Bukidnon | 4334000 |  |  | 1 |  |  |  | DED & POW FINALIZATION |  | 2020-02-07
022 | 2020 | REGION X | BUKIDNON | SAN FERNANDO | Potable Water System | Provision of Potable Water Supply | New Construction of Level II Potable Water Supply | Little Baguio | 11555000 |  |  | 1 |  |  |  | DED & POW FINALIZATION |  | 2020-01-28
|  |  |  | 6 | 7 |  |  |  | 51266000 | 0 | 1 | 4 | 2 | 0 | 0
035 | 2020 | REGION X | CAMIGUIN | MAMBAJAO | Potable Water System | Rehab./Improvement of Pandan Level II Water System | Pandan water system improved and rehabilitated | Pandan, Mambajao | 3000000 |  |  | 1 |  |  |  | DED & POW FOR FINALIZATION |  | 2020-05-11
037 | 2020 | REGION X | CAMIGUIN | SAGAY | Potable Water System | Potable Water System Projects - Water Metering System for Barangay Bacnit, Bugang, Mayana and Poblacion | Procurement and installation of 1,500 units water meter for level III household water connections | Barangay Bacnit, Bugang, Mayana and Poblacion | 2371000 |  |  | 1 |  |  |  | DED & POW FOR FINALIZATION |  | 2020-05-11
|  |  |  | 1 | 2 |  |  |  | 3000000 | 0 | 0 | 2 | 0 | 0 | 0
047 | 2020 | REGION X | LANAO DEL NORTE | LINAMON | PWS | Enhancement/Expansion of Potable Water System | Expansion/installation of water transmission pipelines to serve other barangays | Brgy. Robocon, Borque and Purakan | 9254000 |  |  | 1 |  |  |  | DED & POW FINALIZATION |  | 2020-01-28
057 | 2020 | REGION X | LANAO DEL NORTE | PANTAR | Potable Water System | Construction of Potable Water System | Additional main line and distribution line from the existing source of water | Bancal Water Source | 2555000 |  |  | 1 |  |  |  | DED & POW FOR FINALIZATION |  | 2020-02-26
|  |  |  | 2 | 2 |  |  |  | 11809000 | 0 | 0 | 2 | 0 | 0 | 0
087 | 2020 | REGION X | MISAMIS OCCIDENTAL | JIMENEZ | Potable Water System | Improvement of level 2&3 water system in waterless barangay | 1 unit-10 cu.m. Reservoir, 5hp submersible pump, Drilling of Borehole | Brgy. Macabayao | 3000000 |  |  |  | 1 |  |  | DED & POW APPROVED |  | 2020-01-28
088 | 2020 | REGION X | MISAMIS OCCIDENTAL | JIMENEZ | Potable Water System | Improvement of level 2&3 water system in waterless barangay | 1 unit-10 cu.m. Reservoir 5hp submersible pump, Drilling of Borehole | Brgy. Guintomoyan | 3000000 |  |  |  | 1 |  |  | DED & POW APPROVED |  | 2020-01-28
089 | 2020 | REGION X | MISAMIS OCCIDENTAL | JIMENEZ | Potable Water System | Improvement of level 2&3 water system in waterless barangay | +/- 2km Pipelines | Brgy. Taboo | 3254000 |  |  |  | 1 |  |  | DED & POW APPROVED |  | 2020-01-28
097 | 2020 | REGION X | MISAMIS OCCIDENTAL | TUDELA | Water Supply System | Completion of Pan ay Diot level III Water System | Construction of Reservoir, Addtional Distribution Pipeline & Service Connection | Brgy. Pan ay Diot | 4334000 |  | 1 |  |  |  |  | DED & POW FOR REVIEW |  | 2020-06-08
|  |  |  | 2 | 4 |  |  |  | 13588000 | 0 | 1 | 0 | 3 | 0 | 0
101 | 2020 | REGION X | MISAMIS ORIENTAL | BINUANGAN | Water Supply Sytem | Rehabilitation/ Improvement of Municipal Water System |  | Brgy. Valdeconcha | 3975000 |  |  | 1 |  |  |  | DED & POW FINALIZATION |  | 2020-04-21
106 | 2020 | REGION X | MISAMIS ORIENTAL | JASAAN | Potable Water Supply System | Potable Water Supply (Level II/Level III) - Luz Banzon - Kimaya |  | Brgys. Luz Banzon and Kimaya | 4334000 |  |  |  | 1 |  |  | DED & POW APPROVED |  | 2020-01-28
118 | 2020 | REGION X | MISAMIS ORIENTAL | MANTICAO | Potable Water System | Expansion of Level III Potable Water System | Development of additional spring water sources that will impound 216 cu.m with treatment facilities, installation of 1,500 l.m new distribution lines. | Barangay Paniangan Barangay Poblacion Barangay Punta Silum | 4334000 |  |  |  | 1 |  |  | DED & POW APPROVED |  | 2020-01-27 | FCLA
123 | 2020 | REGION X | MISAMIS ORIENTAL | SUGBONGCOGON | Potable Water System | Source Development for Potable Water System Level III |  | Barangay Mimbuahan | 8067000 |  |  |  | 1 |  |  | DED & POW APPROVED |  | 2020-02-26
124 | 2020 | REGION X | MISAMIS ORIENTAL | TAGOLOAN | Potable Water System | Construction of Level III Potable Water System |  | Maribojoc - Sta. Ana | 4060000 |  |  |  | 1 |  |  | DED & POW APPROVED |  | 2020-03-02
|  |  |  | 5 | 5 |  |  |  | 24770000 | 0 | 0 | 1 | 4 | 0 | 0
|  |  |  | 16 | 20 |  |  |  | 104433000 | 0 | 2 | 9 | 9 | 0 | 0 | 20

## 2012 SALINTUBIG
REGION X
2012 SALINTUBIG
as of June 26, 2020
PHYSICAL | [12 empty] | FINANCIAL |  |  | REMARKS
PROJECT CODE | PROVINCES | LGUs | NO. OF LGUs | ALLOCATION | TOTAL NO. OF PROJECTS | CANCELLED PROJECTS | CANCELLED ALLOCATION | UNDER PREP | APPROVED FS/POW or DED PREP. | PROCUREMENT | ON-GOING | COMPLETED | TOTAL RELEASES | TOTAL LIQUIDATION | AMOUNT OBLIGATED
SA-12-10-13-07-1 | BUKIDNON | KALILANGAN | 1 | 7 | 1 | - | - |  |  |  |  | 1 | 7000000 | 7000000 | 7 | Completed
SA 12-10-13-07-2
SA-12-10-13-16-1 | BUKIDNON | PANGANTUCAN RHU | 1 | 1 | 1 | - | - |  |  |  |  | 1 | 1000000 | 1000000 | 1 | Completed
SA-12-10-35-04-1 | LANAO DEL NORTE | ILIGAN CITY | 1 | 7 | 1 | - | - |  |  |  |  | 1 | 7000000 | 7000000 | 7 | Completed
SA-12-10-42-03-1 | MISAMIS OCCIDENTAL | BONIFACIO | 1 | 2 | 1 | - | - |  |  |  |  | 1 | 2000000 | 2000000 | 2 | Completed
SA-12-10-42-14-1 | MISAMIS OCCIDENTAL | SINACABAN RHU | 1 | 1 | 1 | - | - |  |  |  |  | 1 | 1000000 | 1000000 | 1 | Completed
SA-12-10-42-15-1 | MISAMIS OCCIDENTAL | TANGUB | 1 | 1 | 1 | - | - |  |  |  |  | 1 | 1000000 | 1000000 | 1 | Completed
SA-12-10-42-15-2
SA-12-10-42-15-3
SA12-10-43-05-1 | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY | 1 | 6 | 1 | - | - |  |  |  |  | 1 | 6000000 | 6000000 | 6 | Completed
SA-12-10-43-05-2
SA-12-10-43-18-1 | MISAMIS ORIENTAL | MANTICAO | 1 | 1 | 1 | - | - |  |  |  |  | 1 | 1000000 | 1000000 | 1 | Completed
Total 2012 Salintubig |  |  | 8 | 26 | 8 | - | - |  |  |  |  | 8 | 26000000 | 26000000 | 26

## 2013 SALINTUBIG COMPLETED
REGION X
2013 SALINTUBIG
as of June 26, 2020
|  |  |  | FINANCIAL |  |  |  |  | CANCELLED PROJECTS | UNDER PREP | APPROVED FS/POW or DED PREP. | PROCUREMENT | ON-GOING | COMPLETED | STATUS | REMARKS | Date Updated
PROVINCES | LGUs | NO. OF LGUs | TOTAL NO. OF PROJECTS | ALLOCATION | CANCELLED ALLOCATION | TOTAL RELEASES | TOTAL LIQUIDATION | AMOUNT OBLIGATED
LANAO DEL NORTE | NUNUNGAN | 1 | 1 | 8 | - | 8000000 | 8000000 | 8 | - |  |  |  |  | 1 | Completed
LANAO DEL NORTE | PANTAO RAGAT | 1 | 1 | 9 | - | 9000000 | 9000000 | 9 | - |  |  |  |  | 1 | Completed
LANAO DEL NORTE | POONA PIAGAPO | 1 | 1 | 8 | - | 8000000 | 8000000 | 8 | - |  |  |  |  | 1 | Completed
LANAO DEL NORTE | SAPAD | 1 | 2 | 8 | - | 8000000 | 8000000 | 8 | - |  |  |  |  | 2 | Completed
LANAO DEL NORTE | TAGOLOAN | 1 | 1 | 8 | - | 8000000 | 8000000 | 8 | - |  |  |  |  | 1 | Completed
LANAO DEL NORTE | MATUNGAO | 1 | 1 | 8 |  | 8000000 | 8000000 | 8 | [5 empty] | 1 | Completed
Sub-Total Lanao del Norte |  | 6 | 7 | 49 | - | 49000000 | 49000000 | 49 | - | 0 | 0 | 0 | 0 | 7
MISAMIS OCCIDENTAL | CALAMBA | 1 | 1 | 8 | - | 6962455 | 6962455 | 8 | - |  |  |  |  | 1 | Completed |  | 2018-11-01 | MOT
Sub-Total Misamis Occidental |  | 1 | 1 | 8 | - | 6962455 | 6962455 | 8 | - | 0 | 0 | 0 | 0 | 1
MISAMIS ORIENTAL | ALUBIJID | 1 | 1 | 2.299 | - | 2299000 | 2299000 | 2.299 | - |  |  |  |  | 1 | Completed
MISAMIS ORIENTAL | GITAGUM | 1 | 1 | 2.25 | - | 2250000 | 2250000 | 2.25 | - |  |  |  |  | 1 | Completed
MISAMIS ORIENTAL | LAGONGLONG | 1 | 1 | 2 | - | 1770975.12 | 1770975.12 | 2 | - |  |  |  |  | 1 | Completed
MISAMIS ORIENTAL | LIBERTAD | 1 | 3 | 2.25 | - | 2250000 | 2250000 | 2.25 | - |  |  |  |  | 3 | Completed
MISAMIS ORIENTAL | MAGSAYSAY | 1 | 1 | 2 | - | 2000000 | 2000000 | 2 | - |  |  |  |  | 1 | Completed
MISAMIS ORIENTAL | MANTICAO | 1 | 1 | 2.25 | - | 2250000 | 2250000 | 2.25 | - |  |  |  |  | 1 | Completed
Sub-Total Misamis Oriental |  | 6 | 8 | 13.049 | - | 12819975.12 | 12819975.12 | 13.049 | - | 0 | 0 | 0 | 0 | 8
Total 2013 Salintubig |  | 13 | 16 | 70.049 | - | 68782430.12 | 68782430.12 | 70.049 | - | 0 | 0 | 0 | 0 | 16

## 2014 SALINTUBIG COMPLETED
REGION X
2014 SALINTUBIG
as of June 26, 2020
|  |  |  | FINANCIAL |  |  |  |  | CANCELLED PROJECTS | UNDER PREP | APPROVED FS/POW or DED PREP. | PROCUREMENT | ON-GOING | COMPLETED | STATUS | REMARKS | DATE UPDATED
PROVINCES | LGUs | NO. OF LGUs | TOTAL NO. OF PROJECTS | ALLOCATION | CANCELLED ALLOCATION | TOTAL RELEASES | TOTAL LIQUIDATION | AMOUNT OBLIGATED
BUKIDNON | BAUNGON | 1 | 1 | 8 | - | 7986394.98 | 7986394.98 | 8 | - |  |  |  |  | 1 | Completed
BUKIDNON | PANGANTUCAN | 1 | 2 | 8 | - | 8000000 | 8000000 | 8 | -
| Kimanait |  |  |  | - |  |  |  | - |  |  |  |  | 1 | Completed | (No funds allocated for the Pump accessories) | 2018-11-01 | BT
| Lantay,New Eden, Adtuyon & Pob |  |  |  | - |  |  |  | - |  |  |  |  | 1 | Completed |  | 2018-06-19 | BT
Sub-Total Bukidnon |  | 2 | 3 | 16 | 0 | 15986394.98 | 15986394.98 | 16 | 0 | 0 | 0 | 0 | 0 | 3
LANAO DEL NORTE | BALOI | 1 | 1 | 8 | - | 7935854.16 | 7935854.16 | 8 | - |  |  |  |  | 1 | Completed |  | 2017-07-21
LANAO DEL NORTE | MAGSAYSAY | 1 | 1 | 9 | - | 9000000 | 9000000 | 9 | - |  |  |  |  | 1 | Completed |  | 2018-03-13 | SWA
LANAO DEL NORTE | PANTAO RAGAT | 1 | 1 | 2 | - | 2000000 | 1600000 | 2 | - |  |  |  |  | 1 | Completed
LANAO DEL NORTE | SALVADOR | 1 | 3 | 9 | - | 9000000 | 9000000 | 9 | -
| Mabatao |  |  |  | - |  |  |  | - |  |  |  |  | 1 | Completed |  | 2018-08-07 | SWA
| Buntong |  |  |  | - |  |  |  | - |  |  |  |  | 1 | Completed |  | 2018-08-14 | SWA
| Poblacion |  |  |  | - |  |  |  | - |  |  |  |  | 1 | Completed |  | 2018-08-24 | SWA
Sub-Total Lanao del Norte |  | 4 | 6 | 28 | 0 | 27935854.16 | 27535854.16 | 28 | 0 | 0 | 0 | 0 | 0 | 6
MISAMIS OCCIDENTAL | CONCEPCION | 1 | 1 | 9 | - | 4500000 | 4500000 | 9 | 1 | [5 empty] | Cancelled |  | 2019-05-17 | KE
MISAMIS OCCIDENTAL | PLARIDEL | 1 | 1 | 1 | - | 1000000 | 1000000 | 1 | - |  |  |  |  | 1 | Completed
MISAMIS OCCIDENTAL | SAPANG DALAGA | 1 | 1 | 1 | - | 1000000 | 1000000 | 1 | - |  |  |  |  | 1 | Completed
Sub-Total Misamis Occidental |  | 3 | 3 | 11 | 0 | 6500000 | 6500000 | 11 | 1 | 0 | 0 | 0 | 0 | 2
MISAMIS ORIENTAL | BINUANGAN | 1 | 1 | 2 | - | 1840000 | 1840000 | 2 | - |  |  |  |  | 1 | Completed
Sub-total Misamis Oriental |  | 1 | 1 | 2 | 0 | 1840000 | 1840000 | 2 | 0 | 0 | 0 | 0 | 0 | 1
Total 2014 Salintubig |  | 10 | 13 | 57 | 0 | 52262249.14 | 51862249.14 | 57 | 1 | 0 | 0 | 0 | 0 | 12

## 2015 SALINTUBIG COMPLETED
REGION X
2015 SALINTUBIG
as of June 26, 2020
|  |  |  | FINANCIAL |  |  |  |  | CANCELLED PROJECTS | UNDER PREP | APPROVED FS/POW or DED PREP. | PROCUREMENT | ON-GOING | COMPLETED | STATUS | REMARKS | DATE UPDATED
PROVINCES | LGUs | NO. OF LGUs | TOTAL NO. OF PROJECTS | ALLOCATION | CANCELLED ALLOCATION | TOTAL RELEASES | TOTAL LIQUIDATION | AMOUNT OBLIGATED
LANAO DEL NORTE | BACOLOD | 1 | 7 | 15 | - |  |  | 15 | -
| Alegria |  |  |  |  | 2000000 | 2000000 | [6 empty] | 1 | Completed
| Delabayan West |  |  |  |  | 2000000 | 2000000 | [6 empty] | 1 | Completed
| Babalayan Townsite |  |  |  |  | 2000000 | 2000000 | [6 empty] | 1 | Completed
| Pagayawan |  |  |  |  | 2000000 | 2000000 | [6 empty] | 1 | Completed
| Punod (Maliwanag) |  |  |  |  | 2000000 | 2000000 | [6 empty] | 1 | Completed
| Kahayag |  |  |  |  | 3000000 | 3000000 | [6 empty] | 1 | Completed
| Dimarao |  |  |  |  | 2000000 | 2000000 | [6 empty] | 1 | Completed
LANAO DEL NORTE | SULTAN NAGA DIMAPORO (KAROMATAN) | 1 | 7 | 13 | - |  |  | 13 | -
| Bansarvil II |  |  |  | - | 2000000 | 2000000 |  | - |  |  |  |  | 1 | Completed
| Cabongbongan |  |  |  | - | 2000000 | 2000000 |  | - |  |  |  |  | 1 | Completed | SWA | 2018-07-25
| Ditago |  |  |  | - | 2000000 | 2000000 |  | - |  |  |  |  | 1 | Completed | SWA | 1/29/2018
| Calube |  |  |  | - | 2000000 | 2000000 |  | - |  |  |  |  | 1 | Completed | SWA | 1/29/2018
| Lantawan |  |  |  | - | 2000000 | 2000000 |  | - |  |  |  |  | 1 | Completed | SWA | 1/29/2018
| Calipapa |  |  |  | - | 1000000 | 1000000 |  | - |  |  |  |  | 1 | Completed | SWA | 1/29/2018
| Campo Islam |  |  |  | - | 2000000 | 2000000 |  | - |  |  |  |  | 1 | Completed | SWA | 2018-07-25
LANAO DEL NORTE | BAROY | 1 | 6 | 11 | - |  |  | 11 | -
| Limuag |  |  |  | - | 2000000 | 2000000 |  | - |  |  |  |  | 1 | Completed
| Andil |  |  |  | - | 3000000 | 3000000 |  | - |  |  |  |  | 1 | Completed | SWA | 2018-08-08
| Libertad |  |  |  | - | 2000000 | 2000000 |  | - |  |  |  |  | 1 | Completed | SWA | 2018-06-28
| Pendolonan |  |  |  | - | 2000000 | 2000000 |  | - |  |  |  |  | 1 | Completed | SWA | 11/22/2018
| Upper Sagadan |  |  |  | - | 1000000 | 1000000 |  | - |  |  |  |  | 1 | Completed | SWA | 2018-08-08
| Bato |  |  |  | - | 1000000 | 1000000 |  | 1 | [5 empty] | CANCELLED |  | 2019-02-01 | ND
LANAO DEL NORTE | TUBOD (Capital) | 1 | 6 | 12 | - |  |  | 12 | -
| Taguranao |  |  |  | - | 2000000 | 2000000 |  | - |  |  |  |  | 1 | Completed | SWA | 11/22/2018
| Bulod |  |  |  | - | 2000000 | 2000000 |  | - |  |  |  |  | 1 | Completed | SWA | 1/29/2018
| Sto. Niño |  |  |  | - | 2000000 | 2000000 |  | - |  |  |  |  | 1 | Completed | SWA | 2017-10-24
| Kalilangan |  |  |  | - | 2000000 | 2000000 |  | - |  |  |  |  | 1 | Completed | SWA | 2018-02-13
| Licapao |  |  |  | - | 2000000 | 2000000 |  | - |  |  |  |  | 1 | Completed | SWA | 2018-05-07
| Taden |  |  |  | - | 2000000 | 2000000 |  | - |  |  |  |  | 1 | Completed | SWA | 1/29/2018
LANAO DEL NORTE | KAUSWAGAN | 1 | 5 | 9 | - |  |  | 9 | -
| Cayontor |  |  |  | - | 2000000 | 1967150 |  | - |  |  |  |  | 1 | Completed |  | 2018-10-10 | AL
| Bagumbayan |  |  |  | - | 2000000 | 1986700 |  | - |  |  |  |  | 1 | Completed | SWA | 2018-05-07
| Delabayan, Bumbaran |  |  |  | - | 1000000 | 825443.64 |  | - |  |  |  |  | 1 | Completed |  | 2018-10-10 | AL
| Paiton |  |  |  | - | 3000000 | 3000900.25 |  | - |  |  |  |  | 1 | Completed |  | 2018-10-10 | AL
| Poblacion |  |  |  | - | 1000000 | 997450 |  | - |  |  |  |  | 1 | Completed |  | 2018-10-10 | AL
LANAO DEL NORTE | MAIGO | 1 | 3 | 6 | - |  |  | 6 | -
| Inoma |  |  |  |  | 2000000 | 2000000 |  | 1 | [5 empty] | CANCELLED |  | 2019-07-19 | CL
| Maliwanag |  |  |  |  | 2000000 | 2000000 | [6 empty] | 1 | Completed |  | 2020-01-24 | CL
| Camp 1 |  |  |  | - | 2000000 | 2000000 |  | 1 | [5 empty] | CANCELLED |  | 2019-02-01 | ND
Sub-Total Lanao del Norte |  | 6 | 34 | 66 | 0 | 66000000 | 65777643.89 | 66 | 3 | 0 | 0 | 0 | 0 | 31
MISAMIS OCCIDENTAL | CLARIN | 1 | 7 | 12 | - |  |  | 12 | -
| Bitoon |  |  |  | - | 2000000 | - |  | - |  |  |  |  | 1 | Completed | AS OF 11/15/2019 SWA | 2020-01-31
| Cabunga-an |  |  |  | - | 2000000 | 1794232.88 |  | - |  |  |  |  | 1 | Completed | AS OF 5/26/2019 SWA | 2020-01-31
| Sebasi |  |  |  | - | 2000000 | - |  | - |  |  |  |  | 1 | Completed | AS OF 10/25/2019 SWA | 2020-01-31
| Canipacan |  |  |  | - | 1000000 | 848251 |  | - |  |  |  |  | 1 | Completed | AS OF 5/23/2019 SWA | 2020-01-31
| Dela Paz |  |  |  | - | 2000000 | 574610.46 |  | - |  |  |  |  | 1 | Completed | AS OF 4/25/2019 SWA | 2020-01-31
| Dolores |  |  |  | - | 2000000 | 1733519.9 |  | - |  |  |  |  | 1 | Completed |  | 2020-01-17 | KCE
| Segatic Diot |  |  |  | - | 1000000 | 848498.49 |  | - |  |  |  |  | 1 | Completed | AS OF 3/22/2019 SWA | 2020-01-31
MISAMIS OCCIDENTAL | ALORAN | 1 | 4 | 8 | - |  |  | 8 | -
| Balingtonga |  |  |  | - | 2000000 | 1995206.38 |  | - |  |  |  |  | 1 | Completed | as of 7/31/2019 SWA | 2019-09-16 | K.E.
| Macubon(Sina-ad) |  |  |  | - | 2000000 | 2000000 |  | - |  |  |  |  | 1 | Completed | as of January 21, 2019 (SWA) | 2019-02-08
| Monterico |  |  |  | - | 2000000 | 2000000 |  | - |  |  |  |  | 1 | Completed | as of 4/15/2019 (SWA) | 2019-04-15
| Roxas |  |  |  | - | 2000000 | 2000000 |  | - |  |  |  |  | 1 | Completed | as of 3/5/2019 (SWA) | 2019-03-14
MISAMIS OCCIDENTAL | BONIFACIO | 1 | 5 | 8 | - |  |  | 8 | -
| Tangab |  |  |  | - | 2000000 | 2000000 |  | - |  |  |  |  | 1 | Completed
| Sibuyon |  |  |  | - | 2000000 | 2000000 |  | - |  |  |  |  | 1 | Completed
| Lodiong |  |  |  | - | 1000000 | 1000000 |  | - |  |  |  |  | 1 | Completed
| Buracan |  |  |  | - | 1000000 | 1000000 |  | - |  |  |  |  | 1 | Completed | LGU proceed to implementation without the DILG-R10 approval for implementation | 2017-09-06 | RV
| Tusik |  |  |  | - | 2000000 | 2000000 |  | - |  |  |  |  | 1 | Completed |  | 2017-09-06 | RV
MISAMIS OCCIDENTAL | JIMENEZ | 1 | 3 | 6 | - |  |  | 6 | -
| Sinara Alto |  |  |  |  | 2000000 | 2000000 |  | - |  |  |  |  | 1 | Completed | SWA | 10/17/2018
| Carmen |  |  |  |  | 2000000 | 2000000 |  | - |  |  |  |  | 1 | Completed | SWA | 2017-08-16
| Seti |  |  |  | - | 2000000 | 2000000 |  | - |  |  |  |  | 1 | Completed | SWA | 10/17/2018
MISAMIS OCCIDENTAL | PLARIDEL | 1 | 3 | 6 | - |  |  | 6 | -
| Danao |  |  |  | - | 2000000 | 2000000 |  | - |  |  |  |  | 1 | Completed
| Agunod |  |  |  | - | 2000000 | 2000000 |  | - |  |  |  |  | 1 | Completed
| New Cartagena |  |  |  | - | 2000000 | 2000000 |  | - |  |  |  |  | 1 | Completed
MISAMIS OCCIDENTAL | DON VICTORIANO CHIONGBIAN (DON MARIANO MARCOS) | 1 | 2 |  | 3
| Lake Duminagat |  |  |  |  | 0 | 0 |  | 1 | [5 empty] | CANCELLED | Not Obligated | 2018-01-09
| Napangan |  |  |  |  | 0 | 0 |  | 1 | [5 empty] | CANCELLED | Not Obligated | 2018-01-09
MISAMIS OCCIDENTAL | TUDELA | 1 | 4 | 7 | - |  |  | 7 | -
| Gala/Maribojoc |  |  |  |  | 1000000 | 1000000 | [6 empty] | 1 | Completed | as of March 29, 2019 (SWA) | 7/29/2019
| Canibungan Proper |  |  |  |  | 2000000 | 2000000 | [6 empty] | 1 | Completed
| Mitugas |  |  |  |  | 2000000 | 2000000 | [6 empty] | 1 | Completed
| Yahong |  |  |  | - | 2000000 | 2000000 |  | - |  |  |  |  | 1 | Completed
MISAMIS OCCIDENTAL | LOPEZ JAENA | 1 | 2 | 4 | - |  |  | 4 | -
| Macalibre Alto |  |  |  |  | 2000000 | 2000000 | [6 empty] | 1 | Completed | as of 4/22/2019 (SWA) | 2019-04-29
| Bonifacio |  |  |  | - | 2000000 | 2000000 |  | - |  |  |  |  | 1 | Completed | SWA | 2017-09-26
Sub-Total Mis. Occidental |  | 8 | 30 | 51 | 3 | 51000000 | 44794319.11 | 51 | 2 | 0 | 0 | 0 | 0 | 28
TOTAL 2015 SALINTUBIG |  | 14 | 64 | 117 | 3 | 117000000 | 110571963 | 117 | 5 | 0 | 0 | 0 | 0 | 59

## 2016 SALINTUBIG COMPLETED
REGION X
2016 SALINTUBIG
as of June 26, 2020
|  |  |  | FINANCIAL |  |  |  |  | CANCELLED PROJECTS | UNDER PREP | APPROVED FS/POW or DED PREP. | PROCUREMENT | ON-GOING | COMPLETED | STATUS | REMARKS | Date updated
PROVINCES | LGUs | NO. OF LGUs | TOTAL NO. OF PROJECTS | ALLOCATION | CANCELLED ALLOCATION | TOTAL RELEASES | TOTAL LIQUIDATION | AMOUNT OBLIGATED
BUKIDNON | SAN FERNANDO | 1 | 5
| Dao (Sitio Kirangol) |  |  | 1 |  | 1000000 | 1000000 | 1 | [5 empty] | 1 | Completed | SWA | 2018-05-16 | BT
| Kalagangan (Sitio Simsimon & Balugo) |  |  | 2 |  | 2000000 | 2000000 | 2 | [5 empty] | 1 | Completed | Simsimon and Balugo - Competed (SWA) | 2018-03-13
| San Jose (Sitio Inayaman) |  |  | 1 |  | 1000000 | 1000000 | 1 | [5 empty] | 1 | Completed | SWA | 2018-06-18
| Halapitan (Sitio Salumayag) |  |  | 1 |  | 1000000 | 1000000 | 1 | [5 empty] | 1 | Completed | SWA | 2018-06-18
| Matupe (Sitio Kamiyasungan) |  |  | 1 |  | 1000000 | 1000000 | 1 | [5 empty] | 1 | Completed | SWA | 2018-06-18
Sub-Total Bukidnon |  | 1 | 5 | 6 | 0 | 6000000 | 6000000 | 6 | 0 | 0 | 0 | 0 | 0 | 5
CAMIGUIN | MAMBAJAO | 1 | 5
| Magting |  |  | 3 |  | 3000000 | 3000000 | 3 | [5 empty] | 1 | Completed | SWA | 2018-09-11
| Tupsan |  |  | 2 |  | 2000000 | 2000000 | 2 | [5 empty] | 1 | Completed | as of 5/20/2019 (SWA) | 2019-05-24
| Pandan |  |  | 2 |  | 2000000 | 2000000 | 2 | [5 empty] | 1 | Completed | SWA | 2018-09-11
| Poblacion |  |  | 3 |  | 3000000 | 3000000 | 3 | [5 empty] | 1 | Completed | as of 2/15/2019 (SWA) | 2019-04-01
| Yumbing |  |  | 2 |  | 2000000 | 1919114.45 | 2 | [5 empty] | 1 | Completed |  | 2018-09-27 | flor
CAMIGUIN | SAGAY | 1 | 1 | 2 |  |  |  | 2
| Bacnit |  |  |  |  | 2000000 | 2000000 | [6 empty] | 1 | Completed | SWA | 2017-10-04
CAMIGUIN | CATARMAN | 1 |  | 2 |  |  |  | 2
| Catibac |  | 1 |  |  | 2000000 | 609718 | [6 empty] | 1 | Completed
Sub-Total Camiguin |  | 3 | 7 | 16 | 0 | 16000000 | 14528832.45 | 16 | 0 | 0 | 0 | 0 | 0 | 7
LANAO DEL NORTE | KAPATAGAN | 1 | 1 | 12 |  | 12000000 | 12000000 | 12 | [5 empty] | 1 | Completed |  | 2019-07-15 | ND
LANAO DEL NORTE | BACOLOD | 1 | 1 | 2 |  | 2000000 | 2000000 | 2 | [5 empty] | 1 | Completed |  | 2018-01-12 | CP
LANAO DEL NORTE | KAUSWAGAN (Brgy. Inudaran) | 1 | 1 | 2 |  | 2000000 | 2000000 | 2 | [5 empty] | 1 | Completed |  | 2018-10-10 | AL
LANAO DEL NORTE | KOLAMBUGAN | 1 | 1 | 10 |  | 9012963.25 | 9012963.25 | 10 | [5 empty] | 1 | Completed | SWA | 2018-03-26
LANAO DEL NORTE | MAIGO | 1 | 1 | 2 |  | - | - | 2 | 1 | [5 empty] | CANCELLED |  | 2019-02-01 | ND
LANAO DEL NORTE | TUBOD | 1 | 2
| Kakai Renabor |  |  | 2 |  | 2000000 | 2000000 | 2 | [5 empty] | 1 | Completed | SWA | 2018-09-25
| Pigcarangan |  |  | 2 |  | 2000000 | 2000000 | 2 | [5 empty] | 1 | Completed | SWA | 2018-09-12
Sub-Total Lanao del Norte |  | 6 | 7 | 32 | 0 | 29012963.25 | 29012963.25 | 32 | 1 | 0 | 0 | 0 | 0 | 6
MISAMIS OCCIDENTAL | SAPANG DALAGA | 1 | 1 | 8 |  | 6400000 | 6400000 | 8 | [5 empty] | 1 | Completed | as of 3/18/2019 (SWA) | 2019-04-08
MISAMIS OCCIDENTAL | SINACABAN | 1 | 1 | 8 |  | 7958222.75 | 8070712.81 | 8 | [5 empty] | 1 | Completed |  | 2018-02-12 | MOT
MISAMIS OCCIDENTAL | PLARIDEL | 1 | 2 | 6 |  |  |  | 6 | [5 empty] | 2
| New Cartagena |  |  |  |  | 2929706.36 | 2929706.36 | [7 empty] | Completed |  | 2018-07-03 | MCN
| Panalsalan |  |  |  |  | 2929706.36 | 2929706.36 | [7 empty] | Completed |  | 2018-07-03 | MCN
MISAMIS OCCIDENTAL | TUDELA | 1 | 1 | 2 |  |  |  | 2 | [5 empty] | 1
| Gumbil |  |  |  |  | 2000000 | 2000000 | [7 empty] | Completed |  | 2019-07-15 | K.E
MISAMIS OCCIDENTAL | BONIFACIO | 1 | 2
| Bolinsong |  |  | 3 |  | 3000000 | 3000000 | 3 | [5 empty] | 1 | Completed | SWA | 12/20/2018
| Upper Usogan |  |  | 3 |  | 3000000 | 3000000 | 3 | [5 empty] | 1 | Completed | SWA | 2019-02-06
MISAMIS OCCIDENTAL | JIMENEZ | 1 | 2
| Carmen |  |  | 2 |  | 2000000 | 1661715.26 | 2 | [5 empty] | 1 | Completed | as of 3/4/2019 (SWA) | 2019-05-27
| Sinara Bajo |  |  | 2 |  | 2000000 | 2000000 | 2 | [5 empty] | 1 | Completed | SWA | 10/17/2018
MISAMIS OCCIDENTAL | PANAON | 1 | 2 | 4 |  |  |  | 4
| San Roque |  |  |  |  | 2000000 | 1536753.29 | [6 empty] | 1 | Completed | 7/31/2019 SWA | 2019-08-01
| San Juan |  |  |  |  | 2000000 | 1456122.03 | [6 empty] | 1 | Completed | AS OF 12/12/2019 SWA | 2020-01-02
Sub-Total Misamis Occidental |  | 7 | 11 | 38 | 0 | 36217635.47 | 34984716.11 | 38 | 0 | 0 | 0 | 0 | 0 | 11
MISAMIS ORIENTAL | CLAVERIA | 1 | 1 | 12 |  | 11989923.33 | 9600000 | 12 | [5 empty] | 1 | Completed |  | 2020-01-24 | NPJ
MISAMIS ORIENTAL | BALINGOAN | 1 | 6 | 12 |  |  |  | 12
| Dahilig |  |  |  |  | 2000000 | 2000000 | [6 empty] | 1 | Competed | SWA | 2019-03-20
| Mapua |  |  |  |  | 2000000 | 2000000 | [6 empty] | 1 | Competed | SWA | 2019-03-20
| Cabangasan |  |  |  |  | 2000000 | 2000000 | [6 empty] | 1 | Competed | SWA | 2019-03-20
| Kabulakan |  |  |  |  | 2000000 | 2000000 | [6 empty] | 1 | Competed | SWA | 2019-03-20
| Kauswagan |  |  |  |  | 2000000 | 2000000 | [6 empty] | 1 | Competed | SWA | 2019-03-20
| Lapinig |  |  |  |  | 2000000 | 2000000 | [6 empty] | 1 | Competed | SWA | 2019-03-20
MISAMIS ORIENTAL | CAGAYAN DE ORO CITY | 1 | 4 | 8 |  |  |  | 8
| Taglimao |  |  |  |  | 2000000 | 2000000 | [6 empty] | 1 | Competed |  | 2018-06-25 | EJD
| Mambuwaya |  |  |  |  | 2000000 | 2000000 | [6 empty] | 1 | Competed |  | 2018-06-25 | EJD
| FS Catanico |  |  |  |  | 2000000 | 2000000 | [6 empty] | 1 | Competed |  | 2017-07-19
| Tuburan |  |  |  |  | 2000000 | 1329418.87 | [6 empty] | 1 | Competed |  | 2017-07-19
Sub-Total Misamis Oriental |  | 3 | 11 | 32 | 0 | 31989923.33 | 28929418.87 | 32 | 0 | 0 | 0 | 0 | 0 | 11
TOTAL 2016 SALINTUBIG |  | 20 | 41 | 124 | 0 | 119220522.05 | 113455930.68 | 124 | 1 | 0 | 0 | 0 | 0 | 40

## 2017 SALINTUBIG COMPLETED
REGION X
2017 SALINTUBIG
as of June 26, 2020
PHYSICAL |  |  |  | FINANCIAL |  |  |  |  | CANCELLED PROJECTS | UNDER PREP | APPROVED FS/POW or DED PREP. | PROCUREMENT | ON-GOING | COMPLETED | STATUS | REMARKS | DATE UPDATED
PROVINCES | LGUs | NO. OF LGUs | TOTAL NO. OF PROJECTS | ALLOCATION | CANCELLED ALLOCATION | TOTAL RELEASES | TOTAL LIQUIDATION | AMOUNT OBLIGATED
BUKIDNON | DANGCAGAN | 1 | 1 | 2 |  | 2000000 | 2000000 | 2
| Kianggat | [12 empty] | 1 | COMPLETED | SWA | 2019-05-28
BUKIDNON | DON CARLOS | 1 | 1 | 2 |  | 2000000 | 1545192.15 | 2
| Kiara | [12 empty] | 1 | COMPLETED | SWA | 2019-07-30
BUKIDNON | KADINGILAN | 1 | 1 | 12 |  | 11845339.5 | 9090472.19 | 12 | [5 empty] | 1 | COMPLETED | AS OF 03/25/2019 SWA | 2020-05-15
BUKIDNON | SAN FERNANDO | 1 | 1 | 12 |  | 11990000 | 11990000 | 12 | [5 empty] | 1 | COMPLETED |  | 2017-09-16 | Monthly Meeting
Sub-Total Bukidnon |  | 4 | 4 | 28 | 0 | 27835339.5 | 24625664.34 | 28 | 0 | 0 | 0 | 0 | 0 | 4
LANAO DEL NORTE | BAROY | 1 | 1 | 2 |  |  |  | 2
| Riverside |  |  |  |  | 2000000 | 2000000 | [6 empty] | 1 | COMPLETED | SWA | 2019-02-07
LANAO DEL NORTE | MATUNGAO | 1 | 1 | 12 |  | 11989999.41 | 9206606.68 | [6 empty] | 1 | COMPLETED |  | 2019-07-19
LANAO DEL NORTE | NUNUNGAN | 1 | 1 | 12 |  | 11997224.07 | 9464529.25 | 12 | [5 empty] | 1 | Completed | SWA | 2018-07-26
LANAO DEL NORTE | POONA PIAGAPO | 1 | 1 | 2 |  | 1974844.94 | 1974844.94 | 2
| Lupitan | [12 empty] | 1 | Completed |  | 2018-05-29 | ND
LANAO DEL NORTE | TANGCAL | 1 | 1 | 12 |  | 11995914.06 | 7505314.95 | [6 empty] | 1 | COMPLETED | AS OF FEB. 20, 2020 SWA | 2020-03-03
Sub-Total Lanao del Norte |  | 5 | 5 | 40 | 0 | 39957982.48 | 30151295.82 | 16 | 0 | 0 | 0 | 0 | 0 | 5
MISAMIS OCCIDENTAL | ALORAN | 1 | 1 |  |  |  |  | 2
| Culpan |  |  | 2 |  | 2000000 | 2000000 | [6 empty] | 1 | Completed | as of 12-3-2018 (SWA) | 2019-02-08
MISAMIS OCCIDENTAL | PLARIDEL | 1 | 1 | 2 |  | 2000000 | 2000000 | 2
| Bato | [12 empty] | 1 | Completed | SWA | 2017-04-18 | CB
Sub-Total Misamis Occidental |  | 2 | 2 | 4 | 0 | 4000000 | 4000000 | 4 | 0 | 0 | 0 | 0 | 0 | 2
MISAMIS ORIENTAL | MAGSAYSAY | 1 | 2
| Tibon-tibon and Cabalawan |  |  | 4 |  | 4000000 | 3679640.79 | 2 | [5 empty] | 2 | Completed | as of 2/20/2019 (SWA) | 2019-03-15
Sub-Total Misamis Oriental |  | 1 | 2 | 4 | 0 | 4000000 | 3679640.79 | 2 | 0 | 0 | 0 | 0 | 0 | 2
TOTAL 2017 SALINTUBIG |  | 12 | 13 | 76 | 0 | 75793321.98 | 62456600.95 | 50 | 0 | 0 | 0 | 0 | 0 | 13

## 2018 SALINTUBIG
REGION X
2018 SALINTUBIG
as of June 26, 2020
PHYSICAL | [11 empty] | STATUS
PROVINCES | LGUs | NO. OF LGUs | ALLOCATION | TOTAL NO. OF PROJECTS | CANCELLED ALLOCATION | CANCELLED PROJECTS | UNDER PREP | APPROVED FS/POW or DED PREP. | PROCUREMENT | ON-GOING | COMPLETED
BUKIDNON | CABANGLASAN
| Jasaan | 1 | 2000000 | 1 | [6 empty] | 1 | COMPLETED
BUKIDNON | DANGCAGAN | 1 | 10000000 | 1 | [5 empty] | 1 |  | 3.83% Physical Accomplishment ongoing implementation
BUKIDNON | TALAKAG | 1 | 10000000 | 1 | [5 empty] | 1 |  | 81.40% Physical Accomplishment ongoing cancellation
Sub-Total Bukidnon |  | 3 | 22000000 | 3 | 0 | 0 | 0 | 0 | 0 | 2 | 1
CAMIGUIN | SAGAY | 1 | 2000000 | 1 | [6 empty] | 1 | COMPLETED
Sub-Total Camiguin |  | 1 | 2000000 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
LANAO DEL NORTE | BACOLOD
| Dimarao | 1 | 3000000 | 1 | [6 empty] | 1 | COMPLETED
LANAO DEL NORTE | KAUSWAGAN | 1 |  | 2
| Inudaran |  | 2000000 | [7 empty] | 1 | COMPLETED
| Paiton |  | 3000000 | [7 empty] | 1 | COMPLETED
LANAO DEL NORTE | LALA | 1 | 12000000 | 1 | [5 empty] | 1 |  | 85% Physical Accomplishment
LANAO DEL NORTE | MAGSAYSAY | 1 | 10000000 | 1 | [6 empty] | 1 | COMPLETED
LANAO DEL NORTE | SULTAN NAGA DIMAPORO | 1 |  | 3
| Capocao |  | 3000000 | [7 empty] | 1 | COMPLETED
| Topocon (Capocgo) |  | 2000000 | [7 empty] | 1 | COMPLETED
| Mabuhay |  | 3000000 | [7 empty] | 1 | COMPLETED
LANAO DEL NORTE | TUBOD | 1 |  | 3
| Baris (Lumangculob) |  | 3000000 | [7 empty] | 1 | COMPLETED
| Dalama |  | 3000000 | [7 empty] | 1 | COMPLETED
| Palao |  | 2000000 | [7 empty] | 1 | COMPLETED
Sub-Total Lanao del Norte |  | 6 | 46000000 | 11 | 0 | 0 | 0 | 0 | 0 | 1 | 10
MISAMIS OCCIDENTAL | ALORAN | 1 |  | 3
| Palayan |  | 3000000 | [7 empty] | 1 | COMPLETED
| San Pedro |  | 3000000 | [7 empty] | 1 | COMPLETED
| Sinampongan |  | 2000000 | [7 empty] | 1 | COMPLETED
MISAMIS OCCIDENTAL | BONIFACIO
| Dullan | 1 | 2000000 | 1 | [6 empty] | 1 | COMPLETED
MISAMIS OCCIDENTAL | TUDELA | 1 |  | 2
| Gala |  | 3000000 | [7 empty] | 1 | COMPLETED
| Yahong |  | 3000000 | [7 empty] | 1 | COMPLETED
Sub-Total Misamis Occidental |  | 3 | 16000000 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 6
TOTAL 2018 SALINTUBIG |  | 13 | 86000000 | 21 | 0 | 0 | 0 | 0 | 0 | 3 | 18

## 2019 SALINTUBIG
REGION X - AM
2019 SALINTUBIG
as of June 26, 2020
FY | REGION | PROVINCE | CITY / MUNICIPALITY | BARANGAY | ORIGINAL ALLOCATION | CANCELLED | DED/POW PREPARATION | FINALIZATION | PROCUREMENT | ON-GOING | COMPLETED | STATUS | REMARKS | DATE UPDATED
2019 | REGION X | BUKIDNON | DAMULOG | POBLACION | 10000000 |  |  |  |  | 1 |  | 48.51% PHYSICAL ACCOMPLISHMENT | AS OF 05/23//2020 SWA; | 2020-05-27
2019 | REGION X | BUKIDNON | KIBAWE | SPRING, LABUAGON, GUTAPOL & KIORAO | 15000000 |  |  |  | 1 |  |  | DED/POW APPROVED |  | 2020-03-02
TOTAL (BUKIDNON) |  |  | 2 | 2 | 25000000 | 0 | 0 | 0 | 1 | 1 | 0
2019 | REGION X | CAMIGUIN | SAGAY | MAYANA | 3000000 | [5 empty] | 1 | COMPLETED | as of 03/15/2020 SWA | 2019-12-10
TOTAL (CAMIGUIN) |  |  | 1 | 1 | 3000000 | 0 | 0 | 0 | 0 | 0 | 1
2019 | REGION X | Lanao del Norte | BACOLOD | BABALAYA | 3000000 |  |  | 1 |  |  |  | DED/POW FOR FINALIZATION |  | 2020-05-18 | ND
2019 | REGION X | Lanao del Norte | BACOLOD | KAHAYAG | 3000000 |  |  | 1 |  |  |  | DED/POW FOR FINALIZATION |  | 2020-05-18 | ND
2019 | REGION X | Lanao del Norte | NUNUNGAN | RARAB & POBLACION | 10000000 |  |  |  | 1 |  |  | DED APPROVED | NO FUND DOWNLOAD | 2020-01-10 | ND
2019 | REGION X | Lanao del Norte | SULTAN NAGA DIMAPORO | MABUHAY | 9000000 |  |  |  |  | 1 |  | 96.39% PHYSICAL ACCOMPLISHMENT | AS OF03/19//2020 SWA | 2020-03-19
|  |  |  | BANGCO | [7 empty] | COMPLETED | AS OF 03/19/2020 SWA | 2020-03-19
|  |  |  | CALIBAO | [7 empty] | COMPLETED | AS OF 03/19/2020 SWA | 2020-03-19
|  |  |  | KIRAPAN | [7 empty] | 87.03% Physical Accomplishment | AS OF 03/19//2020 SWA | 2020-03-19
|  |  |  | LANTAWAN | [7 empty] | 94.44% Physical Accomplishment | AS OF 003/19//2020 SWA | 2020-03-19
|  |  |  | MAHAYAHAY | [7 empty] | 96.39% Physical Accomplishment | AS OF 03/19//2020 SWA | 2020-03-31
TOTAL (LANAO DEL NORTE) |  |  | 3 | 4 | 25000000 | 0 | 0 | 2 | 1 | 1 | 0
2019 | REGION X | MISAMIS OCCIDENTAL | JIMENEZ | SETI | 3000000 |  |  |  |  | 1 |  | 40.00% Physical Accomplishment | AS OF 04/15/2020 SWA | 2020-04-23
2019 | REGION X | MISAMIS OCCIDENTAL | JIMENEZ | SINARA ALTO | 3000000 |  |  |  |  | 1 |  | 42.00% Physical Accomplishment | AS OF 04/15/2020 SWA | 2020-04-23
2019 | REGION X | MISAMIS OCCIDENTAL | JIMENEZ | SINARA BAJO | 3000000 |  |  |  |  | 1 |  | 45.00% Physical Accomplishment | AS OF 04/15/2020 SWA | 2020-04-23
2019 | REGION X | MISAMIS OCCIDENTAL | LOPEZ JAENA | MACALIBRE ALTO | 3000000 |  |  |  | 1 |  |  | DED/POW APPROVED | 2020-05-18 | 2020-01-24 | CEB
2019 | REGION X | MISAMIS OCCIDENTAL | PLARIDEL | DANAO | 3000000 |  |  |  |  | 1 |  | 74.93% Physical Accomplishment | AS OF 03/16//2020 suspended due to pandemic | 2020-04-28
2019 | REGION X | MISAMIS OCCIDENTAL | TUDELA | GALA | 3000000 |  |  |  | 1 |  |  | DED/POW APPROVED | UPDATE AS OF 1/30/2020 MONTHLY MEETING | 2020-01-31
2019 | REGION X | MISAMIS OCCIDENTAL | TUDELA | YAHONG | 3000000 |  |  |  | 1 |  |  | DED/POW APPROVED |  | 2020-01-24 | CEB
TOTAL (MIS.OCC.) |  |  | 4 | 7 | 21000000 | 0 | 0 | 0 | 3 | 4 | 0
2019 | REGION X | MISAMIS ORIENTAL | SUGBONGCOGON | ALICOMOHAN | 3000000 |  |  |  | 1 |  |  | DED and POW Approved |  | 2019-08-19
2019 | REGION X | MISAMIS ORIENTAL | SUGBONGCOGON | KIRAGING | 3000000 |  |  |  | 1 |  |  | DED and POW Approved |  | 2019-08-19
TOTAL (MIS.OR.) |  |  | 1 | 2 | 6000000 | 0 | 0 | 0 | 2 | 0 | 0
GRAND TOTAL |  |  | 11 | 16 | 80000000 | 0 | 0 | 2 | 7 | 6 | 1

## 2020 SALINTUBIG
REGION X - AM
2020 SALINTUBIG
as of June 26, 2020
FY | REGION | PROVINCE | CITY / MUNICIPALITY | BARANGAY | PROJECT TITLE | NG ALLOCATION | CANCELLED | DED/POW PREPARATION | FINALIZATION | PROCUREMENT | ON-GOING | COMPLETED | STATUS | REMARKS | DATE UPDATED
2020 | REGION X | BUKIDNON | CABANGLASAN | CABULOHAN | REHABILITATION OF CROSSING CABULOHAN WATER SYSTEM | 11652798 |  |  |  | 1 |  |  | DED & POW APPROVED |  | 2020-06-23
2020 | REGION X | BUKIDNON | MANOLO FORTICH | DICKLUM | POBLACION-DICKLUM WATER SYSTEM | 12093596 |  |  |  | 1 |  |  | DED & POW APPROVED |  | 2020-06-03
2020 | REGION X | BUKIDNON | SAN FERNANDO | LITTLE BAGUIO | WATER DISTRIBUTION SYSTEM (LEVEL III) | 11824122 |  |  | 1 |  |  |  | DED & POW FINALIZATION |  | 2020-01-27
TOTAL (BUKIDNON) |  |  | 3 | 3 |  | 35570516 | 0 | 0 | 1 | 2 | 0 | 0
2020 | REGION X | CAMIGUIN | MAHINOG | POBLACION, SAN JOSE, HUBANGON |  | 11067328 |  |  | 1 |  |  |  | DED & POW FINALIZATION |  | 2020-03-03
2020 | REGION X | CAMIGUIN | SAGAY | BON-BON, CUÑA, ALINGILAN |  | 10797854 |  |  | 1 |  |  |  | DED & POW FINALIZATION |  | 2020-04-17
TOTAL (CAMIGUIN) |  |  | 2 | 2 |  | 21865182 | 0 | 0 | 2 | 0 | 0 | 0
2020 | REGION X | LANAO DEL NORTE | BAROY | BATO |  | 11238652 |  | 1 |  |  |  |  | NO SUBMISSION |  | 2020-01-27
2020 | REGION X | LANAO DEL NORTE | MUNAI | TAMPARAN, TAMBO |  | 10797854 |  |  |  | 1 |  |  | DED & POW APPROVED |  | 2020-03-06
2020 | REGION X | LANAO DEL NORTE | NUNUNGAN |  |  | 11508127
|  |  |  | BANCO | [5 empty] | 1 |  |  | DED & POW APPROVED |  | 2020-03-02
|  |  |  | KALUDAN | [5 empty] | 1 |  |  | DED & POW APPROVED |  | 2020-03-02
2020 | REGION X | LANAO DEL NORTE | SULTAN NAGA DIMAPORO |  |  | 11067328
|  |  |  | PIRAKA | [5 empty] | 1 |  |  | DED & POW APPROVED |  | 2020-05-19
|  |  |  | DALAMA | [5 empty] | 1 |  |  | DED & POW APPROVED |  | 2020-06-08
|  |  |  | ROBUGON | [5 empty] | 1 |  |  | DED & POW APPROVED |  | 2020-06-08
|  |  |  | PANTAON | [5 empty] | 1 |  |  | DED & POW APPROVED |  | 2020-06-08
TOTAL (LANAO DEL NORTE) |  |  | 4 | 8 |  | 44611961 | 0 | 1 | 0 | 7 | 0 | 0
2020 | REGION X | MISAMIS OCCIDENTAL | JIMENEZ | MATUGAS BAJO | CONSTRUCTION/REHABILITATION OF WATER SYSTEM LEVEL 2 & LEVEL 3 - SALINTUBIG 2020 | 12479848 |  |  |  | 1 |  |  | DED & POW APPROVED |  | 2020-02-26
2020 | REGION X | MISAMIS OCCIDENTAL | SINACABAN | SAN LORENZO |  | 12479848 |  | 1 |  |  |  |  | NO SUBMISSION |  | 2020-01-27
TOTAL (MISAMIS OCCIDENTAL) |  |  | 2 | 2 |  | 24959696 | 0 | 1 | 0 | 1 | 0 | 0
2020 | REGION X | MISAMIS ORIENTAL | BINUANGAN | KITAMBAN, KITAMBIS, POBLACION |  | 11508127 |  |  | 1 |  |  |  | DED & POW FINALIZATION |  | 2020-01-27
2020 | REGION X | MISAMIS ORIENTAL | LAGONGLONG | KAUSWAGAN | CONSTRUCTION OF KAUSWAGAN, LAGONGLONG WATER SUPPLY SYSTEM | 11238652 |  |  |  | 1 |  |  | DED & POW APPROVED |  | 2020-04-21
2020 | REGION X | MISAMIS ORIENTAL | MAGSAYSAY | KIBUNGSOD, CABUBUHAN, POBLACION, VILLA FELIPA |  | 11383323 |  |  |  | 1 |  |  | DED & POW APPROVED |  | 2020-02-27
TOTAL (MISAMIS ORIENTAL) |  |  | 3 | 3 |  | 34130102 | 0 | 0 | 1 | 2 | 0 | 0
|  |  | 14 | 18 |  | 161137457 | 0 | 2 | 4 | 12 | 0 | 0

## SALINTUBIG-2018 SWA SUB ON-TIME
2018 SALINTUBIG
SWA SUBMISSION
as of June 26, 2020
MUNICIPALITY |  | BARANGAY | % ACCOMPLISHMENT | REMARKS | DATE UPDATED | SUBMITED ON-TIME
BUKIDNON
1 | CABANGLASAN | Jasaan | COMPLETED | #REF! | #REF! | #REF!
2 | DANGCAGAN |  | 3.83% Physical Accomplishment ongoing implementation | #REF! | #REF! | #REF!
3 | TALAKAG |  | 81.40% Physical Accomplishment ongoing cancellation | #REF! | #REF! | #REF!
|  | Total No. of Project = 3 | Total No. of SWA Submitted |  |  | #REF!
CAMIGUIN
1 | SAGAY |  | COMPLETED | #REF! | #REF! | #REF!
|  | Total No. of Project = 1 | Total No. of SWA Submitted |  |  | #REF!
LANAO DEL NORTE
1 | BACOLOD | Dimarao | COMPLETED | #REF! | #REF! | #REF!
2 | KAUSWAGAN | Inudaran | COMPLETED | #REF! | #REF! | #REF!
| KAUSWAGAN | Paiton | COMPLETED | #REF! | #REF! | #REF!
3 | LALA |  | 85% Physical Accomplishment | #REF! | #REF! | #REF!
4 | MAGSAYSAY |  | COMPLETED | #REF! | #REF! | #REF!
5 | SULTAN NAGA DIMAPORO | Capocao | COMPLETED | #REF! | #REF! | #REF!
| SULTAN NAGA DIMAPORO | Topocon (Capocgo) | COMPLETED | #REF! | #REF! | #REF!
| SULTAN NAGA DIMAPORO | Mabuhay | COMPLETED | #REF! | #REF! | #REF!
6 | TUBOD | Baris (Lumangculob) | COMPLETED | #REF! | #REF! | #REF!
| TUBOD | Dalama | COMPLETED | #REF! | #REF! | #REF!
| TUBOD | Palao | COMPLETED | #REF! | #REF! | #REF!
|  | Total No. of Project = 11 | Total No. of SWA Submitted |  |  | #REF!
MISAMIS OCCIDENTAL
1 | ALORAN | Palayan | COMPLETED | #REF! | #REF! | #REF!
| ALORAN | San Pedro | COMPLETED | #REF! | #REF! | #REF!
| ALORAN | Sinampongan | COMPLETED | #REF! | #REF! | #REF!
2 | BONIFACIO | Dullan | COMPLETED | #REF! | #REF! | #REF!
3 | TUDELA | Gala | COMPLETED | #REF! | #REF! | #REF!
| TUDELA | Yahong | COMPLETED | #REF! | #REF! | #REF!
|  | Total No. of Project = 7 | Total No. of SWA Submitted |  |  | #REF!
|  | GTotal No. of Project = 22 | GTotal No. of SWA Submitted |  |  | #REF!

## AM WATER-2018 SWA SUB ON-TIME
2018 AM-WATER
SWA SUBMISSION
as of June 26, 2020
MUNICIPALITY |  | BARANGAY | % ACCOMPLISHMENT | REMARKS | DATE UPDATED | SUBMITED ON-TIME
BUKIDNON
1 | BAUNGON | BRGY. SAN VICENTE - BRGY SALIMBALAN | COMPLETED | as of 11/8/2019 SWA | 2019-12-09 | -
2 | KALILANGAN | BARANGAY LAMPANUSAN | 80.33% Physical Accomplishment | AS OF 05/20/2020 SWA ongoing cancellation | 2020-06-03 | 0
3 | KITAOTAO | SINUDA | CANCELLED | 0 | 0 | -
4 | LANTAPAN | BARANGAY KAATUAN, LANTAPAN | 98.29% Physical Accomplishment | AS OF 5/20/2020 (under suspension due to COVID-19) | 2020-06-25 | 0
5 | MANOLO FORTICH | SANTIAGO | COMPLETED | as of 8/15/2019 (SWA) | 2019-09-23 | -
6 | MANOLO FORTICH | KALUGMANAN | COMPLETED | AS OF 9/30/2019 SWA | 2020-01-09 | -
7 | MANOLO FORTICH | TICALA | COMPLETED | as of 8/1/2019 (SWA) | 2019-08-19 | -
8 | MANOLO FORTICH | MAMPAYAG | COMPLETED | as of 8/8/2019 (SWA) | 2019-08-20 | -
9 | SAN FERNANDO | NACABUKLAD, TUGOP, HALAPITAN AND LITTLE BAGUIO | COMPLETED | as of 11/5/2019 SWA | 11/25/2019 | -
|  | Total No. of Project = 9 | Total No. of SWA Submitted |  |  | 0
CAMIGUIN
1 | SAGAY | BRGY. BUGANG TO BRGY. MAYANA | COMPLETED | as of 3/15/2019 (SWA) | 2019-04-25 | -
2 | SAGAY | SITIO KILOMOY, BRGY. BACNIT | COMPLETED | as of 2/15/2019 (SWA | 2019-02-27 | -
|  | Total No. of Project = 2 | Total No. of SWA Submitted |  |  | 0
LANAO DEL NORTE
1 | KAUSWAGAN | TUGAR | COMPLETED | as of 3/18/2019 (SWA) | 2019-03-25 | -
2 | KAUSWAGAN | BARAASON | COMPLETED | as of 3/18/2019 (SWA) | 2019-03-25 | -
3 | NUNUNGAN | BARANGAY LUPITAN | COMPLETED | Monthly Meeting | 2019-03-08 | -
4 | PANTAR | BRGYS. CAMPONG, POBLACION & PANTAR WEST (BANGCAL) | COMPLETED | as of 12/20/2019 SWA | 2019-12-23 | -
5 | PANTAR | BRGYS. KALANGANAN EAST TO LOWER KALANGANAN (TANCAL) | COMPLETED | as of 12/20/2019 SWA | 2019-12-23 | -
6 | SULTAN NAGA DIMAPORO | BARANGAYS MAMAGUM, BANGAAN, SIGAYAN | COMPLETED | Mamagum - 100% SWA | 2019-06-20 | -
Sigayan - 100% as of 7/22/2019 SWA
Bangaan-100% SWA
|  | Total No. of Project = 6 | Total No. of SWA Submitted |  |  | 0
MISAMIS OCCIDENTAL
1 | JIMENEZ | BRGY. CORRALES, TARAKA, NAGA, NACIONAL, STA. CRUZ, PALILAN, AND TABO-O | COMPLETED | 0 | 2020-01-10 | 0
|  | Total No. of Project = 1 | Total No. of SWA Submitted |  |  | 0
MISAMIS ORIENTAL
1 | BINUANGAN | BARANGAY DAMPIAS, MOSANGOT, POBLACION AND MABINI | COMPLETED | 0 | 2020-06-23 | 0
2 | JASAAN | BARANGAY APLAYA | COMPLETED | AS OF 2/19/2020 SWA | 2020-03-30 | 0
3 | KINOGUITAN | MUNICIPAL WIDE, BARANGAY KAGUMAHAN | COMPLETED | 0 | 2020-06-23 | 0
4 | LUGAIT | POBLACION | 78.00% Physical Accomplishment | AS OF 2/15/2020 SWA ongoing implementation | 2020-03-03 | 0
5 | MANTICAO | PANIANGAN, POBLACION, PUNTA SILUM | COMPLETED | FOR FINAL INSPECTION | 2020-01-10 | 0
6 | TAGOLOAN | NATUMOLAN | CANCELLED | Reverted and remitted the unutilized fund to the Bureau of the Treasury | 2019-12-03 | -
|  | Total No. of Project = 6 | Total No. of SWA Submitted |  |  | 0
|  | GTotal No. of Project = 24 | GTotal No. of SWA Submitted |  |  | 0

## AM-2018 others SWA SUB ON-TIME
2018 AM-OTHERS
SWA SUBMISSION
as of June 26, 2020
MUNICIPALITY |  | BARANGAY | % ACCOMPLISHMENT | REMARKS | DATE UPDATED | SUBMITED ON-TIME
BUKIDNON
2018 AM-LAR
1 | CABANGLASAN | MANDAING | COMPLETED | SWA WITH 100% PHYSICAL ACCOMPLISHMENT AS OF SEPT. 30, 2019 | 2019-10-30 | -
2 | DAMULOG | AGUINALDO STREET JCT. BONIFACIO STREET TO JCT. MANLABAO STREET, POBLACION | COMPLETED | SWA | 2019-03-04 | -
3 | DAMULOG | C.M. RECTO STREET JCT. MANLABAO STREET TO SAN ISIDRO STREET | COMPLETED | SWA | 2019-03-04 | -
4 | DANGCAGAN | MIARAY-TAGONGTONG | COMPLETED | as of 3/8/2019 (SWA) | 2019-03-13 | -
5 | DANGCAGAN | KIANGGAT-SAN VICENTE | COMPLETED | as of January 24, 2019 (SWA) | 2019-03-14 | -
6 | DON CARLOS | DON CARLOS SUR | COMPLETED | as of 7/24/2019 (SWA) | 7/25/2019 | -
7 | IMPASUG-ONG | SITIO QUISUMBING, IMPALUTAO, IMPASUG-ONG, BUKDINON | COMPLETED | Turn over last January 29, 2019 | 2019-02-18 | -
8 | KADINGILAN | BARANGAY PAY-AS | COMPLETED | AS OF 8/20/2019 SWA | 2020-01-31 | -
9 | KIBAWE | JUNCTION BARANGAY OLD KIBAWE NATIONAL HIGHWAY - SITIO GRECAN, BARANGAY OLD KIBAWE | COMPLETED | as of 6/3/2019 (SWA) | 2019-06-18 | -
10 | LIBONA | PUROK 1, PUROK 4, POBLACION | COMPLETED | SWA | 2019-03-19 | -
11 | MALITBOG | POBLACION-MINDAGAT | COMPLETED | as of 10/2/2019 SWA; 11/22/2019 PROJECT INSPECTION REPORT | 2020-01-09 | -
12 | MARAMAG | NORTH POBLACION | COMPLETED | AS OF 04/27/2020 SWA | 2020-04-30 | 0
13 | PANGANTUCAN | CONCEPCION | COMPLETED | AS OF 9/27/2019 SWA | 2019-09-16 | -
14 | PANGANTUCAN | NEW EDEN | COMPLETED | AS OF 9/27/2019 SWA | 2020-01-27 | -
15 | QUEZON | POBLACION | COMPLETED | Turn over last February 13, 2019 | 2019-02-18 | -
16 | SUMILAO | BARANGAY LUPIAGAN | COMPLETED | AS OF DECEMBER19, 2019 SWA | 2019-12-06 | 0
17 | TALAKAG | SITIO BABALAYAN-SITIO BATANG ROAD BRGY COSINA | COMPLETED | AS OF DECEMBER 2019 SWA | 2020-01-10 | -
|  |  | SubTotal No. of SWA Submitted |  |  | 0
2018 AM-OTHERS
18 | MANOLO FORTICH | TANKULAN | COMPLETED | as of 5/30/2019 (SWA) | 2019-06-10 | -
19 | MARAMAG | NORTH POBLACION | COMPLETED | AS OF 1/20/2020 SWA | 2020-01-27 | -
|  |  | SubTotal No. of SWA Submitted |  |  | 0
|  |  | Total No. of SWA Submitted |  |  | 0
CAMIGUIN
2018 AM-LAR
1 | CATARMAN | MANDUAO | COMPLETED | as of 4/15/2019 (SWA) | 2019-04-25 | -
2 | GUINSILIBAN | NATIONAL HIGHWAY, SOUTH POBLACION TO KIWAKAT | COMPLETED | 0 | 2020-06-26 | 1
3 | MAHINOG | TACANGON, POBLACION | COMPLETED | as of 3/25/2019 (SWA) | 2019-04-15 | -
4 | MAHINOG | BRHP, BENONI | COMPLETED | SWA | 2019-02-22 | -
5 | MAHINOG | HUBANGON | COMPLETED | as of 1/11/2019 (SWA) | 2019-04-15 | -
6 | MAHINOG | BENONI | COMPLETED | SWA | 2019-02-22 | -
7 | MAHINOG | POBLACION | COMPLETED | as of 3/22/2019 (SWA) | 2019-04-15 | -
8 | MAMBAJAO (Capital) | GOVERNMENT CENTER, LACAS, POBLACION | COMPLETED | as of 11/25/2019 SWA | 2019-12-17 | -
9 | SAGAY | BRGY. MAYANA | COMPLETED | as of 2/15/2019 (SWA) | 2019-02-27 | -
|  |  | SubTotal No. of SWA Submitted |  |  | 1
2018 AM-OTHERS
10 | MAMBAJAO (Capital) | MAMBAJAO, CAMIGUIN | COMPLETED | PURCHASE ORDER, ACCEPTANCE AND INSPECTION REPORT | 2019-10-09 | -
|  |  | SubTotal No. of SWA Submitted |  |  | 0
|  |  | Total No. of SWA Submitted |  |  | 1
LANAO DEL NORTE
2018 AM-LAR
1 | BACOLOD | BABALAYA | COMPLETED | as of February 2019 (SWA) | 2019-04-24 | -
2 | BALOI | BARANGAY ABAGA | COMPLETED | 0 | 2019-04-01 | -
3 | BALOI | BRGY. CORMATAN TO SIGAYAN | COMPLETED | 0 | 2019-04-01 | -
4 | BAROY | PUROK 2 & 3, MALIWANAG | COMPLETED | as of 7/21/2019 (SWA) | 2019-03-07 | -
5 | KAPATAGAN | POBLACION | COMPLETED | SWA | 2019-04-22 | -
6 | KAUSWAGAN | KAWIT ORIENTAL | COMPLETED | SWA | 2019-02-22 | -
7 | KAUSWAGAN | KAWIT OCCIDENTAL | COMPLETED | Monthly Meeting | 2019-03-08 | -
8 | KAUSWAGAN | POBLACION | COMPLETED | SWA | 2019-02-22 | -
9 | KOLAMBUGAN | INUDARAN | COMPLETED | as of 4/9/2019 (SWA) | 2019-04-23 | -
10 | LALA | REBE | COMPLETED | 0 | 2019-03-04 | -
11 | LINAMON | BARANGAY MAG-ONG | COMPLETED | SWA | 2019-06-20 | -
12 | LINAMON | BARANGAY BOSQUE | COMPLETED | SWA | 2019-02-04 | -
13 | LINAMON | BARANGAY ROBOCON | COMPLETED | Monthly Meeting | 2019-03-08 | -
14 | MAGSAYSAY | POBLACION TO LEMONCRET | COMPLETED | as of 3/12/2019 (SWA) | 2019-03-25 | -
15 | MAIGO | BALAGATASA | COMPLETED | as of 4/22/2019 (SWA) | 2019-04-26 | -
16 | MATUNGAO | BRGY. BATANGAN | COMPLETED | Monthly Meeting | 2019-03-08 | -
17 | MUNAI | PANGGAO-TAMPARAN | 23.91% Physical Accomplishment | AS OF 04/15/2020 SWA ongoing implementation | 2020-05-05 | 0
18 | PANTAO RAGAT | BARANGAY CABASAGAN | COMPLETED | as of 3/12/2019 (SWA) | 2019-03-26 | -
19 | PANTAR | LUMBA PUNOD TO SUNDIGA PUNOD | COMPLETED | SWA | 2018-09-11 | -
20 | POONA PIAGAPO | BRGY. NUNANG TO BRGY. POBLACION | 37.76% Physical Accomplishment | AS OF 1/15/2020 SWA ongoing cancellation | 2020-06-26 | 0
21 | SALVADOR | BARANGAY PADIANAN | COMPLETED | 2019-03-25 | 2019-04-24 | -
22 | SAPAD | BARANGAY PANOLOON TO BARANGAY KATIPUNAN | COMPLETED | SWA | 12/21/2018 | -
23 | TAGOLOAN | BRGY. KIAZAR | CANCELLED | No download/no GFH Passer | 2019-03-04 | -
24 | TANGCAL | BARANGAY BUBONG TO LINAO | COMPLETED | as of 6/20/2019 (SWA) | 2019-07-03 | -
25 | TUBOD | POBLACION (Legaspi - Gom-os) | COMPLETED | as of 4/22/2019 (SWA) | 2019-04-23 | -
|  |  | SubTotal No. of SWA Submitted |  |  | 0
2018 AM-OTHERS
26 | KAUSWAGAN | UPPER BAGUMBAYAN | COMPLETED | as of 3/5/2019 (SWA) | 2019-04-02 | -
27 | LINAMON | DRRMO/POBLACION | COMPLETED | 0 | 2019-07-19 | -
28 | LINAMON | POBLACION | COMPLETED | Monthly Meeting | 2019-03-08 | -
29 | NUNUNGAN | BARANGAY RABARAN | COMPLETED | Monthly Meeting | 2019-03-08 | -
30 | SULTAN NAGA DIMAPORO | SND, LDN | COMPLETED | 0 | 2019-09-09 | -
|  |  | SubTotal No. of SWA Submitted |  |  | 0
|  |  | Total No. of SWA Submitted |  |  | 0
MISAMIS OCCIDENTAL
2018 AM-LAR
1 | ALORAN | BRGY. TUBURAN | COMPLETED | UPDATE AS OF 1/30/2020 MONTHLY MEETING | 2020-01-31 | 0
2 | BALIANGAO | BRGY. MISOM - BPLS ROAD | COMPLETED | as of 2/2019 (SWA) | 2019-05-03 | -
3 | BONIFACIO | BOLINSONG | COMPLETED | SWA | 12/20/2018 | -
4 | CALAMBA | BARANGAY LIBERTAD | COMPLETED | as of 3/28/2019 (SWA) | 2019-03-29 | -
5 | CLARIN | SEGATIC DAKU AND CABUNGA-AN | COMPLETED | as of 2/7/2019 (SWA) | 2/18/019 | -
6 | CONCEPCION | BRGY. NEW CASUL | CANCELLED | 0 | 2020-01-10 | -
7 | DON VICTORIANO CHIONGBIAN (DON MARIANO MARCOS) | PUROK 5, LALUD | COMPLETED | as of 6/27/2019 (SWA) | 2019-09-09 | -
8 | LOPEZ JAENA | BRGY. RIZAL | COMPLETED | as of 5/22/2019 (SWA) | 2019-06-24 | -
9 | PANAON | BRGY. SAN ROQUE | COMPLETED | 4/29/2019 SWA | 2019-08-01 | -
10 | PANAON | BRGY. PUNTA | COMPLETED | 4/25/2019 SWA | 2019-08-01 | -
11 | PLARIDEL | SITIO TAGAYTAY - BRGY. DIVISORIA | COMPLETED | 0 | 2019-02-18 | -
12 | PLARIDEL | PUROK PARPAGAYO - BRGY. LAO PROPER | COMPLETED | 0 | 2019-02-18 | -
13 | SAPANG DALAGA | SALIMPUNO TO CAPUNDAG ROAD SECTION | COMPLETED | as of 6/20/2019 (SWA) | 2019-06-27 | -
14 | SINACABAN | LIBERTAD ALTO | COMPLETED | SWA | 2019-02-22 | -
15 | TUDELA | YAHONG | COMPLETED | as of 12/5/2018 (SWA) | 2019-06-24 | -
|  |  | Total No. of SWA Submitted |  |  | 0
MISAMIS ORIENTAL
2018 AM-LAR
1 | ALUBIJID | BARANGAY LOGUILO | COMPLETED | AS OF 12/13/2019 SWA;FOR FINAL INSPECTION | 2019-12-24 | -
2 | BALINGASAG | SITIO VENCER, BARANGAY COGON | COMPLETED | SWA | 2019-03-20 | -
3 | CLAVERIA | SITIO IMPAKIBIL, APOSKAHOY | COMPLETED | as of 7/9/2019 SWA | 7/24/2019 | -
4 | GITAGUM | PUROK 6, G.PELAEZ | COMPLETED | SWA | 2019-02-06 | -
5 | KINOGUITAN | BRGY. CALUBO TO BRGY. KITOTOK ROAD | COMPLETED | PER ENGR. PUIG | 2020-06-23 | 0
6 | LAGONGLONG | SAPONG-AGONG GAMAY TABOK | COMPLETED | as of 12/31/2018 (SWA) | 2019-04-03 | -
7 | LAGONGLONG | SAPONG, TABOK | COMPLETED | as of 12/27/2018 (SWA) | 2019-04-03 | -
8 | LIBERTAD | PUROK 10 (TAMBO), BRGY. POBLACION | COMPLETED | as of 7/22/2019 (SWA) | 2019-08-12 | -
9 | MAGSAYSAY (LINUGOS) | CABUBUHAN-KAUSWAGAN | COMPLETED | as of 6/26/2019 (SWA) | 2016-07-10 | -
10 | MEDINA | P-2 TO P-3, BRGY. ROAD, SAN JOSE | COMPLETED | as of 5/23/2019 (SWA) | 2019-05-28 | -
11 | MEDINA | P-6, PAHINDONG | COMPLETED | as of 5/23/2019 (SWA) | 2019-05-28 | -
12 | NAAWAN | BARANGAY MAPULOG | COMPLETED | SWA | 2019-05-24 | -
13 | OPOL | BARANGAY AWANG | COMPLETED | SWA | 2019-05-28 | -
14 | SALAY | SITIO SALAHON, BRGY. ALIPUATON | COMPLETED | as of 3/29/2019 SWA | 2019-04-15 | -
15 | SUGBONGCOGON | BARANGAY MANGGA | COMPLETED | 370 meters: 100% as of 3/28/2019 (SWA) | 2019-04-08 | -
350 meters: 100% as of 3/28/2019 (SWA)
16 | TAGOLOAN | POBLACION | CANCELLED | RETURNED TO BTr | 2020-01-10 | -
17 | TALISAYAN | BARANGAY BUGDANG | COMPLETED | AS OF MAY 2020 SWA | 2020-06-05 | 0
18 | TALISAYAN | BARANGAY MAGKARILA | COMPLETED | AS OF MAY 2020 SWA | 2020-06-05 | 0
19 | VILLANUEVA | SITIO BANBAN TO SITIO MADRID, BRGY. LOOC | COMPLETED | PER ENGR. PUIG BUT HAS DEFFECTS | 2020-06-23 | 0
|  |  | SubTotal No. of SWA Submitted |  |  | 0
2018 AM-OTHERS
20 | BALINGOAN | MUNICIPAL WIDE | 90.00% Physical Accompishment | ongoing implementation | 2020-06-23 | 0
21 | BALINGOAN | MUNICIPAL WIDE | COMPLETED | 0 | 2019-09-16 | 0
22 | INITAO | APAS, INITAO | COMPLETED | UPDATE PER ENGR.PUIG | 2020-06-23 | 0
23 | LAGUINDINGAN | BARANGAY TUBAJON | COMPLETED | as of 10/15/2019 SWA | 2019-10-28 | -
|  |  | SubTotal No. of SWA Submitted |  |  | 0
|  |  | Total No. of SWA Submitted |  |  | 0
|  |  | GTotal No. of SWA Submitted |  |  | 1

## SCORECARD
as of June 26, 2020
MUNICIPALITY |  | BARANGAY | TOTAL NO. OF PROJECTS | % ACCOMPLISHMENT | DATE UPDATED |  | TOTAL NO. OF SWA SUBMITTED | PROGRAM
BUKIDNON
1 | CITY OF MALAYBALAY | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | CITY OF VALENCIA | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | BAUNGON | BRGY. SAN VICENTE - BRGY SALIMBALAN | 1 | COMPLETED | 2019-12-09 | - |  | 2018 AM-WATER | 1
4 | CABANGLASAN | Jasaan | 2 | COMPLETED | #REF! | #REF! |  | 2018 SALINTUBIG | 1
| CABANGLASAN | MANDAING |  | COMPLETED | 2019-10-30 | - |  | 2018 AM-LAR | 1
5 | DAMULOG | AGUINALDO STREET JCT. BONIFACIO STREET TO JCT. MANLABAO STREET, POBLACION | 2 | COMPLETED | 2019-03-04 | - |  | 2018 AM-LAR | 1
| DAMULOG | C.M. RECTO STREET JCT. MANLABAO STREET TO SAN ISIDRO STREET |  | COMPLETED | 2019-03-04 | - |  | 2018 AM-LAR | 1
6 | DANGCAGAN |  | 3 | 3.83% Physical Accomplishment ongoing implementation | #REF! | #REF! | #REF! | 2018 SALINTUBIG |  |  |  | 1
| DANGCAGAN | MIARAY-TAGONGTONG |  | COMPLETED | 2019-03-13 | - |  | 2018 AM-LAR | 1
| DANGCAGAN | KIANGGAT-SAN VICENTE |  | COMPLETED | 2019-03-14 | - |  | 2018 AM-LAR | 1
7 | DON CARLOS | DON CARLOS SUR | 1 | COMPLETED | 7/25/2019 | - | - | 2018 AM-LAR | 1
8 | IMPASUG-ONG | SITIO QUISUMBING, IMPALUTAO, IMPASUG-ONG, BUKDINON | 1 | COMPLETED | 2019-02-18 | - | - | 2018 AM-LAR | 1
9 | KADINGILAN | BARANGAY PAY-AS | 1 | COMPLETED | 2020-01-31 | - | - | 2018 AM-LAR | 1
10 | KALILANGAN | BARANGAY LAMPANUSAN | 1 | 80.33% Physical Accomplishment | 2020-06-03 | 0 | 0 | 2018 AM-WATER |  | 1
11 | KIBAWE | JUNCTION BARANGAY OLD KIBAWE NATIONAL HIGHWAY - SITIO GRECAN, BARANGAY OLD KIBAWE | 1 | COMPLETED | 2019-06-18 | - | - | 2018 AM-LAR | 1
12 | KITAOTAO | SINUDA | 1 | CANCELLED | 0 | - | - | 2018 AM-WATER |  |  |  |  | 1
13 | LANTAPAN | BARANGAY KAATUAN, LANTAPAN | 1 | 98.29% Physical Accomplishment | 2020-06-25 | 0 | 0 | 2018 AM-WATER |  | 1
14 | LIBONA | PUROK 1, PUROK 4, POBLACION | 1 | COMPLETED | 2019-03-19 | - | - | 2018 AM-LAR | 1
15 | MALITBOG | POBLACION-MINDAGAT | 1 | COMPLETED | 2020-01-09 | - | - | 2018 AM-LAR | 1
16 | MANOLO FORTICH | SANTIAGO | 5 | COMPLETED | 2019-09-23 | - |  | 2018 AM-WATER | 1
| MANOLO FORTICH | KALUGMANAN |  | COMPLETED | 2020-01-09 | - |  | 2018 AM-WATER | 1
| MANOLO FORTICH | TICALA |  | COMPLETED | 2019-08-19 | - |  | 2018 AM-WATER | 1
| MANOLO FORTICH | MAMPAYAG |  | COMPLETED | 2019-08-20 | - |  | 2018 AM-WATER | 1
| MANOLO FORTICH | TANKULAN |  | COMPLETED | 2019-06-10 | - |  | 2018 AM-OTHERS | 1
17 | MARAMAG | NORTH POBLACION | 2 | COMPLETED | 2020-04-30 | 0 | 0 | 2018 AM-LAR |  | 1
| MARAMAG | NORTH POBLACION |  | COMPLETED | 2020-01-27 | - |  | 2018 AM-OTHERS | 1
18 | PANGANTUCAN | CONCEPCION | 2 | COMPLETED | 2019-09-16 | - |  | 2018 AM-LAR | 1
| PANGANTUCAN | NEW EDEN |  | COMPLETED | 2020-01-27 | - |  | 2018 AM-LAR | 1
19 | QUEZON | POBLACION | 1 | COMPLETED | 2019-02-18 | - | - | 2018 AM-LAR | 1
20 | SAN FERNANDO | NACABUKLAD, TUGOP, HALAPITAN AND LITTLE BAGUIO | 1 | COMPLETED | 11/25/2019 | - | - | 2018 AM-WATER | 1
21 | SUMILAO | BARANGAY LUPIAGAN | 1 | COMPLETED | 2019-12-06 | 0 | 0 | 2018 AM-LAR | 1
22 | TALAKAG | 0 | 2 | 81.40% Physical Accomplishment ongoing cancellation | #REF! | #REF! | #REF! | 2018 SALINTUBIG |  | 1
| TALAKAG | SITIO BABALAYAN-SITIO BATANG ROAD BRGY COSINA |  | COMPLETED | 2020-01-10 | - |  | 2018 AM-LAR | 1
CAMIGUIN
1 | CATARMAN | MANDUAO | 1 | COMPLETED | 2019-04-25 | - | - | 2018 AM-LAR | 1
2 | GUINSILIBAN | NATIONAL HIGHWAY, SOUTH POBLACION TO KIWAKAT | 1 | COMPLETED | 2020-06-26 | 1 | 1 | 2018 AM-LAR |  | 1
3 | MAHINOG | TACANGON, POBLACION | 5 | COMPLETED | 2019-04-15 | - |  | 2018 AM-LAR | 1
| MAHINOG | BRHP, BENONI |  | COMPLETED | 2019-02-22 | - |  | 2018 AM-LAR | 1
| MAHINOG | HUBANGON |  | COMPLETED | 2019-04-15 | - |  | 2018 AM-LAR | 1
| MAHINOG | BENONI |  | COMPLETED | 2019-02-22 | - |  | 2018 AM-LAR | 1
| MAHINOG | POBLACION |  | COMPLETED | 2019-04-15 | - |  | 2018 AM-LAR | 1
4 | MAMBAJAO | GOVERNMENT CENTER, LACAS, POBLACION | 2 | COMPLETED | 2019-12-17 | - |  | 2018 AM-LAR | 1
| MAMBAJAO | MAMBAJAO, CAMIGUIN |  | COMPLETED | 2019-10-09 | - |  | 2018 AM-OTHERS | 1
5 | SAGAY | 0 | 4 | COMPLETED | #REF! | #REF! |  | 2018 SALINTUBIG | 1
| SAGAY | BRGY. BUGANG TO BRGY. MAYANA |  | COMPLETED | 2019-04-25 | - |  | 2018 AM-WATER | 1
| SAGAY | SITIO KILOMOY, BRGY. BACNIT |  | COMPLETED | 2019-02-27 | - |  | 2018 AM-WATER | 1
| SAGAY | BRGY. MAYANA |  | COMPLETED | 2019-02-27 | - |  | 2018 AM-LAR | 1
LANAO DEL NORTE
1 | BACOLOD | Dimarao | 2 | COMPLETED | #REF! | #REF! | #REF! | 2018 SALINTUBIG |  | 1
| BACOLOD | BABALAYA |  | COMPLETED | 2019-04-24 | - |  | 2018 AM-LAR | 1
2 | BALO-I | BARANGAY ABAGA | 2 | COMPLETED | 2019-04-01 | - |  | 2018 AM-LAR | 1
| BALO-I | BRGY. CORMATAN TO SIGAYAN |  | COMPLETED | 2019-04-01 | - |  | 2018 AM-LAR | 1
3 | BAROY | PUROK 2 & 3, MALIWANAG | 1 | COMPLETED | 2019-03-07 | - | - | 2018 AM-LAR | 1
4 | ILIGAN CITY
5 | KAPATAGAN | POBLACION | 1 | COMPLETED | 2019-04-22 | - | - | 2018 AM-LAR | 1
6 | KAUSWAGAN | Inudaran | 8 | COMPLETED | #REF! | #REF! |  | 2018 SALINTUBIG | 1
| KAUSWAGAN | Paiton |  | COMPLETED | #REF! | #REF! |  | 2018 SALINTUBIG | 1
| KAUSWAGAN | TUGAR |  | COMPLETED | 2019-03-25 | - |  | 2018 AM-WATER | 1
| KAUSWAGAN | BARAASON |  | COMPLETED | 2019-03-25 | - |  | 2018 AM-WATER | 1
| KAUSWAGAN | KAWIT ORIENTAL |  | COMPLETED | 2019-02-22 | - |  | 2018 AM-LAR | 1
| KAUSWAGAN | KAWIT OCCIDENTAL |  | COMPLETED | 2019-03-08 | - |  | 2018 AM-LAR | 1
| KAUSWAGAN | POBLACION |  | COMPLETED | 2019-02-22 | - |  | 2018 AM-LAR | 1
| KAUSWAGAN | UPPER BAGUMBAYAN |  | COMPLETED | 2019-04-02 | - |  | 2018 AM-OTHERS | 1
7 | KOLAMBUGAN | INUDARAN | 1 | COMPLETED | 2019-04-23 | - | - | 2018 AM-LAR | 1
8 | LALA | 0 | 2 | 85% Physical Accomplishment | #REF! | #REF! | #REF! | 2018 SALINTUBIG |  | 1
| LALA | REBE |  | COMPLETED | 2019-03-04 | - |  | 2018 AM-LAR | 1
9 | LINAMON | BARANGAY MAG-ONG | 5 | COMPLETED | 2019-06-20 | - |  | 2018 AM-LAR | 1
| LINAMON | BARANGAY BOSQUE |  | COMPLETED | 2019-02-04 | - |  | 2018 AM-LAR | 1
| LINAMON | BARANGAY ROBOCON |  | COMPLETED | 2019-03-08 | - |  | 2018 AM-LAR | 1
| LINAMON | DRRMO/POBLACION |  | COMPLETED | 2019-07-19 | - |  | 2018 AM-OTHERS | 1
| LINAMON | POBLACION |  | COMPLETED | 2019-03-08 | - |  | 2018 AM-OTHERS | 1
10 | MAGSAYSAY | 0 | 2 | COMPLETED | #REF! | #REF! |  | 2018 SALINTUBIG | 1
| MAGSAYSAY | POBLACION TO LEMONCRET |  | COMPLETED | 2019-03-25 | - |  | 2018 AM-LAR | 1
11 | MAIGO | BALAGATASA | 1 | COMPLETED | 2019-04-26 | - | - | 2018 AM-LAR | 1
12 | MATUNGAO | BRGY. BATANGAN | 1 | COMPLETED | 2019-03-08 | - | - | 2018 AM-LAR | 1
13 | MUNAI | PANGGAO-TAMPARAN | 1 | 23.91% Physical Accomplishment | 2020-05-05 | 0 | 0 | 2018 AM-LAR |  | 1
14 | NUNUNGAN | BARANGAY LUPITAN | 2 | COMPLETED | 2019-03-08 | - |  | 2018 AM-WATER | 1
| NUNUNGAN | BARANGAY RABARAN |  | COMPLETED | 2019-03-08 | - |  | 2018 AM-OTHERS | 1
15 | PANTAO RAGAT | BARANGAY CABASAGAN | 1 | COMPLETED | 2019-03-26 | - | - | 2018 AM-LAR | 1
16 | PANTAR | BRGYS. CAMPONG, POBLACION & PANTAR WEST (BANGCAL) | 3 | COMPLETED | 2019-12-23 | - |  | 2018 AM-WATER | 1
| PANTAR | BRGYS. KALANGANAN EAST TO LOWER KALANGANAN (TANCAL) |  | COMPLETED | 2019-12-23 | - |  | 2018 AM-WATER | 1
| PANTAR | LUMBA PUNOD TO SUNDIGA PUNOD |  | COMPLETED | 2018-09-11 | - |  | 2018 AM-LAR | 1
17 | POONA PIAGAPO | BRGY. NUNANG TO BRGY. POBLACION | 1 | 37.76% Physical Accomplishment | 2020-06-26 | 0 | 0 | 2018 AM-LAR |  | 1
18 | SALVADOR | BARANGAY PADIANAN | 1 | COMPLETED | 2019-04-24 | - | - | 2018 AM-LAR | 1
19 | SAPAD | BARANGAY PANOLOON TO BARANGAY KATIPUNAN | 1 | COMPLETED | 12/21/2018 | - | - | 2018 AM-LAR | 1
20 | SULTAN NAGA DIMAPORO | Capocao | 5 | COMPLETED | #REF! | #REF! | #REF! | 2018 SALINTUBIG | 1
| SULTAN NAGA DIMAPORO | Topocon (Capocgo) |  | COMPLETED | #REF! | #REF! |  | 2018 SALINTUBIG | 1
| SULTAN NAGA DIMAPORO | Mabuhay |  | COMPLETED | #REF! | #REF! |  | 2018 SALINTUBIG |  | 1
| SULTAN NAGA DIMAPORO | BARANGAYS MAMAGUM, BANGAAN, SIGAYAN |  | COMPLETED | 2019-06-20 | - |  | 2018 AM-WATER | 1
| SULTAN NAGA DIMAPORO | SND, LDN |  | COMPLETED | 2019-09-09 | - |  | 2018 AM-OTHERS | 1
21 | TAGOLOAN | BRGY. KIAZAR | 1 | CANCELLED | 2019-03-04 | - | - | 2018 AM-LAR |  |  |  |  | 1
22 | TANGCAL | BARANGAY BUBONG TO LINAO | 1 | COMPLETED | 2019-07-03 | - | - | 2018 AM-LAR | 1
23 | TUBOD | Baris (Lumangculob) | 4 | COMPLETED | #REF! | #REF! |  | 2018 SALINTUBIG | 1
| TUBOD | Dalama |  | COMPLETED | #REF! | #REF! |  | 2018 SALINTUBIG | 1
| TUBOD | Palao |  | COMPLETED | #REF! | #REF! |  | 2018 SALINTUBIG | 1
| TUBOD | POBLACION (Legaspi - Gom-os) |  | COMPLETED | 2019-04-23 | - |  | 2018 AM-LAR | 1
MISAMIS OCCIDENTAL
1 | ALORAN | Palayan | 4 | COMPLETED | #REF! | #REF! |  | 2018 SALINTUBIG | 1
| ALORAN | San Pedro |  | COMPLETED | #REF! | #REF! |  | 2018 SALINTUBIG | 1
| ALORAN | Sinampongan |  | COMPLETED | #REF! | #REF! |  | 2018 SALINTUBIG | 1
| ALORAN | BRGY. TUBURAN |  | COMPLETED | 2020-01-31 | 0 |  | 2018 AM-LAR | 1
2 | BALIANGAO | BRGY. MISOM - BPLS ROAD | 1 | COMPLETED | 2019-05-03 | - | - | 2018 AM-LAR | 1
3 | BONIFACIO | Dullan | 2 | COMPLETED | #REF! | #REF! |  | 2018 SALINTUBIG | 1
| BONIFACIO | BOLINSONG |  | COMPLETED | 12/20/2018 | - |  | 2018 AM-LAR | 1
4 | CALAMBA | BARANGAY LIBERTAD | 1 | COMPLETED | 2019-03-29 | - | - | 2018 AM-LAR | 1
5 | CLARIN | SEGATIC DAKU AND CABUNGA-AN | 1 | COMPLETED | 2/18/019 | - | - | 2018 AM-LAR | 1
6 | CONCEPCION | BRGY. NEW CASUL | 1 | CANCELLED | 2020-01-10 | - | - | 2018 AM-LAR |  |  |  |  | 1
7 | DON VICTORIANO | PUROK 5, LALUD | 1 | COMPLETED | 2019-09-09 | - | - | 2018 AM-LAR | 1
8 | JIMENEZ | BRGY. CORRALES, TARAKA, NAGA, NACIONAL, STA. CRUZ, PALILAN, AND TABO-O | 1 | COMPLETED | 2020-01-10 | 0 | 0 | 2018 AM-WATER | 1
9 | LOPEZ JAENA | BRGY. RIZAL | 1 | COMPLETED | 2019-06-24 | - | - | 2018 AM-LAR | 1
10 | OROQUIETA CITY |  | 0
11 | OZAMIS CITY |  | 0
12 | PANAON | BRGY. SAN ROQUE | 2 | COMPLETED | 2019-08-01 | - |  | 2018 AM-LAR | 1
| PANAON | BRGY. PUNTA |  | COMPLETED | 2019-08-01 | - |  | 2018 AM-LAR | 1
13 | PLARIDEL | SITIO TAGAYTAY - BRGY. DIVISORIA | 2 | COMPLETED | 2019-02-18 | - |  | 2018 AM-LAR | 1
| PLARIDEL | PUROK PARPAGAYO - BRGY. LAO PROPER |  | COMPLETED | 2019-02-18 | - |  | 2018 AM-LAR | 1
14 | SAPANG DALAGA | SALIMPUNO TO CAPUNDAG ROAD SECTION | 1 | COMPLETED | 2019-06-27 | - | - | 2018 AM-LAR | 1
15 | SINACABAN | LIBERTAD ALTO | 1 | COMPLETED | 2019-02-22 | - | - | 2018 AM-LAR | 1
16 | TANGUB CITY
17 | TUDELA | Gala | 3 | COMPLETED | #REF! | #REF! |  | 2018 SALINTUBIG | 1
| TUDELA | Yahong |  | COMPLETED | #REF! | #REF! |  | 2018 SALINTUBIG | 1
| TUDELA | YAHONG |  | COMPLETED | 2019-06-24 | - |  | 2018 AM-LAR | 1
MISAMIS ORIENTAL
1 | ALUBIJID | BARANGAY LOGUILO | 1 | COMPLETED | 2019-12-24 | - | - | 2018 AM-LAR | 1
2 | BALINGASAG | SITIO VENCER, BARANGAY COGON | 1 | COMPLETED | 2019-03-20 | - | - | 2018 AM-LAR | 1
3 | BALINGOAN | MUNICIPAL WIDE | 2 | 90.00% Physical Accompishment | 2020-06-23 | 0 | 0 | 2018 AM-OTHERS |  | 1
| BALINGOAN | MUNICIPAL WIDE |  | COMPLETED | 2019-09-16 | 0 |  | 2018 AM-OTHERS | 1
4 | BINUANGAN | BARANGAY DAMPIAS, MOSANGOT, POBLACION AND MABINI | 1 | COMPLETED | 2020-06-23 | 0 | 0 | 2018 AM-WATER |  | 1
5 | CAGAYAN DE ORO CITY |  | 1
6 | CLAVERIA | SITIO IMPAKIBIL, APOSKAHOY | 1 | COMPLETED | 7/24/2019 | - | - | 2018 AM-LAR | 1
7 | EL SALVADOR CITY |  | 0
8 | GINGOOG CITY |  | 0
9 | GITAGUM | PUROK 6, G.PELAEZ | 1 | COMPLETED | 2019-02-06 | - | - | 2018 AM-LAR | 1
10 | INITAO | APAS, INITAO | 1 | COMPLETED | 2020-06-23 | 0 | 0 | 2018 AM-OTHERS | 1
11 | JASAAN | BARANGAY APLAYA | 1 | COMPLETED | 2020-03-30 | 0 | 0 | 2018 AM-WATER |  | 1
12 | KINOGUITAN | MUNICIPAL WIDE, BARANGAY KAGUMAHAN | 2 | COMPLETED | 2020-06-23 | 0 | 0 | 2018 AM-WATER |  | 1
| KINOGUITAN | BRGY. CALUBO TO BRGY. KITOTOK ROAD |  | COMPLETED | 2020-06-23 | 0 |  | 2018 AM-LAR |  | 1
13 | LAGONGLONG | SAPONG-AGONG GAMAY TABOK | 2 | COMPLETED | 2019-04-03 | - |  | 2018 AM-LAR | 1
| LAGONGLONG | SAPONG, TABOK |  | COMPLETED | 2019-04-03 | - |  | 2018 AM-LAR | 1
14 | LAGUINDINGAN | BARANGAY TUBAJON | 1 | COMPLETED | 2019-10-28 | - | - | 2018 AM-OTHERS | 1
15 | LIBERTAD | PUROK 10 (TAMBO), BRGY. POBLACION | 1 | COMPLETED | 2019-08-12 | - | - | 2018 AM-LAR | 1
16 | LUGAIT | POBLACION | 1 | 78.00% Physical Accomplishment | 2020-03-03 | 0 | 0 | 2018 AM-WATER |  | 1
17 | MAGSAYSAY | CABUBUHAN-KAUSWAGAN | 1 | COMPLETED | 2016-07-10 | - | - | 2018 AM-LAR | 1
18 | MANTICAO | PANIANGAN, POBLACION, PUNTA SILUM | 1 | COMPLETED | 2020-01-10 | 0 | 0 | 2018 AM-WATER | 1
19 | MEDINA | P-2 TO P-3, BRGY. ROAD, SAN JOSE | 2 | COMPLETED | 2019-05-28 | - |  | 2018 AM-LAR | 1
| MEDINA | P-6, PAHINDONG |  | COMPLETED | 2019-05-28 | - |  | 2018 AM-LAR | 1
20 | NAAWAN | BARANGAY MAPULOG | 1 | COMPLETED | 2019-05-24 | - | - | 2018 AM-LAR | 1
21 | OPOL | BARANGAY AWANG | 1 | COMPLETED | 2019-05-28 | - | - | 2018 AM-LAR | 1
22 | SALAY | SITIO SALAHON, BRGY. ALIPUATON | 1 | COMPLETED | 2019-04-15 | - | - | 2018 AM-LAR | 1
23 | SUGBONGCOGON | BARANGAY MANGGA | 1 | COMPLETED | 2019-04-08 | - | - | 2018 AM-LAR | 1
24 | TAGOLOAN | NATUMOLAN | 2 | CANCELLED | 2019-12-03 | - |  | 2018 AM-WATER |  |  |  |  | 1
| TAGOLOAN | POBLACION |  | CANCELLED | 2020-01-10 | - |  | 2018 AM-LAR |  |  |  |  | 1
25 | TALISAYAN | BARANGAY BUGDANG | 2 | COMPLETED | 2020-06-05 | 0 | 0 | 2018 AM-LAR |  | 1
| TALISAYAN | BARANGAY MAGKARILA |  | COMPLETED | 2020-06-05 | 0 |  | 2018 AM-LAR |  | 1
26 | VILLANUEVA | SITIO BANBAN TO SITIO MADRID, BRGY. LOOC | 1 | COMPLETED | 2020-06-23 | 0 | 0 | 2018 AM-LAR |  | 1
1
|  | Grand Total No. of Project | 143 | [5 empty] | COMPL | ON-GO | PROC |  | CANCE
|  | GrandTotal # of Swa Sub. | #REF!
|  | Completed | 117
|  | On-going | 19
|  | Procurement Process | 0
|  | Cancelled | 5